FROM PREDICTION TO PRODUCTION

A THREE-ACT STRATEGY FOR ELBERT PALMER, THE FORWARD BUILDING SYSTEM, AND MERGE4WARD MANUFACTURING

Merge 4 Design LLC  ×  L.E.E.P., Inc.  |  M4Di Predevelopment Intelligence

July 8, 2026  |  Internal Team Strategy Document  |  Confidential

On April 9, 2026, M4Di completed a routine predevelopment analysis of a vacant site at 1212 Lobdell Street, Wilmington DE — a former elementary school on 1.39 acres in the Southbridge neighborhood. We were engaged by WHA to assess development potential. We ran the site through our OI Tool, modeled three construction scenarios, identified the brownfield risk, and recommended 36 units at $263K/unit as the primary development path.

Three months later — July 6, 2026 — the Wilmington Neighborhood Conservancy Land Bank (WNCLB) published a legal notice in the News Journal advertising an RFQ for a qualified developer partner to construct 30 two-story townhomes on the same site. Their project architect had priced construction at $300,000+ per unit. Their total GFA target: 45,000 square feet.

Our April analysis produced 45,360 square feet. Our modular cost estimate was $263,000 per unit. The M4Di methodology was accurate to within 1% of GFA and 12% below the developer's own budget estimate — three months before the RFQ was issued.

This document lays out what we do next.

01  THE M4Di PROOF — HOW WE CALLED THIS IN APRIL

1.1  What We Analyzed

In April 2026, under document M2_2026_004, M4Di conducted a Gate 0 ROM analysis of 1212 Lobdell Street for WHA. At the time, WHA believed they had site control. The analysis proceeded on standard ALDi Gate 0 methodology: confirm site dimensions, apply City of Wilmington R-3 zoning standards, run three construction type scenarios, model unit economics, and flag data gaps.

| METRIC | M4Di ANALYSIS (April 2026) | WNCLB RFQ (July 2026) | VARIANCE |
| --- | --- | --- | --- |
| Total GFA | 45,360 SF | 45,000 SF | +360 SF / 0.8% |
| Unit Count (recommended) | 36 units (Scenario I) | 30 units (RFQ specification) | M4Di exceeded by +20% |
| Unit Size | 1,260 SF | 1,500 SF | -240 SF (community choice) |
| Construction Cost / Unit | $263,462 (Modular / Scen. B) | $300,000+ (Freel estimate) | M4Di $37K below / 12% |
| Brownfield Risk | Flagged as CRITICAL BLOCKING gap — Phase I ESA required | DNREC BDA confirmed — active since June 2024 | M4Di methodology caught it |
| Zoning Applied | City of Wilmington R-3 (Ch.48 — confirmed correct) | City of Wilmington R-3 | Exact match |

1.2  Why the GFA Match Matters

The convergence of 45,360 SF (M4Di) and 45,000 SF (WNCLB) on the same site is not coincidental. Both analyses read the same site constraints — 175 ft frontage, 352.6 ft depth, R-3 setbacks, 10-unit row limit — and arrived at the same total buildable area. The 240 SF per-unit difference reflects the community's preference for larger units, not a different site reading. The M4Di methodology independently produced the correct answer on an active RFQ before the RFQ existed.

1.3  The Brownfield Call — Our Most Important Accuracy

In the April data gaps list, M4Di flagged Phase I ESA as a HIGH-impact blocking item: "Site history as school facility. Possible asbestos, underground tanks, contaminated soil." DNREC's Brownfields Development Agreement for the Elbert Palmer site (Site ID DE-1857) was publicly noticed in June 2024 — two years before our analysis. We identified the risk through methodology alone, without knowing the BDA existed. That is predevelopment intelligence operating as designed.

FOR WELLS FARGO / ENTERPRISE COMMUNITY ROUND 2 SELECTION: The Elbert Palmer analysis demonstrates M4Di's core value proposition in a live, verifiable context: we analyzed a site three months before an RFQ was issued, produced GFA within 1% of the developer's own program, priced construction 12% below the developer's estimate, and independently identified a brownfield risk that was confirmed by DNREC. We are now competing to develop that same site. This is not a hypothetical. This is the platform working in the real world.

02  THE OPPORTUNITY — ELBERT PALMER TOWNHOMES RFQ

2.1  What This Is

The Wilmington Neighborhood Conservancy Land Bank (WNCLB, est. 2016 — Delaware's first land bank) is seeking a qualified developer partner to construct 30 two-story townhomes at the former Elbert-Palmer Elementary School site, 1212 Lobdell Street, Southbridge, Wilmington DE 19801. The school was transferred from the Christina School District to WNCLB in December 2024.

This is not a design competition. WNCLB has already retained a design consultant and obtained approved, recorded architectural drawings specifying 30 units across 6 buildings at 1,500 SF per unit. The winning respondent builds to those drawings as a developer/builder partner. The competition selects for developer qualification, capital stack capability, cost discipline, brownfield navigation experience, and community benefit commitment.

2.2  The Site and Community Context

| Site | 1212 Lobdell St + 326 Chapel St, Wilmington DE 19801 (Southbridge) |
| --- | --- |
| Tax Parcels | 26-051.30-241 + 26-051.30-245 |
| Site Area | 1.39 acres / 61,705 SF (175 ft × 352.6 ft) |
| Owner | WNCLB — 501(c)(3) land bank. Transferred from Christina School District Dec 2024. |
| WNCLB Director | Bud Freel, Executive Director (former Delaware State Representative) |
| Community History | Elbert-Palmer Elementary, built 1928. Majority-Black, historic Southbridge neighborhood. Deep emotional attachment. School demolished. |
| Unit Count History | Original plan: 20 units + park. Southbridge Civic Association pushed to 30 units, preferring housing over park. |
| Political Engagement | Rep. Frank Cooke (D-New Castle) in working group. Councilwoman Michelle Harlee represents area. Mayor Carney committed $20M housing fund (separate). |
| Brownfield | DNREC BDA confirmed — Site DE-1857. Possible historical hazardous substance release. DNREC contact: Tracy Spinden, (302) 395-2600. |
| Zoning | City of Wilmington R-3 — One-Family Row Houses (Ch.48 Sec.48-134) |

2.3  The RFQ Program

| Total Units | 30 |
| --- | --- |
| Configuration | 6 buildings × 5 units per building |
| Unit Type | 2-story townhome — 3BR / 1.5BA |
| Unit Size | ~1,500 SF |
| Private Amenity | Porch + backyard + personal driveway per unit |
| Affordability Type | For-sale homeownership. ARPA-funded → HUD affordability standard (≤30% gross income for housing costs). |
| Construction Budget | $300,000+ per unit (Freel estimate) → $9,000,000+ total |
| Design Supplied | Approved and recorded site plan + full contract/architectural drawings provided to developer. Developer builds to supplied drawings. |
| Wilmington Median HH Income | $58,671 (U.S. Census) → qualifying price range approx. $130K–$185K at 30% income ratio |

2.4  Critical Deadlines

| DEADLINE | DATE | NOTES |
| --- | --- | --- |
| Mandatory Pre-RFQ Meeting | July 10, 2026 11:00 AM | 226 N. Franklin St, Wilmington. ATTENDANCE REQUIRED TO SUBMIT. Cannot participate in RFQ without attending. |
| Notice of Intent to Respond | July 13 or 18 (confirm at meeting) | Email submission. Deadline date slightly ambiguous in scan — confirm at meeting. Simple letter of intent sufficient. |
| Final RFQ Submission | July 30, 2026 3:00 PM EST | PDF format. Confirm Dropbox RFQ package link at July 10 meeting. |

2.5  Known Funding Already Committed

| SOURCE | AMOUNT | PURPOSE / STATUS |
| --- | --- | --- |
| State (mini-bond bill, Gov. Carney) | $1,200,000 | Demolition + sitework. Likely expended. |
| ARPA (Federal COVID Relief) | $3,000,000 | $2M+ toward subsidizing homes. Balance for construction/soft costs. Committed to WNCLB. |
| NCC Redirect (sought) | $500,000 | Freel actively negotiating. Not confirmed. |
| COMMITTED TOTAL | $4,200,000 | + $500K sought = $4.7M |
| CONSTRUCTION COST ESTIMATE | $9,000,000+ | At Freel's $300K+/unit × 30 units |
| FUNDING GAP TO CLOSE | ~$4,300,000 – $4,800,000 | Developer must bring capital stack strategy. This is the primary competitive differentiator. |

03  OUR COMPETITIVE POSITION — WHY M4D WINS THIS

3.1  The Role We Are Playing

This is a developer/builder competition — not an architecture competition. The design is done. We are competing to execute it better, finance it smarter, and deliver more community benefit than any other developer who walks through that door. Our competitive advantages are not design — they are predevelopment intelligence, capital stack depth, construction methodology, and community benefit infrastructure.

3.2  Our Six Differentiators

| # | DIFFERENTIATOR | THE ARGUMENT |
| --- | --- | --- |
| 1 | M4Di Cost Intelligence | We independently priced this exact site at $263K/unit — $37K below Freel's $300K estimate — three months before the RFQ. We can deliver 30 homes at or below budget because we already know what this project costs. No other developer in this competition has done a ROM analysis of this site before reading the RFQ. |
| 2 | Capital Stack Depth | Our 6-layer analysis methodology covers DSHA HOME, Catalyst Fund, DNREC brownfield incentives, ARPA compliance, FHLB AHP, and federal programs. We don't just know housing finance — we built a platform around it. |
| 3 | Brownfield Intelligence | We flagged Phase I ESA as a critical blocking risk in April. The DNREC BDA has been active since June 2024. We understand what this site carries and we have a relationship strategy for working with DNREC's process and negotiating appropriate risk allocation with WNCLB before contract execution. |
| 4 | Forward Building System — 4WardSIP | Our proprietary SIP wall assembly (4WardSIP / Barricade Thermo-Brace) can be proposed as a performance-equivalent envelope alternate to whatever the supplied drawings specify. All components carry existing ICC-ES listings — no new testing required. T1 saves 13% vs. stick-frame equivalent. Savings go back to the project. |
| 5 | Off-Site Assembly + Merge4Ward Hub | We propose to build off-site — in a warehouse assembly environment — regardless of the construction type specified. Off-site assembly is the developer's operational decision. It delivers better quality control, year-round production, reduced weather delay, and a training environment for M4Academy workforce development. The finished product meets the construction documents. |
| 6 | L.E.E.P. / M4Academy Community Benefit | We are not just building homes in Southbridge. We are training Southbridge residents in the trades that build those homes — and the trades that will produce homes for Wilmington for years to come. This is the community benefit story no other developer in this RFQ can tell. |

04  THE FORWARD BUILDING SYSTEM — OUR CONSTRUCTION METHODOLOGY

4.1  What It Is

The Forward Building System (FBS) is M4D's proprietary four-tier performance framework for off-site assembled residential and community housing. It is a SIP-based panel system — not volumetric modular. The structural wall is the ACME 6.5" SIP panel (ESR-4689, Neopor GPS) with a Barricade Thermo-Brace SIB R-5 continuous insulation and WRB layer (TER 1507-09). Party walls are 8" CMU continuous from foundation to underside of roof — inherent STC ≥ 50. The system carries all necessary ICC-ES listings. No new UL or ICC testing is required for the specified assembly.

The 4WardSIP is the branded product name for this proprietary assembly — the Thermo-Brace SIP package as a Merge 4 Design / L.E.E.P. product.

4.2  Performance and Cost by Tier

| TIER | T1 Code+ | T2 Zero | T3 Positive | T4 Harvest | NOTES |
| --- | --- | --- | --- | --- | --- |
| Effective R-value | R-21–23 | R-22–24 | R-38+ | R-44+ | Thermally broken assembly |
| Airtightness target | <2.0 ACH50 | <1.0 ACH50 | <0.6 ACH50 | <0.6 ACH50 | Auto-tight — SIP |
| FBS Installed $/SF wall | $33.40 | $39.20 | $48.60 | $52.60 | Mid-Atlantic ROM, June 2026 |
| Stick-frame equivalent | $38.50 | $52.80 | $71.40 | $84.60 | True code-equivalent cost |
| Savings vs. stick-frame | $5.10 (13%) | $13.60 (26%) | $22.80 (32%) | $32.00 (38%) | MEP factory credit included |

4.3  Off-Site Assembly Advantage — Even for Stick-Build

The supplied RFQ drawings may specify conventional stick-frame, CMU, or another system. Regardless of what the drawings specify, we propose to build off-site in a controlled warehouse environment. The finished product meets the construction documents. Where it is assembled is the developer's operational decision.

Off-site assembly — even for conventional stick-frame — delivers:

- Year-round production regardless of weather — no seasonal delay, no rain days, no freeze delays

- Quality-controlled environment — consistent fastening patterns, inspectable assemblies, no field substitution errors

- 80–120 field trade hours saved per unit in full hub operation (SIPA data)

- $2,800–$3,900 per unit in material waste reduction and volume purchasing savings

- A teaching and training environment for M4Academy workforce development — production and education in the same facility

- For 30 units: estimated 2,400–3,600 hours of field labor saved and $84,000–$117,000 in material savings

4.4  The 4WardSIP Alternate Specification Proposal

If the supplied drawings' specifications allow performance equivalence or value engineering alternates, we will propose the 4WardSIP (Thermo-Brace SIB assembly) as a documented cost-saving envelope alternate. The proposal is structured as a benefit to the homebuyers — any savings realized through the alternate are applied to reduce the subsidy gap. WNCLB retains approval authority over any design alternate.

For Elbert Palmer's estimated 27,000 SF of exterior wall area:

- T1 savings: 27,000 SF × $5.10 = ~$138,000

- T2 savings: 27,000 SF × $13.60 = ~$367,000

- Combined with off-site assembly savings: $222,000–$484,000 total construction cost advantage

05  THE MERGE4WARD MANUFACTURING HUB — E. 12TH STREET

5.1  The Site

1400 E. 12th Street (parcel 2604500006) is part of a three-parcel industrial campus in the Brandywine Industrial Complex, Wilmington DE 19802 — on the Brandywine Creek waterfront, 9.19 acres (1400 alone), 11.75 acres in the three-parcel assembly. Owner: Brandywine Realty LLC (Paterson NJ). Current tenants include Advantage Building Supply — a building materials operation that is directly on-thesis for a manufacturing supply chain story.

| Parcels in Assembly | 1330 E. 12th (2 ac) + 1340 E. 12th (0.56 ac) + 1400 E. 12th (9.19 ac) = 11.75 ac total |
| --- | --- |
| Owner | Brandywine Realty LLC, Paterson NJ — acquired Oct 2020 ($10 intra-entity transfer) |
| Assessed Value (1400 alone) | $14,682,000 (Land: $129K + Structure: $14,553K) — 2025 reassessment |
| Asking Price (3 parcels) | $10,000,000 — buying below one parcel's assessed value with 2.6 additional acres |
| Zoning | 26M-2 General Industrial + 26W1 Waterfront Manufacturing |
| Constraints | Wetlands-LU, State Wetlands, Floodplain overlays — creek-edge portions restricted. PCA and FEMA FIRM review required. |
| Tenants | Advantage Building Supply (anchor, on-thesis); cell tower ($21,600/yr lease); others TBD pending rent roll |
| OED Connection | Sean Park at City of Wilmington OED suggested this site. Existing city awareness of property and potential. |
| Census Tract | 30.02 — QCT status for NMTC to be confirmed |

5.2  The Vision — Merge4Ward Manufacturing + Training Hub

The E. 12th Street campus is the permanent home of the Merge4Ward Manufacturing and Sustainable Innovative Building Technology Training Hub — a dual-purpose facility that assembles Forward Building System components and educates the next generation of Wilmington construction workers in the same building, simultaneously.

- Panel assembly line: SIP cutting, SAPK connector kit staging, prefab wet wall modules, cabinet modules, flooring pre-cut kits — all Forward Building System Phase 1 enhancements

- Year-round production: weather-independent schedule, assembly-line quality control, zero site exposure during fabrication

- M4Academy workforce training: CNC machinist, structural assembly tech, quality control inspector, logistics coordinator — $45K–$65K+ positions accessible to workers with vocational training

- Advantage Building Supply as anchor tenant and potential supply chain partner — building materials already on site

- Cell tower lease ($21,600/yr) as passive contract income from day one

- Merge4Ward Phase 1 related-party lease ($260,000/yr) as anchor income for the operating pro forma

5.3  The E. 12th Financial Model (M4Di FeasOps G0 ROM)

| LINE ITEM | AMOUNT | NOTES |
| --- | --- | --- |
| Acquisition — 3-parcel assembly | $10,000,000 | ~$50/SF on placeholder 200K SF — well below assessed improvements on 1400 alone |
| Closing + transaction costs (2%) | $200,000 |  |
| Due diligence package | $150,000 | Phase I + targeted Phase II, ALTA survey, PCA, rent-roll audit |
| Phase 1 renovation (panel line bay) | $3,400,000 | One bay fully retrofitted for panel assembly line |
| Pilot-to-production equipment | $2,000,000 | EDA Build to Scale / DEMEP target |
| Deferred maintenance / site | $750,000 | Pending PCA |
| Soft costs + contingency | $1,414,500 |  |
| TOTAL PROJECT COST | $17,914,500 |  |
| Stabilized NOI (third-party leases + M4W anchor) | $731,048/yr | Yield on cost: 4.1% — this behaves like real estate |
| Supportable senior debt | $7,053,947 | 6.75% / 25-yr placeholder rate |
| GAP TO CLOSE (grant + equity stack) | $10,860,553 | See funding stack in Section 7 |

06  THE THREE-ACT STRATEGY — HOW IT ALL CONNECTS

These are not three separate opportunities. They are three acts of the same play. Each one creates the conditions for the next. The sequencing is intentional.

ACT I — WIN ELBERT PALMER AS DEVELOPER (July–December 2026) M4D competes as developer/builder partner for the 30-unit, $9M Elbert Palmer Townhomes project. What this act accomplishes: - Establishes M4D as a qualified developer in Wilmington — not just an architect, not just a predevelopment consultant, but an entity that executes projects - Produces the first off-site assembly production run for the Forward Building System in a leased interim warehouse facility - Proposes the 4WardSIP as a value-engineering envelope alternate — if approved, generates $138K–$484K in cost savings returned to the project - Creates the live demonstration case for HABC Wells Fargo Round 2: "We analyzed this site, then we built it" - Opens the community trust relationship with Southbridge Civic Association, Rep. Frank Cooke, and Councilwoman Harlee - Generates the first revenue stream directly attributable to the Forward Building System - Creates the documented project record that strengthens the Merge4Ward grant applications for E. 12th Street

ACT II — LOI AND ACQUISITION OF E. 12TH STREET (Concurrent with Act I) While the Elbert Palmer process is in motion, advance the E. 12th Street acquisition in parallel. These two moves are not sequential — they are simultaneous. What this act accomplishes: - Locks the Merge4Ward hub site before the Elbert Palmer project demonstrates its value and drives up interest in the property - OED connection (Sean Park suggested this site) gives us first-mover intelligence and potential city backing for the acquisition - The Elbert Palmer win — or even the submission and shortlisting — is sufficient evidence of manufacturing demand to begin LOI negotiations - The $10M asking price is below the assessed value of one parcel alone ($14.68M) — the acquisition is undervalued relative to income-producing potential - NMTC eligibility (if tract 30.02 is QCT — confirm this week) unlocks $3M in tax credit equity that changes the entire financing structure - Advantage Building Supply as existing anchor tenant generates immediate on-thesis income and supply chain narrative

ACT III — MERGE4WARD MANUFACTURING + TRAINING HUB LAUNCH (2027) E. 12th Street becomes the permanent home of the Forward Building System — the manufacturing facility, the training hub, and the workforce development anchor for Wilmington. What this act accomplishes: - Merge4Ward enters full panel assembly production — SIP cutting, SAPK connector staging, prefab wet wall modules, cabinet modules, flooring pre-cut kits — all 16 FBS hub enhancements operational - M4Academy workforce training operates year-round in the same facility: CNC, structural assembly, QC inspector, logistics coordinator — trades at $45K–$65K+ accessible to Wilmington residents - Advantage Building Supply as anchor tenant: building materials on site + potential supply chain integration - Five-partner Merge4Ward team: David (architecture + technical system), Trevor (business development), Leo (operations + grants), Travis (BIM + process documentation), Gwen (grant strategy + community partnerships) - The HABC Wells Fargo grant outcome — Round 3 finalists November 2026, winners Winter 2027 — funds the hub's technical research and workforce development program - Governor of Delaware meeting (Q3/Q4 2026): position Merge4Ward as proof-of-concept for DE Skills Compact / vocational pipeline policy. Elbert Palmer is the evidence.

07  FUNDING STRATEGY

7.1  Elbert Palmer — Closing the $4.3M–$4.8M Developer Gap

The RFQ submission (July 30) requires a credible capital stack strategy — not committed capital. The goal is to assemble letters of interest, letters of intent, and eligibility confirmations from multiple sources that demonstrate a realistic path to closing the gap. The following stack is achievable on the July 30 timeline.

| FUNDING SOURCE | TARGET AMOUNT | WHAT IS NEEDED BY JULY 30 | NOTES |
| --- | --- | --- | --- |
| Private Investor | $1,500,000–$2,000,000 | LOI — in motion | Most flexible and fastest source. LOI being pursued. |
| WNCLB Land Value as Equity | $750,000–$1,000,000 | Negotiate July 10 meeting | If WNCLB contributes land value as subordinate equity rather than requiring land purchase, gap reduces by this amount immediately. Ask Freel directly. |
| Delaware Catalyst Fund (Cinnaire) | $1,050,000 | Eligibility letter from Cinnaire | $35K/unit × 30 units. Cinnaire administers. 80–120% AMI for-sale housing. Call Cinnaire this week before July 10 meeting. |
| DSHA HOME Investment Partnerships | $500,000–$1,500,000 | Letter of intent to consider application | Competitive round — needs letter of support from DSHA confirming eligibility and interest. OED relationship (Sean Park) may facilitate. |
| DNREC Brownfield Incentives | $300,000–$500,000 | Confirm scope at Tracy Spinden call | EPA Brownfields Cleanup Grant (up to $500K). DE VCP program. Call Tracy Spinden (302) 395-2600 this week. If remediation is in the $9M budget, separating it via brownfield funding reduces net construction cost. |
| FHLB Affordable Housing Program (AHP) | $500,000–$750,000 | Sponsoring bank letter | Federal Home Loan Bank of Pittsburgh serves Delaware. Up to $750K per project. Requires a sponsoring member bank. Identify banking relationship this week. |
| Mayor's $20M Housing Fund | Unknown / TBD | Ask at July 10 meeting | Not currently allocated to Elbert Palmer. Worth direct ask at meeting or through OED. Even $500K from this fund signals city partnership. |
| 4WardSIP / Off-Site Assembly Savings | $222,000–$484,000 | Reflected in cost proposal | Not external funding — internal cost discipline. Reduces the gap rather than filling it. Positions our bid below $300K/unit. |
| TOTAL STACK TARGET | $4,822,000–$6,284,000 | Full gap coverage + cushion | Letters and LOIs needed by July 30, not committed capital. |

NOTE ON LIHTC: Low Income Housing Tax Credits (LIHTC) do NOT apply to for-sale homeownership. LIHTC is a rental housing program. Do not include LIHTC in any Elbert Palmer funding strategy.

7.2  Merge4Ward / E. 12th Street — Closing the $10.86M Manufacturing Gap

The E. 12th Street acquisition and manufacturing hub capitalization requires a different stack — industrial real estate financing with manufacturing grants and mission capital layered on top of senior debt. The M4Di FeasOps workbook at G0 produces the following target stack.

| FUNDING SOURCE | TARGET | STATUS + PATHWAY |
| --- | --- | --- |
| Senior Debt (commercial real estate loan) | $7,053,947 | Supportable from $731K stabilized NOI at 6.75%/25-yr. SBA 504 alternate if Merge4Ward occupancy qualifies. |
| NMTC Net Equity | $3,000,000 | CONFIRM QCT STATUS FOR TRACT 30.02 IMMEDIATELY. If qualified, NMTC is the single largest grant-equivalent source in the stack. Partner: Reinvestment Fund or LISC as CDE. |
| EDA Build to Scale (pilot production line) | $1,500,000 | Direct program fit — advanced manufacturing, underserved community, job creation. Applicant entity structure to be confirmed. |
| DNREC HSCA Brownfield Grant/Loan | $750,000 | Legacy industrial site + substation adjacency. Certify brownfield status early; fund remediation through grant rather than project budget. |
| DEDO Strategic Fund / DE Incentives | $500,000 | Job-creation performance grant/loan through Delaware Economic Development Office. Governor meeting narrative asset — DE Skills Compact hook. |
| CDFI / PRI Soft Debt | $1,000,000 | Mission-aligned lenders on workforce + supply-chain story. NCALL Research, Reinvestment Fund, impact investors. |
| DEMEP Matching / Technical Assistance | $150,000 | DE Manufacturing Extension Partnership — process engineering + workforce training design assistance. |
| Sponsor Equity (Merge4Ward partners) | $3,960,553 | Balance remaining after debt and grants. Five-partner Merge4Ward team equity commitment. Includes HABC grant proceeds if awarded. |
| TOTAL (= Project Cost) | $17,914,500 | G0 ROM — update at G1 with actual rent roll and PCA |

08  THE HABC / WELLS FARGO GRANT NARRATIVE

The Wells Fargo / Enterprise Community Housing Built to Last Challenge Round 2 semifinalists are notified in late July 2026 — the same month as the Elbert Palmer RFQ submission. The timing is not coincidental. It is an asset.

The Story We Tell Wells Fargo

"In April 2026, our M4Di platform analyzed 1212 Lobdell Street as a routine predevelopment engagement. We produced a site yield of 45,360 SF, a cost estimate of $263,000 per unit, and flagged an active brownfield risk — all from parcel data and public records. Three months later, the Land Bank published an RFQ for 30 townhomes on that site, with an architect's budget of $300,000 per unit and a total GFA of 45,000 SF. Our methodology was accurate to within 1% of GFA and 12% below the developer's estimate, before the RFQ existed. We are now the developer competing to build those homes — with our Forward Building System, from a warehouse assembly facility we are acquiring on E. 12th Street, with Wilmington residents trained in our M4Academy earning $45,000 to $65,000 per year in the trades that build affordable housing for their city. This is M4Di working in the real world."

This narrative — prediction to production, data to demonstration — is the HABC round 2 competitive differentiator. It is not theoretical. It is happening right now, and the timeline aligns.

Round 2 and Round 3 Timeline Alignment

| DATE | EVENT | CONNECTION TO ELBERT PALMER / MERGE4WARD |
| --- | --- | --- |
| Late July 2026 | Round 2 semifinalists announced | Elbert Palmer RFQ submitted July 30 — simultaneous. If we're a semifinalist, the RFQ submission is our live evidence. |
| Aug 10 – Sep 18, 2026 | Round 2 review window | Elbert Palmer NOI accepted. If we win developer selection, construction planning underway. Merge4Ward LOI on E. 12th St in progress. |
| Nov 2, 2026 | Round 3 finalists announced | Elbert Palmer developer contract executed (if won). E. 12th St acquisition LOI submitted. Construction begins at leased interim hub. |
| Q4 2026 | PHOENIX event window | Post-El Niño reconstruction cycle thesis activated. Forward Building System positioned for climate-resilient forward housing demand. |
| Winter 2027 | Round 3 winners | Elbert Palmer under construction. E. 12th St acquisition closed or in contract. Merge4Ward Phase 1 renovation underway. HABC grant funds the training program. |

09  ACTION ITEMS — SEQUENCED BY PRIORITY

THIS WEEK (July 8–12)

- ATTEND mandatory pre-RFQ meeting — July 10, 11:00 AM, 226 N. Franklin St. Confirm: NOI deadline (July 13 or 18), Dropbox RFQ package link, construction type in supplied drawings, brownfield liability allocation to developer, whether WNCLB will contribute land value as equity. This meeting is the most important 60 minutes of the month.

- Confirm census tract 30.02 QCT (Qualified Census Tract) status using the HUD NMTC mapping tool — free, 10 minutes. This single data point determines whether $3M in NMTC equity is available for E. 12th Street.

- Call Cinnaire (Delaware Catalyst Fund) — confirm Elbert Palmer eligibility and request a letter of intent to consider the project for funding. $35K/unit × 30 units = $1.05M. This is the fastest gap-closer with existing program precedent.

- Call Tracy Spinden at DNREC (302-395-2600) — confirm BDA scope, what obligations transfer to the developer vs. remain with WNCLB, and what brownfield funding is available. This is a go/no-go risk factor.

- Download and review the Dropbox RFQ package (link to be confirmed at July 10 meeting). Confirm construction type specified in drawings — this determines whether 4WardSIP alternate is available.

- Contact OED (Sean Park) — confirm city awareness of E. 12th Street situation, ask what they know about seller motivation, and ask whether any Mayor's housing fund dollars can be directed to Elbert Palmer.

- Confirm Gwen Motley availability and interest in the Merge4Ward five-partner structure and E. 12th Street Training Hub concept. Brief her on Elbert Palmer RFQ timeline.

WEEK OF JULY 14–18 (NOI + STACK ASSEMBLY)

- Submit Notice of Intent to Respond to WNCLB by confirmed deadline. Keep it simple: firm name, contact information, statement of intent. One paragraph.

- Re-pull 1330/1340 E. 12th St parcel cards — original records were illegible. Confirm single-seller control of all three parcels behind the $10M package.

- Initiate contact with Brandywine Realty LLC (Paterson NJ) to confirm seller motivation, asking price posture, and whether three-parcel control is available. Understand the $10 intra-entity transfer history.

- Identify sponsoring member bank for FHLB AHP application. Any existing banking relationship with a FHLB member should be activated this week.

- Contact DSHA — confirm HOME Investment Partnerships program eligibility for Elbert Palmer and request letter of intent. Coordinate with OED relationship if available.

- Begin capital stack research memo: DSHA HOME, Catalyst Fund, FHLB AHP, DNREC brownfield, Mayor's fund, NCC CDBG — document current program status, eligibility, and amount achievable with a letter by July 30.

- Develop the LOI strategy memo for E. 12th Street — price vs. occupancy scenarios (occupied / partially vacant / fully vacant) and what that means for NOI and debt capacity.

WEEK OF JULY 21–30 (RFQ SUBMISSION)

- Draft RFQ submission package — developer qualifications, project approach (off-site assembly + 4WardSIP alternate), capital stack strategy with supporting letters, community benefit plan (M4Academy workforce pipeline + L.E.E.P. partnership), references.

- Assemble all funding letters and LOIs: private investor LOI, Cinnaire eligibility letter, DSHA letter of intent, DNREC brownfield confirmation, FHLB sponsoring bank letter, land value equity confirmation from WNCLB.

- Prepare community benefit narrative — specific, earned, not generic. Name Neighborhood House, name the Civic Association, name what "more than houses" means for this specific neighborhood.

- Submit RFQ package by July 30, 3:00 PM EST via PDF to confirmed submission address. Verify Dropbox link and submission method at July 10 meeting.

- Push all documents from this week to GitHub studio-content repo and update STATUS.md version table.

AUGUST–SEPTEMBER (PARALLEL TRACKS)

- E. 12th Street: Advance LOI and purchase agreement. Retain industrial real estate counsel. Initiate Phase I ESA and ALTA survey. Order PCA.

- NMTC: If QCT confirmed, begin outreach to CDE allocatees (Reinvestment Fund, LISC, Enterprise). NMTC applications typically annual — get into 2026 cycle if possible.

- EDA Build to Scale: Prepare application or letter of intent with manufacturing program narrative. Applicant entity (Merge4Ward LLC vs. M4Di) to be confirmed with counsel.

- HABC Round 2 prep: If semifinalist, prepare presentation with Elbert Palmer as live evidence. The July 30 RFQ submission is the document you show them.

- Identify and lease interim warehouse assembly space (8,000–15,000 SF) for Elbert Palmer off-site assembly program — this is the Phase 0 Merge4Ward hub, before E. 12th Street is operational.

- Governor of Delaware meeting preparation: one-pager positioning Merge4Ward as DE Skills Compact proof-of-concept. Target Q3/Q4 2026 post-grant outcome.

THE BOTTOM LINE Three months ago we did the homework on a site we thought WHA controlled. WHA didn't have the site. But our analysis was right. The site is now an open RFQ, the owner wants a developer, and we are the only team in Delaware that walked in on day one already knowing what this site costs, what it can build, and what it carries underground. Win Elbert Palmer. Build it from a warehouse. Prove the system. Acquire E. 12th Street. Launch Merge4Ward. Everything else follows.

Merge 4 Design LLC  ×  L.E.E.P., Inc.  |  M4Di Predevelopment Intelligence  |  July 8, 2026

Internal team document. Not for external distribution without authorization from M4D leadership.