## COVER
M4Di ¦ OI Tool + ALDi Budget Tracker
1212 Lobdel Avenue — Multi-Unit Affordable Infill ¦ Document M2_2026_004 ¦ Version v1
April 9, 2026 ¦ Gate: G0 — ROM ¦ Lead: Merge 4 Design LLC (M4D) ¦ (c) 2026 M4Di / M4D
PROJECT IDENTITY
Project Code | M2_2026_004 | ALDi document number
Project Name | 1212 Lobdel Avenue — Multi-Unit Affordable Infill
Address | 1212 Lobdel Avenue, Wilmington, DE 19801
Client / Owner | Wilmington Housing Authority (WHA)
Lead Firm | Merge 4 Design LLC (M4D) | M4D holds prime WHA contract
AOR | Aubyn Architecture LLC (subconsultant) | Subconsultant to M4D
ALDi Gate | G0 — ROM | G0=ROM ¦ G1=Feasibility ¦ G2=75%DD ¦ G3=GMP ¦ G4=Closeout
Document Date | April 9, 2026
Version | v1 | Each version is a fresh complete document
Governing Code | City of Wilmington R-3 — One-Family Row Houses (Ch.48) | NOT NCC UDC — City of Wilmington Ch.48 only
SITE & PROGRAM — DATA SPINE
Site Area (SF) | 61705 | Confirmed: 175 ft x 352.6 ft
Site Area (Acres) | 1.39
Site Dimensions | 175 ft x 352.6 ft | Width x Depth
Former Use | School facility — fully cleared | No demolition assumed
Zoning | R-3 | City of Wilmington One-Family Row Houses
Construction Type | B - Off-Site Modular | A=CLT/SIP ¦ B=Modular ¦ C=Stick
Total Units (Scen. I) | 36 | 4 rows x 9 units x 18 ft wide
Units Per Row | 9 | Max 10 per Wilmington building code Sec.504.4.2
Number of Rows | 4 | 4-row layout
Unit Width (ft) | 18 | Exceeds existing 14-16 ft block face stock
Unit Depth (ft) | 35
Unit Size (SF) | 1260 | 18 ft x 35 ft x 2 stories
Total GFA (SF) | 45360 | 36 units x 1260 SF
Front Setback (adopted, ft) | 20 | Exceeds <17 ft contextual avg. New standard.
Rear Setback (required, ft) | 20 | Per Sec.48-155
Site Depth Used (ft) | 240 | 20+4x35+3x20+20 = 240 ft
Surplus Depth (ft) | 112.6 | Parking, garden, bio-retention
COLUMN D — ROM (LOCKED AT GATE 0)
LINE ITEM | AMOUNT ($) | NOTES
Sitework / Civil | 432000
Foundations (modular-spec) | 816480
Modular Factory Units (factory-complete) | 3009600
Freight + Set (crane, ~200 mi) | 540000
Site MEP Tie-Ins + Utility Connections | 306000
Exterior Finish Completion | 726000
Interior Finish Completion (punch-out) | 234000
Shared Open Space / Parking Court | 200000
Landscaping / Fencing / Unit Walks | 162000
HARD COST SUBTOTAL
General Conditions (8%)
OH&P / GC Fee (6%)
Design Contingency (6%)
Soft Costs (12%)
Owner Contingency (5%)
TOTAL PROJECT ROM — COLUMN D (LOCKED)
UNIT ECONOMICS — DATA SPINE OUTPUT
Total Project ROM (= Col D) |  | Locked. Cross-ref to BUDGET TRACKER Col D.
Total Units (Scenario I) |  | From Site & Program above.
Cost Per Unit |  | ROM / units
Target Sales Price (WHA) | 215000 | $200K-$235K WHA program target
Subsidy Gap Per Unit |  | Gap = cost/unit - target
Total Subsidy Gap |  | Gap x units
Catalyst Fund Potential |  | $35K/unit x units
Hard Cost / SF
Total Cost / SF
ENR Index Applied | Mid-Atlantic Q2 2026
Bid Date Assumption | Q4 2026 / Q1 2027
COLOR KEY: Blue = hardcoded input (your data) ¦ Black = formula (do not override) ¦ Dark green = cross-sheet link

## ASSUMPTIONS
PROJECT ASSUMPTIONS & CONTROLS
Input | Value | Notes
Project Name | 1212 Lobdel Avenue — Multi-Unit Affordable Infill | Use a short, consistent project code (e.g., WHACC-2026).
Estimate Date |  | Enter as MM/DD/YYYY. Update with each revision.
Estimate Type | ROM / Conceptual | ROM / Conceptual ¦ Schematic ¦ Design Development ¦ GMP
Project Type | Interior Improvement | Interior Improvement ¦ Adaptive Reuse ¦ New Construction ¦ Mixed-Use
Client / Owner |  | Legal entity name of the owner organization.
Site Address |  | Full property address for zoning lookup reference.
Total Gross Area (SF) | 8700 | Total gross building SF affected by the scope.
Base Region | Delaware | Delaware = M4Di baseline. All unit prices sourced from Delaware competitive bid market.
Selected Pricing Region | New Castle/Wilmington | Must match a region defined in REGIONAL FACTORS sheet.
Weighted Trade Labor Factor |  | Auto-pulled from REGIONAL FACTORS. 1.000x = Delaware baseline. Philadelphia Metro ≈ 1.145x.
COST ESCALATION
ENR Construction Cost Index (CCI) Escalation % | 2.7% | Source: ENR CCI Q1 2026. Update quarterly. Applies to all labor-heavy items.
ENR Building Cost Index (BCI) Escalation % | 4.3% | Source: ENR BCI Q1 2026. Update quarterly. Applies to material-heavy items.
Blended Escalation Rate |  | Formula: average of CCI and BCI. Used in unit price adjusted cost calculation.
Material / Market Factor | 1 | Adjust for procurement pressure, bid climate volatility, or material shortages. 1.000x = neutral.
MARKUPS & CONTINGENCIES
General Conditions % | 8% | Typical range: 6%–10%. Covers on-site supervision, temporary facilities, insurance.
Overhead & Profit (OH&P) % | 10% | Typical range: 8%–12%. Applied to subtotal after GC.
Design Contingency % | 12% | Reduce to 8% at SD; 5% at DD; 0% at GMP. Reflects design development risk.
Existing Conditions Contingency % | 10% | Higher for gut renovations (12%–15%). Covers concealed conditions and substrate damage.
Equipment / Owner Selection Contingency % | 8% | Reduce as owner selections are confirmed. Set to 0% when all allowances are locked.
Bid / Permit / Bonds % | 2% | Covers permitting fees, bid bonds, performance bonds. Adjust for municipality.
Sales Tax % | 0% | Delaware: 0%. Adjust for other jurisdictions. Apply only to taxable material costs if split.
Total Contingency % |  | Sum of all contingency lines. For reference only.
QUICK REFERENCE TOTALS (auto-calculated from BID SUMMARY)
Base Building Subtotal
Equipment Allowances
Subtotal Before Markups
General Conditions
OH&P
Total Contingencies
Bid / Permit / Bonds
TOTAL PROJECT ROM
FEE SCHEDULE CONTROLS (feeds SOFT COSTS sheet)
AIA Project Type Code | C | A=warehouse, B=office, C=school/fitness (M4Di default), D=clinic/theater, E=hospital/research.
Renovation Project? | Yes | Yes adds renovation premium to base architecture fee. WHACC = Yes.

## REGIONAL FACTORS
REGIONAL MARKET FACTORS — Public Data-Based Labor Basket
Region | Carpenters $/hr | Laborers $/hr | Electricians $/hr | Painters $/hr | Concrete Finishers $/hr | Drywall/Ceiling $/hr | Weighted Labor Basket | Region Factor vs. Delaware | Trade | Weight
Delaware | 29.3 | 22.57 | 30.93 | 23.48 | 25.47 | 25.32 |  |  | Carpenters | 30% | Baseline — Delaware statewide OEWS wages. Source: BLS OEWS 2024, State=DE.
New Castle/Wilmington | 29.5 | 22.5 | 30.5 | 22.9 | 25.3 | 25.2 |  |  | Laborers | 20% | New Castle County sub-market proxy. Slightly above state average for urban premium.
Philadelphia Metro | 31.47 | 27.82 | 37.24 | 26.36 | 30.83 | 28.7 |  |  | Electricians | 10% | Philadelphia-Camden-Wilmington MSA. Source: BLS OEWS 2024, MSA=37980.
New Jersey | 35.16 | 34.27 | 38.51 | 31.16 | 34.78 | 29.5 |  |  | Painters | 20% | NJ statewide OEWS 2024, all industries. Higher union density drives premium.
Baltimore Area | 28.74 | 22.99 | 33.83 | 27.86 | 26.34 | 24.13 |  |  | Concrete Finishers | 10% | Baltimore-Columbia-Towson MSA proxy. Source: BLS OEWS 2024, MSA=12580.
Washington DC Metro | 34.5 | 27.1 | 40.2 | 29.5 | 31.2 | 30.4 |  |  | Drywall/Ceiling | 10% | DC-VA-MD-WV MSA. Source: BLS OEWS 2024, MSA=47900. High labor market tightness.
Custom | 0 | 0 | 0 | 0 | 0 | 0 |  |  | TOTAL |  | Enter custom wage rates. Factor auto-calculates vs. Delaware baseline.
NOTE: Weighted Labor Basket is an internal blended labor-only ROM index using BLS OEWS wage data and the trade weightings shown at right. It is not a full construction location factor. ENR City Cost Indexes should be used for full project-level location adjustment when available.

## UNIT PRICE LIBRARY
UNIT PRICE LIBRARY — Architectural / Athletic / Community Facility Scope
Div | Cost Code | Spec Section | Bid Package | Scope Item | Unit | Base Unit Price (Baseline Region) | Region Factor | Escalation Factor | Adjusted Unit Price | Owner Selection Sensitive? | Source / Basis
02 | DEM-01 | 02 41 19 |  | Selective demolition – interior finishes | SF | 6.5 |  |  |  | No | Placeholder. Calibrate to local GC pricing. Range: $4–9/SF for interior gut renovation.
02 | DEM-02 | 02 41 19 |  | Selective demolition – athletic equipment removal | EA | 450 |  |  |  | Yes | Allowance. Depends on equipment type. Coordinate with equipment supplier.
03 | CON-01 | 03 30 00 |  | Concrete housekeeping pad, reinforced (4" slab) | CY | 1450 |  |  |  | No | Includes forming, rebar, pour, finish. Verify structural requirements.
04 | MAS-01 | 04 20 00 |  | CMU infill / repair, reinforced | SF | 28 |  |  |  | No | For openings or damaged block. Includes masonry, grout, block.
05 | MET-01 | 05 52 13 |  | Aluminum/glass guardrail, per ASTM F2923 | LF | 350 |  |  |  | No | IBC-compliant. Includes anchor system. Powder coat finish standard.
05 | MET-02 | 05 52 13 |  | Painted aluminum handrail, 1.5" dia. | LF | 165 |  |  |  | No | Standard IBC rail. Field paint after installation.
06 | CAR-01 | 06 10 00 |  | Rough carpentry, blocking and backing | SF | 18 |  |  |  | No | Includes lumber, installation labor. For equipment attachment points.
07 | INS-01 | 07 21 00 |  | Batt insulation, 3.5" R-13 | SF | 2.5 |  |  |  | No | Faced batt in exterior walls. Energy code compliance item.
08 | DOO-01 | 08 11 13 |  | New HM door frame + hollow metal door + hardware, complete | EA | 3800 |  |  |  | No | Complete unit: frame, door, closer, HW set. ADA lever required.
08 | DOO-02 | 08 11 13 |  | Door frame only – existing door reused | EA | 1200 |  |  |  | No | Replace damaged frame, retain serviceable door and hardware.
09 | FIN-01 | 09 91 00 |  | High-performance corrosion-resistant coating (2-coat system) | SF | 9.5 |  |  |  | No | For pool decks, pump rooms, humid athletic spaces. Tnemec or equal.
09 | FIN-02 | 09 91 00 |  | Standard interior latex paint system (2 coats) | SF | 3.75 |  |  |  | No | Two coat system walls + ceiling. Does not include prep beyond light sanding.
09 | FIN-03 | 09 64 66 |  | Wood athletic floor refinishing – sand, recoat, stripe | SF | 8.5 |  |  |  | No | Per MFMA standards. Includes sanding, 3 coats finish, re-striping.
09 | FIN-04 | 09 65 66 |  | Rubber athletic flooring system (6mm standard thickness) | SF | 14.5 |  |  |  | Yes | Allowance based on Mondo/Ecore/Gerflor. Thickness TBD by owner.
09 | FIN-05 | 09 65 00 |  | VCT replacement / refinishing in place | SF | 7.25 |  |  |  | No | New VCT over existing slab. Includes adhesive, installation, wax.
09 | FIN-06 | 09 51 00 |  | ACT ceiling – grid + tile replacement (2x2 standard) | SF | 8.75 |  |  |  | No | Standard 2x2 ACT. Includes grid, tile, suspension wires. Does not include MEP.
09 | FIN-07 | 09 29 00 |  | GWB partition – 3-5/8" metal stud, taped, primed | SF | 16.5 |  |  |  | No | Full-height partition, per-face cost. Double for both faces.
10 | ACC-01 | 10 28 13 |  | Mirrors, wall-mounted, tempered safety glass | SF | 28 |  |  |  | Yes | Allowance. Size/count TBD by owner. Boxing gym standard: 8'x5' panels.
10 | ACC-02 | 10 26 00 |  | Wall corner guards, stainless steel | LF | 35 |  |  |  | No | Impact-resistant stainless, mechanically attached.
11 | ATH-01 | 11 66 23 |  | Gymnasium wall padding (2" thick, floor to 6') | SF | 36 |  |  |  | Yes | Allowance: Jaypro/Safety Padding/Bison. Color and graphic scope TBD.
11 | ATH-02 | 11 66 23 |  | Scoreboard / control system – gymnasium | EA | 18000 |  |  |  | Yes | Allowance: Daktronics/Watchfire/Electro-Mech. Power/data coordination required.
11 | ATH-03 | 11 66 23 |  | Telescoping bleacher system – gymnasium | LS | 95000 |  |  |  | Yes | Allowance: Jaypro/Irwin/Hussey. Row count, ADA seating, and finish TBD.
11 | ATH-04 | 11 66 23 |  | Basketball backstop system (single court) | EA | 14500 |  |  |  | Yes | Allowance: Jaypro/Porter/Draper J800 or equal. Extension length and mounting TBD.
11 | ATH-05 | 11 66 23 |  | Volleyball post/sleeve system | EA | 3500 |  |  |  | Yes | Allowance: Jaypro 7000-series or equal. Sleeve sleeve coordination with slab.
11 | ATH-06 | 11 66 43 |  | Boxing ring, 14x14, new training ring | EA | 18000 |  |  |  | Yes | Allowance: Title/Ringside/Everlast. Model, ropes, corner pads, canvas TBD.
11 | ATH-07 | 11 66 43 |  | Bag systems / speed bag station – boxing | LS | 14000 |  |  |  | Yes | Allowance: Various. Count, mounting type, and bag style TBD.
15 | PLB-01 | 22 11 16 |  | Plumbing rough-in per fixture (allowance) | EA | 3500 |  |  |  | No | MEP allowance per fixture for minor plumbing modifications. Verify with MEP engineer.
16 | ELC-01 | 26 05 00 |  | Electrical rough-in / circuit additions (allowance) | EA | 2800 |  |  |  | No | MEP allowance per new circuit. Verify panel capacity. Coordinate with MEP.
16 | ELC-02 | 26 05 00 |  | Scoreboard/specialty equipment power feed | EA | 4500 |  |  |  | Yes | Dedicated circuit for scoreboard, PA, or specialty equip. Allowance pending design.
→ ADD NEW SCOPE ITEMS BELOW THIS ROW. Copy formulas in columns I–K from any row above.

## TAKEOFF
QUANTITY TAKEOFF — By Floor / Division / Scope Item
Floor | Area / Zone | Div | Spec Section | Bid Package | Cost Code | Scope Item | Unit | Quantity Source | Quantity | Adj. Unit Cost (from Library) | Line Total | Included? | Comments
LL | Pump Room/Pool Area | 02 | 02 41 19 |  | DEM-01 | Selective demolition – interior finishes | SF | Pump Rm Area | 953 |  |  | Yes
LL | Pump Room/Pool Area | 03 | 03 30 00 |  | CON-01 | Concrete housekeeping pad, reinforced | CY | 11'x7'x6" calc | 1.43 |  |  | Yes | 11 ft x 7 ft x 0.5 ft / 27 = 1.43 CY
LL | Pump Room/Pool Area | 09 | 09 91 00 |  | FIN-01 | High-performance corrosion coating – pump room | SF | Pump Rm Area | 3170 |  |  | Yes | Walls + ceiling + 20% surface factor
LL | Pool Area | 09 | 09 91 00 |  | FIN-01 | High-performance corrosion coating – pool walls | SF | Pool Area | 16300 |  |  | Yes | Pool walls and ceiling + 15% surface factor
LL | Stair Tower | 09 | 09 91 00 |  | FIN-01 | High-performance corrosion coating – stair | SF | Stair Area | 3070 |  |  | Yes | Stair walls and ceiling + 35% surface factor
1F | Bleachers/Balcony | 02 | 02 41 19 |  | DEM-01 | Selective demolition – interior finishes | SF | Balcony Area | 1130 |  |  | Yes
1F | Bleachers/Balcony | 05 | 05 52 13 |  | MET-01 | Aluminum/glass guardrail | LF | Field Measure | 92 |  |  | Yes
1F | Bleachers/Balcony | 09 | 09 65 66 |  | FIN-04 | Rubber athletic flooring system | SF | Balcony Area | 1130 |  |  | Allowance | Thickness TBD by owner
1F | Bleachers/Balcony | 05 | 05 52 13 |  | MET-02 | Painted aluminum handrail | LF | Field Measure | 28 |  |  | Yes | 4 × 7-ft sections in center aisle
1F | Stair Tower | 09 | 09 51 00 |  | FIN-06 | ACT ceiling replacement | SF | Actual Area | 520 |  |  | Yes
2F | Gymnasium/Practice | 09 | 09 64 66 |  | FIN-03 | Wood athletic floor refinishing | SF | Actual Area | 6730 |  |  | Yes
2F | Gymnasium/Practice | 09 | 09 65 00 |  | FIN-05 | VCT replacement/refinishing | SF | Actual Area | 270 |  |  | Yes | Practice room and instructor office
2F | Gymnasium/Practice | 08 | 08 11 13 |  | DOO-01 | New HM door + frame + hardware | EA | Count | 1 |  |  | Allowance
2F | Gymnasium/Practice | 11 | 11 66 23 |  | ATH-02 | Scoreboard / control system | EA | Count | 2 |  |  | Allowance | One main + one practice
2F | Gymnasium/Practice | 11 | 11 66 23 |  | ATH-03 | Telescoping bleacher system | LS | LS | 1 |  |  | Allowance | Row count and ADA layout TBD
2F | Gymnasium/Practice | 11 | 11 66 23 |  | ATH-04 | Basketball backstop (single court) | EA | Count | 4 |  |  | Allowance | Main + 3 side courts
2F | Gymnasium/Practice | 11 | 11 66 23 |  | ATH-05 | Volleyball post/sleeve system | EA | Count | 1 |  |  | Allowance
2F | Gymnasium/Practice | 11 | 11 66 23 |  | ATH-01 | Gymnasium wall padding | SF | Actual Area | 900 |  |  | Allowance | 75 × 2x6 pads
2F | Gymnasium/Practice | 11 | 11 66 23 |  | ATH-01 | Gymnasium wall padding – pillar wraps | SF | Actual Area | 119 |  |  | Allowance | 17 × 2x3.5 pads
3F | Boxing Gym | 02 | 02 41 19 |  | DEM-01 | Selective demolition – interior finishes | SF | Actual Area | 2700 |  |  | Yes
3F | Boxing Gym | 06 | 06 10 00 |  | CAR-01 | Rough carpentry / blocking / backing | SF | Actual Area | 450 |  |  | Yes | Partitions and equipment backing
3F | Boxing Gym | 09 | 09 65 66 |  | FIN-04 | Rubber athletic flooring – boxing | SF | Actual Area | 2500 |  |  | Allowance | Thickness TBD by owner
3F | Boxing Gym | 10 | 10 28 13 |  | ACC-01 | Mirrors, wall-mounted | SF | Actual Area | 240 |  |  | Yes | 8 × 6x5 mirrors
3F | Boxing Gym | 11 | 11 66 43 |  | ATH-06 | Boxing ring, 14x14 training ring | EA | Count | 1 |  |  | Allowance | Model and accessories TBD
3F | Boxing Gym | 11 | 11 66 43 |  | ATH-07 | Bag systems / speed bag station | LS | LS | 1 |  |  | Allowance | Count and mounting TBD
TAKEOFF SUBTOTAL (before markups)
→ ADD NEW TAKEOFF ROWS ABOVE THE SUBTOTAL. Enter Floor, Zone, and Cost Code. Adj. Unit Cost auto-populates from UNIT PRICE LIBRARY via VLOOKUP on Cost Code.

## FLOOR SUMMARY
FLOOR-BY-FLOOR COST SUMMARY
Floor | Base Building Subtotal | Equipment Allowances | Subtotal | General Conditions | OH&P | Contingencies | Bid/Permit/Bonds | Est. Floor Total
LL
1F
2F
3F
TOTAL
↑ Total Project ROM feeds BID SUMMARY and SF BENCHMARK sheets.

## SCENARIO COMP
YIELD & ROM SCENARIO COMPARISON ¦ 1212 Lobdel Ave ¦ City of Wilmington R-3
April 9, 2026 ¦ M2_2026_004 ¦ Merge 4 Design LLC (M4D) ¦ 30-unit WHA target exceeded in Scen. I and II
METRIC | SCN I - 36 UNITS / 18 ft | SCN II - 40 UNITS / 16 ft | SCN III - 24 UNITS / 20 ft
YIELD
Unit Configuration | 4 rows x 9 units | 4 rows x 10 units | 3 rows x 8 units
Unit Width (ft) | 18 | 16 | 20
Unit Size (SF) | 1,260 | 1,120 | 1,520
Total Units | 36 | 40 | 24
Density (du/ac) | 25.9 | 28.8 | 17.3
Site Depth Used | 240 ft | 240 ft | 194 ft
Surplus Depth | 112.6 ft | 112.6 ft | 158.6 ft
vs WHA 30-unit target | +6 units (+20%) | +10 units (+33%) | Below target
CONSTRUCTION TYPE B - MODULAR ROM
Total ROM | $9,200,026 | $9,918,373 | $6,509,701
Cost Per Unit | $255,556 | $247,959 | $271,238
Gap vs $215K Target | ~$40,556/unit | ~$32,959/unit | ~$56,238/unit
Total Subsidy Gap | ~$1,460,016 | ~$1,318,360 | ~$1,349,712
Catalyst Fund ($35K/unit) | $1,260,000 | $1,400,000 | $840,000
Remaining Gap after Catalyst | ~$200,016 | ~$(81,640) | ~$509,712
CONSTRUCTION TYPE A - CLT/SIP ROM
Total ROM (A) | $14,875,352 | $15,005,993 | $11,635,084
Gap vs $215K (A) | ~$198K/unit | ~$160K/unit | ~$270K/unit
CONSTRUCTION TYPE C - STICK ROM
Total ROM (C) | $14,731,123 | $14,797,583 | $11,553,115
Gap vs $215K (C) | ~$194K/unit | ~$155K/unit | ~$266K/unit
M4D RECOMMENDATION
M4D Recommendation | PRIMARY PATH | MAX DENSITY OPTION | QUALITY BENCHMARK

## BID SUMMARY
ROM COST ESTIMATE — EXECUTIVE SUMMARY
Summary Item | Amount | Pricing Basis / Notes
Base Building Subtotal |  | Architectural / interior renovation ROM with quantity-based takeoff. Excludes allowances.
Equipment Allowances |  | Owner-selection-dependent athletic and specialty equipment. Pending confirmation.
Subtotal Before Markups
General Conditions |  | Rate: per ASSUMPTIONS!C19
Overhead & Profit (OH&P) |  | Rate: per ASSUMPTIONS!C20
Total Contingencies |  | Design + existing conditions + equipment/owner selection contingencies.
Bid / Permit / Bonds |  | Rate: per ASSUMPTIONS!C24
TOTAL PROJECT ROM
Project Cost per SF |  | Reference only. Compare to SF BENCHMARK sheet for sanity check.
CONTINGENCY BREAKDOWN (for reference)
Design Contingency
Existing Conditions Contingency
Equipment/Owner Selection Contingency
SOFT COSTS & TOTAL PROJECT INVESTMENT (see SOFT COSTS and TOTAL PROJECT BUDGET sheets)
Architecture Fee (from SOFT COSTS) |  | Base fee + renovation premium per M4Di fee schedule.
Total Engineering Fees |  | Structural, MEP, FP, Civil, Geotech.
Other Consultant & Owner Costs |  | Technology, legal, permits, insurance, testing, environmental.
TOTAL SOFT COSTS |  | See SOFT COSTS sheet for detail and overrides.
Owner Contingency |  | Post-GMP owner contingency and program reserves.
TOTAL PROJECT INVESTMENT |  | Full project cost: hard + soft + owner costs.

## BUDGET TRACKER
M4Di ¦ ALDi Budget Tracker ¦ 1212 Lobdel Avenue — Multi-Unit Affordable Infill ¦ M2_2026_004
LINE ITEM | COL D - ROM (LOCKED G0) | COL E - 75% DD (Gate 2) | COL F - GMP/SOV (Gate 3) | COL G - ACTUAL (Gate 4) | ROM vs DD Var % | ROM vs GMP Var %
Col D = locked ROM from COVER tab. Col D never changes after Gate 0. Enter E, F, G at respective gates. Variance >5% triggers Variance Log entry.
HARD COSTS
Sitework / Civil (drives, walks)
Foundations (modular-spec slab)
Modular Factory Units (36 units)
Freight + Set (crane, ~200 mi)
Site MEP Tie-Ins + Utilities
Exterior Finish Completion
Interior Finish Completion
Shared Open Space / Parking Court
Landscaping / Fencing / Walks
HARD COST SUBTOTAL
General Conditions (8%)
OH&P / GC Fee (6%)
Design Contingency (6%)
SOFT COSTS & CONTINGENCY
Soft Costs (12% of hard+markups)
Owner Contingency (5%)
TOTAL PROJECT ROM - COLUMN D
UNIT ECONOMICS
Total Units (36 - Scenario I)
Cost Per Unit (ROM)
Target Sales Price (WHA) | 215000
Subsidy Gap Per Unit
Total Subsidy Gap

## VARIANCE LOG
VARIANCE LOG — Cost Changes Requiring Documentation
Any variance >5% between estimate columns must be documented here before the next ALDi gate is cleared.
Line Item / Budget Category | Gate | ROM Amt ($) | New Est. Amt ($) | Var ($) | Var (%) | Status | Root Cause & Resolution | Approved By
Existing Conditions Contingency — higher than ROM | Gate 2 | 347000 | 420000 | 73,000 | 21.0% | Approved | Hazmat survey confirmed asbestos in 3 locations. Abatement scope added. Owner approved $73K increase. | T. Maxwell / M4Di
HVAC — Phase 1A scope expanded per DDDS requirements | Gate 2 | 310000 | 365000 | 55,000 | 17.7% | Watch | DDDS licensing pre-app required supplemental ventilation for clinical areas. Engineering confirmed scope. | Pending owner
[Next Variance Item — enter as identified] | [5 empty] | On Track

## CHANGE ORDER LOG
CHANGE ORDER LOG — ALDi Gate 3–4
All changes to the contracted GMP/SOV (Column F) must be logged here. Actual Cost (Column G) = Column F + approved COs below.
CO # | Description | Date | GC Amount ($) | Owner Cost ($) | Cumulative COs ($) | CO Running % of GMP | Status | Category | Notes / Justification
CO-001 | Hazardous Materials Abatement — Phase 1 (asbestos, 3 locations) | 04/15/2026 | 73000 | 0 | 73000 | 2.1% | Approved | Existing Conditions | Required; covered by existing conditions contingency draw
CO-002 | Additional HVAC ductwork — DDDS ventilation compliance | 05/01/2026 | 55000 | 0 | 128000 | 3.7% | Pending | Regulatory | DDDS licensing requirement; pending owner authorization
[Future CO — enter as issued] | [6 empty] | Pending
TOTAL APPROVED COs

## DRAW SCHEDULE
FUNDING DRAW SCHEDULE — Budget vs. Actual Spend
Track each funding source draw against actual project expenditures. Updated monthly with each pay application.
Funding Source | Total Committed ($) | Draw 1 ($) | Draw 2 ($) | Draw 3 ($) | Draw 4 ($) | Draw 5 ($) | Total Drawn ($) | Remaining ($) | % Drawn
Owner / Developer Equity (Dr. Maxwell) | 2500000
CDFI Construction Loan (NCALL) | 3500000
HUD CDBG Grant | 750000
Delaware DDDS Capital Support | 500000
Philanthropic Grants (Longwood / Welfare Fdn) | 750000
Owner Contingency Reserve (escrowed) | 300000
TOTAL FUNDING

## GATE DASHBOARD
ALDi GATE DASHBOARD — Project Status Summary
One-page project status for owner, AE, and lender reporting. Update at each gate.
Project
Owner
AE
M4Di Lead
Building SF
ALDi Start
M4Di ROM (Locked Baseline)
75% DD Estimate
100% CD / GMP (Contracted)
Actual Cost to Date
ROM vs. Current Estimate Variance
ROM vs. Current Estimate Variance %
ALDi GATE STATUS
Gate | Name | Target Date | Actual Date | Status | Budget Check | Key Conditions / Notes
Gate 0 | Controls Setup + Budget Baseline Lock |  |  | In Progress | ROM Locked | Project charter issued. Budget baseline = Column D. Procurement calendar set.
Gate 1 | Schematic Design Review |  |  | Pending | Target ±15% | SD documents reviewed. Constructability input provided. DDDS pre-app status confirmed.
Gate 2 | Design Development + 75% DD Estimate |  |  | Pending | Column E entered | DD estimate entered in Column E. Variance log updated. Owner contingency reviewed.
Gate 3 | GMP Execution + SOV Entry |  |  | Pending | Column F = GMP | Contractor SOV entered in Column F. GMP executed. Financing closed.
Gate 4 | Construction Controls + Closeout |  |  | Pending | Column G current | Monthly actual cost updates. CO log maintained. HISTORICAL DB row completed.

## SF BENCHMARK
COST PER SF — BENCHMARK DASHBOARD
Compares current ROM estimate to M4Di historical database and facility type benchmarks.
Metric | Value |  | Historical Comparison | Value
Project Area (SF) |  |  | Project $/SF vs. Hist. Avg
ROM Construction Cost |  |  | Project $/SF vs. Hist. Median
Calculated Project Cost/SF |  |  | Sanity Check
Historical Average $/SF
Historical Median $/SF
Historical Min $/SF
Historical Max $/SF
Historical Data Count
FACILITY TYPE BENCHMARK RANGES ($/SF)
Facility Type | Low $/SF | High $/SF |  | Check vs. Project
Community Facility Renovation | 120 | 250
Church / Faith-Based Renovation | 110 | 230
Athletic Facility Upgrade | 150 | 320
Athletic Flooring Replacement | 80 | 165
Adaptive Reuse — Community Use | 140 | 290
New Construction — Community Fac. | 220 | 420
Mixed-Use (residential + community) | 260 | 480
HOW TO READ THIS DASHBOARD
If project $/SF is BELOW all ranges: | Scope may be missing items, quantities may be understated, or allowances are not yet included.
If project $/SF is ABOVE all ranges: | Owner selections, specialty equipment, corrosion remediation, or code upgrades may be driving cost.
If project aligns with historical average: | ROM is behaving like a plausible early estimate. Continue to P3 for detailed scope confirmation.
Historical database: | Replace example rows in HISTORICAL DB with M4Di's own completed projects over time. This is the proprietary asset.

## HISTORICAL DB
M4Di HISTORICAL PROJECT COST DATABASE — PROPRIETARY ASSET
CRITICAL: Enter every completed M4Di engagement in this database. This is M4Di's proprietary competitive advantage. Do not distribute externally. Source for SF BENCHMARK dashboard and annual cost reports.
Project Name / Code | Project Type | Location / Region | Year Completed | Building Area (SF) | Final Const. Cost | Cost / SF | Scope Description | Data Source / Notes
YMCA Gymnasium Renovation | Athletic Facility Upgrade | Pennsylvania | 2023 | 18000 | 3200000 |  | Gym upgrades, flooring, bleachers, scoring equipment, wall padding. | Example benchmark — replace with M4Di project data
High School Gymnasium Upgrade | Athletic Facility Upgrade | Delaware | 2022 | 12000 | 2100000 |  | Bleacher replacement, floor refinish, scoreboard, accessible path of travel. | Example benchmark — replace with M4Di project data
Community Rec Center Interior | Community Facility Renovation | Maryland | 2021 | 8000 | 950000 |  | Interior renovation, athletic flooring, community room upgrades. | Example benchmark — replace with M4Di project data
Church Fellowship Hall Adaptive Reuse | Adaptive Reuse — Community Use | Delaware | 2023 | 6500 | 1450000 |  | Fellowship hall converted to community clinic and gathering space. ADA upgrades. | Example benchmark — replace with M4Di project data
Faith-Based Youth Center Renovation | Community Facility Renovation | New Jersey | 2024 | 9200 | 2280000 |  | Full interior renovation, new MEP, gymnasium floor, community kitchen. | Example benchmark — replace with M4Di project data
→ ADD NEW COMPLETED PROJECTS ABOVE THIS LINE. Copy Cost/SF formula from column H. Fill all fields at project closeout.
DATABASE STATISTICS (auto-calculated — used by SF BENCHMARK)
Total Projects in Database
Average Cost / SF
Median Cost / SF
Minimum Cost / SF
Maximum Cost / SF

## SOFT COSTS
SOFT COSTS — Professional Fees & Pre-Construction Budget
Soft costs are calculated as a percentage of the Total Hard Cost ROM (from BID SUMMARY). Architecture fee uses the M4Di Base Fee Schedule (AIA-aligned). Engineering and specialty fees use benchmark percentages adjustable per project. All rates are user-overridable.
A — PROJECT BASIS (from ASSUMPTIONS & BID SUMMARY)
Total Hard Cost ROM |  | Pulled from BID SUMMARY. This is the construction cost base for all fee calculations.
Project Type (for fee schedule) |  | Auto-pulled from ASSUMPTIONS. Drives fee type classification below.
Estimate Phase |  | ROM / Conceptual ¦ Schematic ¦ Design Development ¦ GMP
Gross Area (SF) |  | From ASSUMPTIONS. Used for cost/SF benchmarking.
B — ARCHITECTURE FEE (M4Di Base Fee Schedule)
Fee lookup uses the M4Di Base Fee Schedule. Select the Project Type Code (A–E) based on complexity. For renovation/adaptive reuse, apply the renovation premium. New Construction = base rate only. Renovation = base + premium.
FEE SCHEDULE REFERENCE TABLE — Base % of Construction Cost
Construction Budget Range |  | Type A | Type B | Type C | Type D | Type E
Up to – $49,999 |  | 8.9% | 9.9% | 10.9% | 11.7% | 12%
$50,000 – $99,999 |  | 8.4% | 9.4% | 10.7% | 11.1% | 11.9%
$100,000 – $149,999 |  | 8.1% | 9.1% | 10.4% | 10.9% | 11.5%
$150,000 – $199,999 |  | 7.9% | 8.9% | 10.1% | 10.5% | 11.2%
$200,000 – $299,999 |  | 7.4% | 8.4% | 9.9% | 10.3% | 11%
$300,000 – $499,999 |  | 7.2% | 8.2% | 9.4% | 10% | 10.7%
$500,000 – $749,999 |  | 6.9% | 7.9% | 9.1% | 9.7% | 10.4%
$750,000 – $999,999 |  | 6.7% | 7.7% | 8.9% | 9.4% | 10.1%
$1,000,000 – $1,499,999 |  | 6.4% | 7.4% | 8.4% | 9.1% | 9.8%
$1,500,000 – $1,999,999 |  | 6.2% | 7.2% | 8.2% | 8.8% | 9.5%
$2,000,000 – $2,999,999 |  | 5.9% | 6.9% | 7.9% | 8.5% | 9.2%
$3,000,000 – $3,999,999 |  | 5.7% | 6.7% | 7.7% | 8.3% | 9%
$4,000,000 – $4,999,999 |  | 5.4% | 6.4% | 7.4% | 8.1% | 8.8%
$5,000,000 – $7,999,999 |  | 5.2% | 6.2% | 7.2% | 7.9% | 8.6%
$8,000,000 – $11,999,999 |  | 4.9% | 5.9% | 7.1% | 7.7% | 8.4%
$12,000,000 – $14,999,999 |  | 4.7% | 5.7% | 6.9% | 7.1% | 7.6%
$15,000,000 – $19,999,999 |  | 4.4% | 5.4% | 6.7% | 6.9% | 7.4%
$20,000,000 – $24,999,999 |  | 4.2% | 5.2% | 6.4% | 6.7% | 7.2%
Renovation premium (add to above) |  | 0.5% | 0.65% | 0.75% | 0.85% | 1%
PROJECT TYPE CLASSIFICATION — Select the code that matches your facility
Type A | Warehouse, Public Garage, Residential (standard)
Type B | Office, Parking Facility, Retail, Visitor Center, Maintenance Garage, Tenant Fit-out
Type C | School, Training Facility, Day Care, Fitness Center, Mixed-Use, Adult Care, Laundry
Type D | Library, Restaurant, Theater (no stage), Outpatient Clinic, Detention, Courthouse, Data Center
Type E | Hospital, Research, Museum, Stadium, Prison, Emergency Ops, Theater/Auditorium with stage
M4Di Default — Community Facility Renovation | Use Type C (Fitness Center / Mixed-Use) for church/community renovation. Use Type D for clinic or complex adaptive reuse.
C — FEE INPUTS & CALCULATIONS (enter yellow cells; formulas auto-populate)
Discipline / Fee Item | % of Hard Cost (enter or auto) | Calculated Fee ($) | User Override ($ if fixed) | Fee Used (calc or override) | Included in Budget? | Notes / Assumptions
PROJECT TYPE CODE & RENOVATION SELECTION (user inputs)
AIA Project Type Code (A / B / C / D / E) | C | Type A=warehouse/parking, B=office/retail, C=school/fitness/mixed-use (M4Di default), D=clinic/library/theater, E=hospital/research. See guide above.
Renovation / Adaptive Reuse? (Yes / No) | Yes | Yes: adds renovation premium to base Arch fee per fee schedule. WHACC = Yes (interior improvement + adaptive reuse elements).
ARCHITECTURE & ENGINEERING FEES
Discipline / Fee Item | % of Hard Cost | Calculated Fee ($) | User Override ($) leave blank = use calc | Fee Used | Include? | Notes / Source
Architecture — Base Fee (fee schedule) |  |  |  |  | Yes | Auto-calculated from M4Di Base Fee Schedule. Based on construction cost tier and Type Code.
+ Renovation Premium (if applicable) |  |  |  |  | Yes | Add-on for renovation/adaptive reuse per fee schedule. Set to 0 if new construction.
Architecture — TOTAL FEE
ENGINEERING DISCIPLINES
Structural Engineering | 1.5% |  |  |  | Yes | Typical: 1.0%–2.0% of construction cost. Higher for complex structural systems, seismic, or adaptive reuse.
Mechanical Engineering (HVAC) | 1.8% |  |  |  | Yes | Typical: 1.2%–2.5%. Higher for healthcare/lab. Use lower end for straightforward community facilities.
Electrical Engineering | 1.5% |  |  |  | Yes | Typical: 1.0%–2.0%. Adjust for high-voltage, generator, or specialty lighting systems.
Plumbing Engineering | 1% |  |  |  | Yes | Typical: 0.8%–1.5%. Minimal for interior renovation with no new fixtures. Higher for kitchen/clinic.
Fire Protection Engineering | 0.8% |  |  |  | Yes | Typical: 0.5%–1.0%. Includes sprinkler design and fire alarm engineering if in scope.
Civil Engineering | 1.2% |  |  |  | Yes | Typical: 0.8%–2.0%. Covers grading, stormwater, utilities, ADA site access. Minimal for interior-only.
Geotechnical / Soils Report | 0.5% |  |  |  | Yes | Typical: 0.3%–0.8% or fixed fee $5K–$25K. Required for new foundations or unknown soil conditions.
Landscape Architecture | 0.5% |  |  |  | Yes | Typical: 0.3%–0.8%. Site improvements, accessible path, outdoor amenity. May be $0 for interior scope.
Accessibility / ADA Consultant | 0.5% |  |  |  | Yes | Typical: 0.3%–0.5% or fixed fee. Recommended for public-access facilities; CDFIs and HUD often require.
SPECIALTY CONSULTANTS & OWNER COSTS
Interior Design / Furniture | 0.5% |  |  |  | Yes | If separate from Arch. Includes FF&E design and procurement management.
Technology / AV / IT Consultant | 0.4% |  |  |  | Yes | Low-voltage, AV, security systems design. Required for scoreboard, PA, access control.
Cost Estimating (M4Di OI) | 0% |  |  |  | Yes | M4Di P1/P2/P3 fees are separate contracts. Shown here for total project budget reference.
Owner Project Management | 0% |  |  |  | Yes | M4Di ALDi retainer. Enter actual contracted amount in override column.
Legal / Title / Closing | 0.3% |  |  |  | Yes | Covers property matters, contract review. Variable; use $5K–$15K allowance for small projects.
Permitting / Plan Review Fees | 1.5% |  |  |  | Yes | Variable by jurisdiction. Delaware municipalities: typically 1.0%–2.0% of construction cost.
Builder's Risk Insurance | 0.8% |  |  |  | Yes | Typically 0.5%–1.5% of total project cost. Confirm with owner's insurance agent.
Testing / Special Inspections | 0.5% |  |  |  | Yes | IBC-required inspections (concrete, steel, masonry) and materials testing. AHJ-dependent.
Survey / As-Builts / Scanning | 0% |  |  |  | Yes | Fixed fee item — enter actual quote in override. Typical range: $3,000–$15,000.
Environmental Assessment (Phase I) | 0% |  |  |  | Yes | Fixed fee — enter in override. Required for most CDFI/HUD-funded projects. ~$2,500–$5,000.
Relocation / Move-Out Costs | 0% |  |  |  | Yes | Owner cost. Enter estimate in override if applicable. Not part of construction budget.
Financing / Loan Origination | 1% |  |  |  | Yes | Typical: 0.5%–1.5% of loan amount. Applies to construction loans and CDFI financing.
Fundraising / Development Costs | 0% |  |  |  | Yes | Owner/nonprofit cost. Enter fixed estimate in override if applicable.
SOFT COST SUBTOTALS & TOTAL PROJECT BUDGET
Architecture Subtotal
Engineering Subtotal (all disciplines)
Other Consultants & Owner Costs Subtotal
TOTAL SOFT COSTS
SOFT COST $/SF BENCHMARKS (informational)
Typical total soft costs range from 18%–35% of hard costs for community/institutional projects. Simpler interior renovations: 18%–22%. Complex adaptive reuse or new construction with full engineering: 25%–35%. Healthcare/research: 30%–40%. Current project soft cost %: see TOTAL SOFT COSTS row above.
▶ Total Soft Costs feeds TOTAL PROJECT BUDGET sheet.

## CLARIFICATIONS
CLARIFICATIONS / EXCLUSIONS / RISK LOG
Include this sheet in all client deliverables. It defines the boundaries of the estimate and protects M4Di from scope disputes. Update at every estimate revision.
Category | Item | Included / Excluded / Allowance | Risk Level | Comment / Mitigation
General | All quantities are conceptual and require field verification before GMP | Included | High | Use as ROM only. Not a GMP or guaranteed maximum price.
General | Estimate based on scope narrative and program only — no drawings | Included | High | Unit quantities are estimator's judgment. Field verify before DD.
Equipment | Athletic equipment model numbers and manufacturers | Allowance | High | Owner selections pending. Allowances will be updated as selections are confirmed.
Equipment | Boxing equipment package | Allowance | High | Basis of design still open. Owner to confirm model and accessory scope.
MEP | Power and data modifications for scoreboards and specialty equipment | Allowance | Medium | Allowance included. Requires MEP engineer coordination and load calculations.
MEP | HVAC modifications or upgrades | Excluded | Medium | Not in scope unless noted. Carry separate MEP budget if HVAC work is anticipated.
MEP | Plumbing — new fixtures or drainage | Excluded | Medium | Minor modifications covered by allowance. Major new plumbing excluded.
Existing Conditions | Concealed corrosion or substrate damage beyond scope assumptions | Excluded | High | Carry contingency or unit rates for concealed conditions. Field verification recommended.
Existing Conditions | Hazardous material abatement (asbestos, lead paint) | Excluded | High | Requires testing and licensed abatement contractor. Separate budget required.
Existing Conditions | Structural deficiencies identified during construction | Excluded | High | Not in scope. Structural engineer review recommended before estimate finalization.
Schedule | Cost escalation beyond current estimate date | Excluded | Medium | Adjust ENR escalation factor in ASSUMPTIONS for revised bid dates.
Schedule | Owner-caused delays extending construction schedule | Excluded | Medium | Extended general conditions are not included. Owner decision delays add cost.
Permits | Building permits, zoning approvals, and municipal fees | Allowance | Low | Bid/permit/bond allowance included at {rate}%. Actual fees may vary.
Soft Costs | Architectural and engineering fees | Excluded | Information Only | AE fees are a separate budget line. Typical range: 8%–12% of construction cost.
Soft Costs | Owner project management / owner's rep fees | Excluded | Information Only | M4Di ALDi retainer fees are a separate agreement, not included in construction budget.
Soft Costs | Furniture, fixtures, and equipment (FF&E) not specified | Excluded | Medium | Only items specifically called out in unit price library are included.
Site | Site utilities, site work, or exterior improvements | Excluded | Medium | Interior scope only unless site work is specifically noted in TAKEOFF.
Accessibility | ADA path of travel upgrades beyond specified scope | Excluded | Medium | ADA items within designated scope are included. Full-building accessibility audit not in scope.
→ ADD PROJECT-SPECIFIC CLARIFICATIONS ABOVE. Always include this sheet in client deliverable packages.

## TOTAL PROJECT BUDGET
TOTAL PROJECT BUDGET — Hard Costs + Soft Costs + Owner Costs
This sheet aggregates the full project investment: construction hard costs (from BID SUMMARY), professional fees and soft costs (from SOFT COSTS), and owner contingency. Use this for board presentations, CDFI loan packages, and grant applications.
Budget Item | Amount ($) | % of Hard Cost | % of Total | Notes
SECTION 1 — HARD COSTS (Construction)
Base Building Subtotal (labor + materials) |  |  |  | Quantity-based takeoff from TAKEOFF sheet, adjusted for region and escalation.
Equipment Allowances (owner selections) |  |  |  | Athletic and specialty equipment. Pending owner selections. See EQUIPMENT ALLOWANCES.
General Conditions |  |  |  | On-site supervision, temp facilities, insurance. Rate per ASSUMPTIONS.
Overhead & Profit (OH&P) |  |  |  | Contractor OH&P. Rate per ASSUMPTIONS.
Total Contingencies |  |  |  | Design + existing conditions + owner selection contingency. Will reduce at each gate.
Bid / Permit / Bonds |  |  |  | Permitting fees, bid bonds, performance bonds.
TOTAL HARD COST (Construction ROM) |  | 100%
SECTION 2 — SOFT COSTS (Professional Fees & Owner Costs)
Architecture — Total Fee (base + renovation premium) |  |  |  | Base fee per M4Di fee schedule + renovation premium. See SOFT COSTS sheet.
Structural Engineering |  |  |  | See SOFT COSTS sheet for rate and override.
Mechanical Engineering (HVAC) |  |  |  | See SOFT COSTS sheet for rate and override.
Electrical Engineering |  |  |  | See SOFT COSTS sheet for rate and override.
Plumbing Engineering |  |  |  | See SOFT COSTS sheet for rate and override.
Fire Protection Engineering |  |  |  | See SOFT COSTS sheet for rate and override.
Civil Engineering |  |  |  | See SOFT COSTS sheet. Minimal for interior-only scope.
Geotechnical / Soils Report |  |  |  | Fixed fee item for new foundations or unknown conditions.
Other Consultants & Owner Costs |  |  |  | Technology, legal, permits, insurance, testing, environmental. See SOFT COSTS.
TOTAL SOFT COSTS
SECTION 3 — OWNER CONTINGENCY & PREDEVELOPMENT
Owner Project Contingency (post-GMP) |  | 5% |  | Owner-held contingency for scope changes, unforeseen conditions, and owner decisions after GMP. Recommend 5%–10%.
Predevelopment Costs (M4Di P1–P3 fees) |  | 0% |  | M4Di feasibility ops fees already incurred or contracted. Enter fixed dollar amount in override on SOFT COSTS.
FF&E — Furniture, Fixtures & Equipment |  | 0% |  | Non-construction FF&E not in the construction contract. Enter lump sum estimate.
Technology / AV / Security Systems |  | 0% |  | Owner-procured tech systems outside of construction contract. Enter estimate.
Moving / Relocation / Swing Space |  | 0% |  | If applicable. Enter fixed estimate.
Program Reserve (funding gap buffer) |  | 0% |  | Discretionary reserve for funding shortfalls. Typically 3%–8% of total project cost for nonprofit owners.
TOTAL OWNER CONTINGENCY & OTHER
TOTAL PROJECT INVESTMENT |  | 100%
SUMMARY METRICS
Total Project Investment
Hard Cost ROM
Soft Costs (professional fees + other)
Soft Costs as % of Hard Costs |  | Benchmark: 18%–25% typical community facility; 25%–35% complex renovation/new construction.
Total Project Cost / SF |  | Total investment including all soft costs. Compare to $/SF benchmarks in SF BENCHMARK sheet.
Hard Cost / SF |  | Construction cost only. Use for benchmarking against comparable projects.

## ALDDB EXPORT
ALDDB EXPORT - Closeout Data Row ¦ M4Di Historical Cost Database
Complete at Gate 4 closeout. Copy Col C as VALUES into ALDDB Master next empty row. This is the moat. Never skip.
FIELD | VALUE / FORMULA
Project Code
Project Name
Address
Client
Lead Firm
ALDi Gate at Export | G4 Closeout (enter manually)
Governing Code
Construction Type
Total Units
Unit SF
Total GFA (SF)
Site SF
Site Acres
Year Completed | Enter at closeout
Column D ROM Total
Column E 75% DD | Enter from BUDGET TRACKER at closeout
Column F GMP/SOV | Enter from BUDGET TRACKER at closeout
Column G Actual Cost | Enter from BUDGET TRACKER at closeout
Column D vs G Variance ($)
Column D vs G Variance (%)
Hard Cost / SF
Total Cost / SF
Subsidy Gap / Unit | Enter from BUDGET TRACKER at closeout
ENR Index
Bid Date
Key Variance Notes | Enter from VARIANCE LOG at closeout
Data Entry Date | Enter at closeout
PROTOCOL: At Gate 4 closeout, complete all blue "Enter" cells. Copy Col C as Paste Special > Values into next ALDDB Master row. One row per closed project. This feeds the moat.

## TAB QA
TAB QA — CRITICAL FORMULA CHECKS & WORKBOOK VALIDATION
Use this sheet after any revision to confirm critical formulas are working correctly. Open in Excel, press Ctrl+Alt+F9 to force full recalculation, then review each check.
Check ID | Sheet | Cell | Description | Expected Behavior | Live Value | Manual QA Result | Reviewer Notes
QA-01 | ASSUMPTIONS | C12 | Weighted trade labor factor | Returns 1.000x for Delaware and ~1.145x for Philadelphia Metro |  | Not Checked
QA-02 | REGIONAL FACTORS | I3 | Delaware weighted labor basket | Returns a numeric weighted basket (should be ~26.17) |  | Not Checked
QA-03 | REGIONAL FACTORS | I4 | Philadelphia region factor | Returns factor >1.000x (should be ~1.145) |  | Not Checked
QA-04 | UNIT PRICE LIBRARY | K3 | Adjusted unit price row 3 | Returns numeric adjusted unit price (Base Price × Region Factor × Escalation) |  | Not Checked
QA-05 | TAKEOFF | L3 | Adj. unit cost VLOOKUP row 3 | Returns matching adjusted unit cost from UNIT PRICE LIBRARY via Cost Code VLOOKUP |  | Not Checked
QA-06 | TAKEOFF | M3 | Takeoff line total row 3 | Returns quantity × adjusted unit cost (or 0 if Included = No) |  | Not Checked
QA-07 | FLOOR SUMMARY | C3 | LL base building total | Sums all LL rows from TAKEOFF where Included = Yes or Allowance |  | Not Checked
QA-08 | FLOOR SUMMARY | I8 | Total Project ROM | Should equal sum of all floor totals in column J |  | Not Checked
QA-09 | BID SUMMARY | C10 | TOTAL PROJECT ROM | Should match FLOOR SUMMARY total project ROM within rounding |  | Not Checked
QA-10 | BID SUMMARY | C14 | Project cost per SF | Total ROM / Project SF from ASSUMPTIONS. Returns numeric $/SF. |  | Not Checked
QA-11 | OWNER SELECTIONS | M12 | Owner selection allowance total | Returns sum of all Allowance Each × Qty. Should match EQUIPMENT ALLOWANCES total. |  | Not Checked
QA-12 | SF BENCHMARK | C6 | Calculated project cost / SF | Returns numeric $/SF from BID SUMMARY |  | Not Checked
QA-13 | SF BENCHMARK | F6 | Sanity check text | Returns readable text: Within historical range / Above / Below |  | Not Checked
QA-14 | HISTORICAL DB | H4 | Historical cost per SF row 4 | Returns numeric cost/SF for the first historical project |  | Not Checked
QA-15 | ALLOWANCE LOG | F12 | Total open allowances | Sum of all allowance amounts. Should be > $0 while items are pending. |  | Not Checked
QUICK QA STEPS
1. Open workbook in desktop Excel (not browser).
2. Press Ctrl+Alt+F9 to force full recalculation of all formulas.
3. Review Live Value column — confirm no REF errors, VALUE errors, NAME errors, or blank totals.
4. Check BID SUMMARY Total ROM vs. FLOOR SUMMARY Total ROM — should match.
5. Confirm ALLOWANCE LOG pending count matches OWNER SELECTIONS pending count.
6. Mark each check as Pass / Fail / Review.
7. Save a dated revision copy before issuing to any external party.