PROFESSIONAL FEE PROPOSAL 1212 Lobdel Avenue — Multi-Unit Affordable Infill Housing Wilmington, DE · ALDi™ Gate 0 — Predevelopment Intelligence · Track A Services

| Submitted To | Wilmington Housing Authority (WHA) · Wilmington, DE |
| --- | --- |
| Submitted By | Merge 4 Design LLC (M4D) · 500 Delaware Ave., Suite 1 #1551, Wilmington, DE 19899 · 302 367 5726 · merge4design.com |
| Date Submitted | April 2026 |
| Project Reference | M2_2026_005 · 1212 Lobdel Avenue |
| Proposal Valid | 90 days from submission date |

# 01.  Project Identification

| Project Name | 1212 Lobdel Avenue — Multi-Unit Affordable Infill Housing |
| --- | --- |
| Parcel ID | 2605130241 |
| Address | 1212 Lobdel Avenue, Wilmington, DE (City of Wilmington limits) |
| Client / Owner | Wilmington Housing Authority (WHA) |
| Lead Firm | Merge 4 Design LLC (M4D) |
| Predevelopment Intelligence | M4Di — Merge 4 Development Institute |
| AOR (if required) | David Ainsworth AIA / Aubyn Architecture LLC (subconsultant to M4D) |
| ALDi™ Gate | G0 — Rough Order of Magnitude / Predevelopment Intelligence |
| Zoning Jurisdiction | City of Wilmington Zoning Ordinance, Chapter 48 (R-3 District) |
| Document | M2_2026_005 · April 2026 |

# 02.  Scope of Services — Track A: ALDi™ Gate 0 Predevelopment Intelligence

Track A delivers the ALDi™ Gate 0 predevelopment intelligence package for 1212 Lobdel Avenue. It is authorized and delivered as a standalone engagement, independent of any subsequent design authorization. All work in this track is complete upon delivery of the items listed below. Track A is priced as a fixed fee.

## 2.1  Deliverables and Schedule

| # | Deliverable | Format | Estimated Delivery |
| --- | --- | --- | --- |
| A1 | Site Assessment & Zoning Research — parcel confirmation, R-3 district analysis, City of Wilmington Chapter 48 applicable standards, block face setback documentation | Memo / Data Table | Week 1 |
| A2 | Three Yield Scenarios — unit count, site layout, regulatory envelope confirmation for Scenarios I (36 units, 18 ft wide), II (40 units, 16 ft wide), and III (24 units, 20 ft wide) | Report + Site Plan Diagrams | Week 1 |
| A3 | Construction Type Matrix — three construction methods (A: CLT/SIP Hybrid, B: Off-Site Modular, C: Stick-Build) analyzed across all yield scenarios with ROM cost ranges, per-unit cost, and gap analysis | Matrix Report | Week 1–2 |
| A4 | Sustainability Add-Alternate Analysis — geothermal HVAC (shared bore field), community solar PV, and rainwater harvesting sized for 36–40 unit scale; PACE financing applicability noted | Analysis Memo | Week 2 |
| A5 | CBai / Blender Site Yield Study — 3D massing studies for all yield scenarios; solar access study; drive aisle and amenity zone layout; photorealistic perspectives (preliminary) | 3D Visualizations + Site Plan | Week 2–3 |
| A6 | WHA Presentation Package — all ROM exhibits, scenario comparison matrix, sustainability options, and subsidy gap analysis compiled into a WHA-ready deck (PPTX + PDF) | Presentation Deck | Week 3–4 |
| A7 | Subsidy Gap & Grant Program Memo — Delaware Catalyst Fund, HOME, and DSHA program fit analysis; subsidy stack structure for Scenario I/B (recommended) | Memo | Week 3 |
| A8 | ALDi™ G0 Lock + M4Di OI Tool Setup — ROM values reconciled, Gate 0 locked in M4Di system, ALDDB entry initiated | Internal / Deliverable Summary | Week 4 |

Note:  Track A deliverables reflect the full ALDi™ G0 predevelopment intelligence scope for this site. The timeline above reflects a streamlined delivery sequence consistent with WHA’s project schedule needs. All items will be delivered within four (4) weeks of written authorization unless site data gaps (Phase I ESA, geotechnical results) extend individual items, in which case M4D will notify WHA in advance.

# 03.  Recommended Owner-Directed Authorizations

In the course of Track A analysis, M4D has identified two additional due diligence items that are necessary inputs for Gate 0 completion but are outside the professional service fee. M4D recommends that WHA authorize these directly with appropriate vendors, and that the resulting reports be provided to M4D for incorporation into the ROM and gap analysis.

## 3.1  Geotechnical Investigation (Soil Borings)

Status:  Not yet ordered. M4D strongly recommends authorization concurrent with this proposal.

Soil bearing capacity is a critical input for foundation design across all construction types — and is especially essential for the recommended off-site modular option (Type B), which requires precise bearing confirmation at module set points. Without geotechnical data, the modular foundation ROM carries elevated uncertainty. M4D recommends that WHA authorize a licensed geotechnical engineer to perform a minimum of four (4) test borings distributed across the 1.39-acre site. Results should be provided to M4D upon receipt for incorporation into the final Gate 0 ROM lock.

## 3.2  Geothermal Feasibility and Alt-Energy Exploration

Status:  Included in Track A at a conceptual level (Item A4). M4D recommends authorizing a qualified MEP engineer or geothermal specialist for a targeted feasibility review.

At 36–40 units, a shared geothermal bore field becomes economically viable on a per-unit basis and is a meaningful differentiator for WHA’s energy cost and long-term operating expense profile. The ROM analysis includes a budgetary allowance for this system; however, a formal feasibility report (geo exchange capacity, bore count, loop field sizing) is required to confirm viability before committing design resources. A community solar PV array and shared rainwater harvesting system are included as alternates in the same analysis scope. M4D is prepared to coordinate the engagement of a qualified consultant for this scope on WHA’s behalf, or WHA may engage directly.

M4D will incorporate the results of both items above into the final ALDi™ G0 ROM lock and WHA presentation package at no additional fee, provided reports are received prior to Week 3 of the Track A schedule.

# 04.  Fee Summary — Track A (Fixed Fee)

| Item | Service Description | Hours (Est.) | Rate | Fee |
| --- | --- | --- | --- | --- |
| A1 | Site Assessment & Zoning Research | 18 | $185/hr | $3,330 |
| A2 | Three Yield Scenarios + Site Layout | 24 | $185/hr | $4,440 |
| A3 | Construction Type Matrix (3 types × 3 scenarios) | 6 | $185/hr | $1,110 |
| A4 | Sustainability Add-Alternate Analysis | 6 | $185/hr | $1,110 |
| A5 | CBai / Blender Site Yield Study + Visualizations | 12 | $165/hr | $1,980 |
| A6 | WHA Presentation Package (deck + exhibits) | 10 | $165/hr | $1,650 |
| A7 | Subsidy Gap & Grant Program Memo | 8 | $165/hr | $1,320 |
| A8 | ALDi™ G0 Lock + M4Di OI Tool Setup | 5 | $185/hr | $925 |
|  | TRACK A TOTAL — FIXED FEE | 89 hrs | — | $15,865 |

AOR Subconsultant Fee — Aubyn Architecture LLC Aubyn Architecture LLC serves as Architect of Record subconsultant to M4D on all Delaware projects requiring a stamped permit set. The Aubyn AOR subconsultant fee is calculated at 10% of the applicable M4D architectural fee for any Track B engagement on this project. This fee is not included in the Track A fixed fee above and will be reflected in the Track B proposal once WHA authorizes design services. The governing instrument is the M4D / Aubyn Architecture Master C401 Subconsultant Agreement (AIA C401-2017 basis). Aubyn Architecture LLC — 215 N. Market St., Suite 317, Wilmington, DE 19801.

Not Included in Track A: - Phase I Environmental Site Assessment — WHA-directed engagement - Geotechnical investigation / soil borings — WHA-directed engagement (see Section 03) - Geothermal or alt-energy formal feasibility study — WHA-directed or M4D-coordinated (see Section 03) - Civil, structural, or MEP engineering services — subconsultants to be engaged per Track B authorization - Reimbursable expenses — printing, travel, plotting billed at cost; estimated at $500 for Track A scope

# 05.  Track B — Architecture & Engineering Services: Notice of Intent

EXHIBIT A — TRACK B ENGAGEMENT NOTICE 1212 Lobdel Avenue — Multi-Unit Affordable Infill Housing · Merge 4 Design LLC Purpose of this Exhibit Merge 4 Design LLC (M4D) intends to submit a complete fee proposal for Track B Architecture & Engineering services — covering Schematic Design through Construction Administration — upon completion of the Track A predevelopment intelligence package and WHA’s selection of a preferred yield scenario and construction type. Track B fee development requires the following inputs from Track A and WHA: - Confirmed yield scenario (Scenario I, II, or III — unit count, unit width) - WHA-selected construction type (Type A CLT/SIP, Type B Off-Site Modular, or Type C Stick-Build) — each type carries materially different documentation and coordination effort - Geotechnical and Phase I ESA results, which affect foundation and structural subconsultant scope - WHA financing structure and subsidy sources, which may impose additional documentation requirements (LIHTC, HOME, HUD Section 3) Anticipated Track B Scope (for planning purposes only — not a binding fee): Phase; Scope; Basis. B1 — Schematic Design (SD); All confirmed scenarios; site plan; unit plan types; CBai renderings; Lump sum per scenario. B2 — Design Development (DD); Selected scenario only; system coordination; modular coordination (if Type B); Lump sum. B3 — Construction Documents (CD); Permit-ready stamped set; standardized row house documentation; Lump sum. B4 — Permitting & AHJ Coordination; City of Wilmington permit submission; plan review response; Hourly NTE. B5 — Construction Administration (CA); Site observation, RFI/submittal review, punch list; Hourly NTE. Subconsultants; Civil, Structural, MEP engineering — firms to be determined by WHA and M4D upon construction type selection; Pass-through or separate contract. Aubyn Architecture AOR fee; 10% of M4D architectural fee (Tracks B1–B3 phases requiring stamped documents); Per Master C401 Agreement. M4D will deliver the Track B fee proposal in writing within fourteen (14) days of WHA’s written notice of scenario and construction type selection. Track B requires a separate written authorization and PSA amendment. No Track B services will commence without written authorization.

# 06.  Authorization — Track A

To authorize Track A services, please execute this proposal and return a signed copy to M4D. A Professional Services Agreement (M4D PSA, Doc No. M2_2026_005-PSA) will be issued upon receipt. Services will commence within three (3) business days of executed PSA and receipt of the Track A retainer.

| Track A Fixed Fee $15,865.00 Retainer (50% due upon authorization): $7,932.50 | Delivery: 4 weeks from written authorization Governing agreement: M4D PSA (to be issued) Invoice: Net 15 days |
| --- | --- |

| AUTHORIZED BY — MERGE 4 DESIGN LLC _______________________________________ David Ainsworth AIA, Principal Merge 4 Design LLC Date: _______________________ | AUTHORIZED BY — WILMINGTON HOUSING AUTHORITY _______________________________________ Name: _______________________ Title: _______________________ Date: _______________________ |
| --- | --- |

FLAG FOR LEGAL/FINANCIAL REVIEW:  Confirm WHA procurement requirements (DBE/MBE thresholds, HUD Section 3, City of Wilmington local hiring provisions) before contract execution. This proposal does not constitute a contract. The ALDi™ G0 ROM values referenced herein are rough orders of magnitude and do not constitute a bid, guarantee, or warranty of construction cost. Professional legal review is recommended prior to execution.