PROFESSIONAL FEE PROPOSAL 1212 Lobdel Avenue — Multi-Unit Affordable Infill Housing Wilmington, DE · Predevelopment Intelligence & Architecture Services · April 2026

| Submitted To | Wilmington Housing Authority (WHA) · Wilmington, DE |
| --- | --- |
| Submitted By | Merge 4 Design LLC (M4D) · 500 Delaware Ave., Suite 1 #1551, Wilmington, DE 19899 · 302 367 5726 · merge4design.com |
| Date Submitted | April 2026 |
| Project Reference | M2_2026_005 · 1212 Lobdel Avenue |
| Proposal Valid | 90 days from submission date |

# 01.  Project Identification

| Project Name | 1212 Lobdel Avenue — Multi-Unit Affordable Infill Housing |
| --- | --- |
| Parcel ID | 2605130241 |
| Address | 1212 Lobdel Avenue, Wilmington, DE (City of Wilmington limits) |
| Client / Owner | Wilmington Housing Authority (WHA) |
| Project Lead | Merge 4 Design LLC (M4D) |
| Zoning Jurisdiction | City of Wilmington Zoning Ordinance, Chapter 48 — R-3 District |
| M4D Project Number | M2_2026_005 · April 2026 |

# 02.  Project Context & Recommended Construction Scenario

1212 Lobdel Avenue is a 1.39-acre cleared infill site within the City of Wilmington, owned by the Wilmington Housing Authority. The site is zoned R-3 (One-Family Row Houses, Chapter 48) and is targeted for 30+ units of affordable for-sale housing. M4D’s predevelopment analysis has identified three construction scenarios for comparison; the recommended approach is detailed below.

## 2.1  Construction Scenario Comparison

| Construction System | Units | $/Unit | Total Cost | Subsidy Gap/Unit |
| --- | --- | --- | --- | --- |
| Conventional Stick-Frame — baseline | 36 | $409K | $14.7M | ~$194K |
| Off-Site Modular — today's best available | 36 | $255K | $9.2M | ~$41K |
| CLT/SIP + AAC + Modular Wet Wall RECOMMENDED — Campus Scenario (Merge4Ward) | 36+ | ~$265K* | ~$9.5M* | ~$50K* |
| CLT/SIP — without regional supply chain | 36 | $413K | $14.9M | ~$198K |

* Campus Scenario Note The CLT/SIP + AAC + Modular Wet Wall scenario is the M4D/Merge4Ward recommended construction approach. It combines CLT structural panels, autoclaved aerated concrete (AAC) party wall and floor panels, and factory-assembled modular wet wall MEP panels into a complete high-performance townhouse system. Cost parity with conventional modular is achieved when the Merge4Ward regional manufacturing campus eliminates the current $8–15/SF Mid-Atlantic freight premium on CLT panels and the Florida supply chain for AAC panels. The Delaware Catalyst Fund at $35K/unit × 36 units = $1.26M closes approximately 70% of the subsidy gap — making this scenario financeable without extraordinary subsidy layering.

## 2.2  Recommended Program — Scenario I

| Configuration | 4 rows × 9 units per row · 18 ft wide × 35 ft deep per unit |
| --- | --- |
| Total Units | 36 units — exceeds WHA 30-unit target by 20% |
| Unit Size | 1,260 SF (2-story) · Proper 3BR/2BA · Wider than existing Lobdel Ave stock |
| Site Area | 1.39 acres / ±61,705 SF · 175 ft × 352.6 ft · Site fully cleared |
| Construction Type | CLT/SIP + AAC Party Wall + Modular Wet Wall (Merge4Ward Campus Scenario) |
| Gross Floor Area | 45,360 SF (2-story) |
| Target Sale Price | $200,000 – $235,000 per home |
| Amenity Zone | 112.6 ft surplus zone: parking court (30+ spaces), community garden, bio-retention |

# 03.  Scope of Services

M4D proposes services in two tracks. Track A — Predevelopment Intelligence — is authorized and delivered as a standalone fixed-fee engagement. Track B — Architecture & Engineering — is authorized separately upon WHA’s selection of a construction type and yield scenario, and is structured as a lump-sum fee by phase.

## 3.1  Track A — Predevelopment Intelligence (Fixed Fee)

| Item | Deliverable | Format | Schedule |
| --- | --- | --- | --- |
| A1 | Site Assessment — parcel confirmation, governing zoning analysis, applicable code standards | Memo / Data Table | Week 1 |
| A2 | Three Yield Scenarios — unit count, site layout, regulatory envelope confirmation for Scenarios I, II, and III | Report + Site Diagrams | Week 1 |
| A3 | Construction Type Matrix — three systems (CLT/SIP Campus, Modular, Stick-Build) analyzed across all yield scenarios with cost ranges, per-unit cost, and gap analysis | Matrix Report | Week 1–2 |
| A4 | Sustainability Add-Alternate Analysis — geothermal HVAC (shared bore field), community solar PV, and rainwater harvesting; PACE financing applicability noted | Analysis Memo | Week 2 |
| A5 | 3D Site Yield Study & Visualization — massing studies for all yield scenarios; solar access study; drive aisle and amenity zone layout; photorealistic perspectives | 3D Visualizations + Site Plan | Week 2–3 |
| A6 | WHA Presentation Package — scenario comparison, cost matrix, sustainability options, and subsidy gap analysis compiled into a WHA-ready deck (PPTX + PDF) | Presentation Deck | Week 3–4 |
| A7 | Subsidy Gap & Grant Program Memo — Delaware Catalyst Fund, HOME, and DSHA program fit analysis | Memo | Week 3 |
| A8 | Gate 0 ROM Lock — cost estimates reconciled and locked; ALDDB entry initiated | Internal / Summary | Week 4 |

## 3.2  Track B — Architecture & Engineering Services (Lump Sum by Phase)

Track B is authorized separately following WHA’s written selection of yield scenario and construction type. Each phase requires individual written authorization. Fees below are based on the recommended Scenario I / CLT/SIP Campus construction type.

| Phase | Scope | Basis | Fee |
| --- | --- | --- | --- |
| B1 | Schematic Design (SD) — all confirmed yield scenarios; unit plan types; 3D visualizations; site plan | Lump Sum | $11,700 |
| B2 | Design Development (DD) — selected scenario; system coordination; CLT/AAC panel grid; structural coordination | Lump Sum | $17,550 |
| B3 | Construction Documents (CD) — permit-ready stamped set; standardized row house documentation; all 36 units | Lump Sum | $35,100 |
| B4 | Permitting & AHJ Coordination — City of Wilmington permit submission; plan review response | Hourly NTE | $5,250 |
| B5 | Construction Administration (CA) — site observation; RFI/submittal review; punch list | Hourly NTE | $9,450 |
| B6 | Reimbursable Expenses — printing, travel, plots (billed at cost) | Actual | ~$4,000 |

Subconsultants (Civil Engineer, Structural Engineer, MEP Engineer) are not included in the M4D fee. Budget approximately 12% of construction cost: ~$1.1M at the recommended scenario basis. Subconsultants will be engaged per written authorization from WHA and M4D.

# 04.  Fee Summary

## 4.1  Track A — Predevelopment Intelligence (Fixed Fee)

| Item | Service | Hrs (Est.) | Rate | Fee |
| --- | --- | --- | --- | --- |
| A1 | Site Assessment & Zoning Analysis | 18 | $185/hr | $3,330 |
| A2 | Three Yield Scenarios + Site Layout | 24 | $185/hr | $4,440 |
| A3 | Construction Type Matrix (3 systems × 3 scenarios) | 6 | $185/hr | $1,110 |
| A4 | Sustainability Add-Alternate Analysis | 6 | $185/hr | $1,110 |
| A5 | 3D Site Yield Study & Visualization | 12 | $165/hr | $1,980 |
| A6 | WHA Presentation Package | 10 | $165/hr | $1,650 |
| A7 | Subsidy Gap & Grant Program Memo | 8 | $165/hr | $1,320 |
| A8 | Gate 0 ROM Lock | 5 | $185/hr | $925 |
|  | TRACK A TOTAL — FIXED FEE | 89 hrs | — | $15,865 |

## 4.2  Track B — Architecture & Engineering (Lump Sum by Phase)

| Phase | Scope | Basis | Fee |
| --- | --- | --- | --- |
| B1 | Schematic Design | Lump Sum | $11,700 |
| B2 | Design Development | Lump Sum | $17,550 |
| B3 | Construction Documents | Lump Sum | $35,100 |
| B4 | Permitting & AHJ Coordination | Hourly NTE | $5,250 |
| B5 | Construction Administration | Hourly NTE | $9,450 |
| B6 | Reimbursable Expenses | Actual | ~$4,000 |
|  | TRACK B SUBTOTAL | — | $83,050 |

## 4.3  Track A + B Combined & Fee Credit

|  | Amount |
| --- | --- |
| Track A — Predevelopment Intelligence (Fixed Fee) | $15,865 |
| Track B — Architecture & Engineering (Lump Sum by Phase) | $83,050 |
| Track B — Reimbursable Expenses (estimated) | ~$4,000 |
| COMBINED TOTAL — TRACKS A + B | ~$102,915 |
| ★ TRACK A FEE CREDIT — Upon WHA’s written authorization of Track B (full design services), M4D will credit the full Track A fee of $15,865 against the Track B invoice for Phase B1 (Schematic Design). This credit is M4D’s commitment to the long-term WHA relationship and its confidence that this project will proceed to full design authorization. | ($15,865) |
| NET TOTAL AFTER TRACK A CREDIT (upon Track B authorization) | ~$87,050 |

AOR Subconsultant — Aubyn Architecture LLC Aubyn Architecture LLC (David Ainsworth AIA) serves as Architect of Record subconsultant to M4D on all Delaware projects requiring a stamped permit set. The AOR fee is 10% of the applicable M4D architectural fee for Track B phases requiring stamped documents, and is reflected in the Track B lump-sum amounts above. Aubyn Architecture LLC — 215 N. Market St., Suite 317, Wilmington, DE 19801. Governing instrument: M4D / Aubyn Architecture Master C401 Subconsultant Agreement (AIA C401-2017 basis).

# 05.  Recommended Next Steps

| # | Action | Lead | Timeline |
| --- | --- | --- | --- |
| 1 | Authorize Track A — Predevelopment Intelligence ($15,865 fixed). Execute M4D PSA M2_2026_005. | WHA + M4D | Immediate |
| 2 | Request City of Wilmington Land Use pre-application meeting — confirm R-3 use, block face setback, 10-unit row cap, and any overlay districts. | M4D | Week 1 |
| 3 | Order Phase I Environmental Site Assessment — prior school facility; possible asbestos, underground tanks, contaminated soil. | WHA | Week 1 |
| 4 | Authorize geotechnical investigation (minimum 4 test borings across 1.39-acre site). Critical for foundation design under all three construction types. | WHA | Week 1–2 |
| 5 | Confirm WHA homebuyer income targeting (% AMI) and subordinate financing capacity — determines subsidy stack and Catalyst Fund eligibility pathway. | WHA Finance | Week 2 |
| 6 | RFI to Merge4Ward / modular manufacturers: 18 ft wide × 35 ft deep × 2-story, quantity 36 units, Mid-Atlantic delivery. Confirm CLT/AAC panel fabrication schedule. | M4D | Week 2 |
| 7 | Confirm Delaware Catalyst Fund eligibility pathway for Lobdel — $35K/unit × 36 units = $1.26M. Coordinate with DSHA. | M4D + WHA | Week 2–3 |
| 8 | WHA presentation — 3 yield scenarios, 3 construction types, cost comparison, sustainability options, subsidy gap. | M4D + WHA | Week 4–5 |
| 9 | WHA scenario selection and written authorization of Track B (Schematic Design). Track A credit applied at this step. | WHA | Post-presentation |

# 06.  Authorization — Track A

To authorize Track A services, please execute this proposal and return a signed copy to M4D. A Professional Services Agreement will be issued upon receipt. Services will commence within three (3) business days of executed PSA and receipt of the retainer.

| Track A Fixed Fee $15,865.00 Retainer (50% due upon authorization): $7,932.50 | Delivery: 4 weeks from written authorization Governing agreement: M4D PSA M2_2026_005-PSA (to be issued) Invoice: Net 15 days |
| --- | --- |

| AUTHORIZED BY — MERGE 4 DESIGN LLC _______________________________________ Trevor Knight, Director of Business Development Merge 4 Design LLC Date: _______________________ PRINCIPAL-IN-CHARGE (OPTIONAL CO-SIGNER) _______________________________________ David Ainsworth AIA, Principal-in-Charge Date: _______________________ | AUTHORIZED BY — WILMINGTON HOUSING AUTHORITY _______________________________________ Name: _______________________ Title: _______________________ Date: _______________________ |
| --- | --- |

FLAG FOR LEGAL/FINANCIAL REVIEW:  Confirm WHA procurement requirements (DBE/MBE thresholds, HUD Section 3, City of Wilmington local hiring provisions) before contract execution. This proposal does not constitute a contract. Cost estimates are rough orders of magnitude and do not constitute a bid, guarantee, or warranty of construction cost. Professional legal review is recommended prior to execution.