PROFESSIONAL FEE PROPOSAL 1212 Lobdel Avenue — Multi-Unit Affordable Infill Housing Wilmington, DE · Predevelopment & Architecture Services · April 2026

| Submitted To | Wilmington Housing Authority (WHA) · Wilmington, DE |
| --- | --- |
| Submitted By | Merge 4 Design LLC (M4D) · 500 Delaware Ave., Suite 1 #1551, Wilmington, DE 19899 · 302 367 5726 · merge4design.com |
| Date Submitted | April 2026 |
| Project Reference | M2_2026_012 · 1212 Lobdel Avenue |
| Proposal Valid | 90 days from submission date |

# 01.  Project Identification

| Project Name | 1212 Lobdel Avenue — Multi-Unit Affordable Infill Housing |
| --- | --- |
| Parcel ID | 2605130241 |
| Address | 1212 Lobdel Avenue, Wilmington, DE (City of Wilmington limits) |
| Client / Owner | Wilmington Housing Authority (WHA) |
| Project Lead | Merge 4 Design LLC (M4D) |
| Zoning Jurisdiction | City of Wilmington Zoning Ordinance, Chapter 48 — R-3 District |
| M4D Project Number | M2_2026_005 · April 2026 |

# 02.  Project Context & Construction Scenario Overview

1212 Lobdel Avenue is a 1.39-acre cleared infill site within the City of Wilmington, owned by the Wilmington Housing Authority. The site is zoned R-3 (One-Family Row Houses, Chapter 48) and is targeted for 30+ units of affordable for-sale housing. M4D’s predevelopment analysis evaluated four construction scenarios across the same Scenario I site layout — 36 units, 18 ft wide, 4-row configuration — to give WHA a full-spectrum cost and quality comparison.

## 2.1  Four-Scenario Summary

|  | Scn A CLT/SIP-Hybrid | Scn B Off-Site Modular | Scn C Stick-Build | Scn D Garage-Base / Garden Roof |
| --- | --- | --- | --- | --- |
| Total Units | 36 | 36 | 36 | 36 |
| Unit Configuration | 18 ft × 35 ft, 2-story | 18 ft × 35 ft, 2-story | 18 ft × 35 ft, 2-story | 18 ft × 35 ft, 3-level Garage + L2 + L3 + Garden Roof |
| Unit Size | 1,260 SF | 1,260 SF | 1,260 SF | 1,890 SF (living) |
| Total ROM | $14,875,352 | $9,200,026 | $14,731,123 | $11,123,852 |
| Cost / Unit | $413,204 | $255,556 | $409,198 | $308,995 |
| Gap vs $215K | ~$198K | ~$41K | ~$194K | ~$94K |
| Parking Strategy | Shared rear court | Shared rear court | Shared rear court | Private garage per unit |
| Amenity Zone | 112.6 ft surplus | 112.6 ft surplus | 112.6 ft surplus | 112.6 ft — full community green |

CLT/SIP-Hybrid — Campus Scenario Context The CLT/SIP-Hybrid scenario (Scenario A) reflects current Mid-Atlantic market conditions including a $8–15/SF freight premium on CLT panels sourced from out-of-region suppliers and a Florida supply chain for AAC party wall panels. These premiums are the primary driver of the $413K/unit cost in the current scenario. The Merge4Ward regional manufacturing campus — currently in early development with Wilmington-area project partners — is designed to eliminate both supply chain constraints by establishing Delaware’s first regional CLT/SIP and AAC production facility on the I-95 corridor. When operational, the campus brings the CLT/SIP-Hybrid cost into near-parity with Scenario B (off-site modular), while delivering a noncombustible, energy-efficient, regionally manufactured building system that conventional framing and out-of-state modular cannot match. WHA’s engagement on this project positions it as the anchor client for the campus’s first production run.

## 2.2  Recommended Program — Scenario I Site Layout (All 4 Scenarios)

| Configuration | 4 rows × 9 units per row · 18 ft wide × 35 ft deep per unit |
| --- | --- |
| Total Units | 36 units — exceeds WHA 30-unit target by 20% |
| Site Area | 1.39 acres / ±61,705 SF · 175 ft × 352.6 ft · Site fully cleared |
| Front Setback | 20 ft (adopted) · Exceeds contextual average · Landscaped stoop zone |
| Rear Yard | 20 ft required · 112.6 ft surplus amenity zone beyond Row 4 |
| Max Height | 35 ft / 3 stories · Scenario D height compliance to be confirmed at pre-application |
| Target Sale Price | $200,000 – $235,000 per home |

# 03.  Rough Order of Magnitude Cost Analysis — All Four Scenarios

The following cost estimates are Rough Orders of Magnitude (ROM) based on available site information, current regional labor and material market conditions, and M4D’s predevelopment cost analysis. These figures do not constitute a bid, guarantee, or warranty of construction cost. All values are subject to revision upon receipt of Phase I ESA, geotechnical data, confirmed zoning compliance, and construction type selection.

All four scenarios apply to the Scenario I site layout: 36 units, 4 rows of 9, 18 ft wide × 35 ft deep unit footprint. Scenario A uses Scenario I unit dimensions. Scenario D adds a garage level below the modular stack and a usable garden roof above, expanding the living program to 1,890 SF per unit.

## 3.1  Scenario A — CLT/SIP-Hybrid

*Cross-laminated timber structural panels + structurally insulated envelope panels. Off-site panel fabrication; on-site erection. Current Mid-Atlantic freight premium applies ($8–15/SF). Cost position improves materially when regional manufacturing supply chain is established.

| Line Item | Scn I — 36 Units | Scn II — 40 Units | Scn III — 24 Units |
| --- | --- | --- | --- |
| Gross Floor Area (2-story) | 45,360 SF | 44,800 SF | 36,480 SF |
| Sitework / Civil | $432,000 | $480,000 | $288,000 |
| Foundations (CLT-spec bearing, party wall footings) | $1,179,360 | $1,164,800 | $948,480 |
| CLT Structural Panels (supply + freight premium) | $2,630,880 | $2,598,400 | $2,115,840 |
| SIP Envelope Panels (ext walls + roof) | $907,200 | $896,000 | $729,600 |
| Erection Crew + Crane | $360,000 | $400,000 | $240,000 |
| Rough-in MEP | $1,360,800 | $1,344,000 | $1,094,400 |
| Interior Finishes | $1,905,120 | $1,881,600 | $1,531,360 |
| Doors, Windows, Hardware | $270,000 | $300,000 | $180,000 |
| Appliances Allowance | $144,000 | $160,000 | $96,000 |
| Site Utilities | $306,000 | $340,000 | $204,000 |
| Shared Open Space / Parking Court | $200,000 | $200,000 | $175,000 |
| Landscaping / Fencing / Unit Walks | $162,000 | $180,000 | $108,000 |
| SUBTOTAL — BASE CONSTRUCTION | $9,857,360 | $9,944,800 | $7,710,680 |
| General Conditions (10%) | $985,736 | $994,480 | $771,068 |
| OH&P / GC Fee (8%) | $868,648 | $875,942 | $679,341 |
| Design Contingency (8%) | $937,580 | $945,458 | $733,449 |
| Soft Costs — Arch, Eng, Permits, Testing (12%) | $1,517,678 | $1,530,742 | $1,187,447 |
| Owner Contingency (5%) | $708,350 | $714,571 | $554,099 |
| SCENARIO A — TOTAL ROM | $14,875,352 | $15,005,993 | $11,635,084 |
| Cost Per Unit | $413,204 | $375,150 | $484,795 |
| Gap vs $215K Target | ~$198K/unit | ~$160K/unit | ~$270K/unit |

## 3.2  Scenario B — Off-Site Modular

*Factory-built volumetric modules, crane-set on-site. Fastest schedule, highest quality control, lowest subsidy gap among the four scenarios in current market conditions.

| Line Item | Scn I — 36 Units | Scn II — 40 Units | Scn III — 24 Units |
| --- | --- | --- | --- |
| Gross Floor Area (2-story) | 45,360 SF | 44,800 SF | 36,480 SF |
| Sitework / Civil | $432,000 | $480,000 | $288,000 |
| Foundations (modular-spec slab/piers) | $816,480 | $806,400 | $656,640 |
| Modular Factory Units (factory-complete, MEP rough-in incl.) | $3,009,600 | $3,344,000 | $2,016,000 |
| Freight + Set (crane, transport) | $540,000 | $600,000 | $360,000 |
| Site MEP Tie-Ins + Utility Connections | $306,000 | $340,000 | $204,000 |
| Exterior Finish Completion (siding, roofing, trim) | $726,000 | $716,800 | $583,680 |
| Interior Finish Completion (punch-out items) | $234,000 | $260,000 | $156,000 |
| Shared Open Space / Parking Court | $200,000 | $200,000 | $175,000 |
| Landscaping / Fencing / Unit Walks | $162,000 | $180,000 | $108,000 |
| SUBTOTAL — BASE CONSTRUCTION | $6,426,080 | $6,927,200 | $4,547,320 |
| General Conditions (8%) | $514,086 | $554,176 | $363,786 |
| OH&P / GC Fee (6%) | $416,770 | $449,483 | $294,968 |
| Design Contingency (6%) | $441,776 | $476,452 | $312,606 |
| Soft Costs — Arch, Eng, Permits (12%) | $963,217 | $1,038,759 | $681,321 |
| Owner Contingency (5%) | $438,097 | $472,303 | $309,700 |
| SCENARIO B — TOTAL ROM | $9,200,026 | $9,918,373 | $6,509,701 |
| Cost Per Unit | $255,556 | $247,959 | $271,238 |
| Gap vs $215K Target | ~$41K/unit | ~$33K/unit | ~$56K/unit |

## 3.3  Scenario C — Conventional Stick-Build

*Traditional wood-frame construction. Highest local GC availability; longest schedule; highest labor content. Retained as baseline benchmark for grant applications requiring conventional cost comparison.

| Line Item | Scn I — 36 Units | Scn II — 40 Units | Scn III — 24 Units |
| --- | --- | --- | --- |
| Gross Floor Area (2-story) | 45,360 SF | 44,800 SF | 36,480 SF |
| Sitework / Civil | $432,000 | $480,000 | $288,000 |
| Foundations (slab-on-grade, party wall footings) | $816,480 | $806,400 | $656,640 |
| Framing Lumber + Labor | $1,587,600 | $1,568,000 | $1,276,800 |
| Sheathing + Insulation + Weather Barrier | $589,680 | $582,400 | $474,240 |
| Roofing | $363,480 | $358,400 | $291,840 |
| Exterior Finish (fiber cement + brick base) | $907,200 | $896,000 | $729,600 |
| Rough MEP | $1,587,600 | $1,568,000 | $1,276,800 |
| Insulation + Drywall | $635,040 | $627,200 | $510,720 |
| Interior Finishes | $1,724,688 | $1,702,880 | $1,386,240 |
| Doors, Hardware, Appliances | $414,000 | $460,000 | $252,000 |
| Site Utilities + Connections | $306,000 | $340,000 | $204,000 |
| Shared Open Space / Parking Court | $200,000 | $200,000 | $175,000 |
| Landscaping / Fencing / Unit Walks | $162,000 | $180,000 | $108,000 |
| SUBTOTAL — BASE CONSTRUCTION | $9,725,768 | $9,769,280 | $7,630,080 |
| General Conditions (10%) | $972,577 | $976,928 | $763,008 |
| OH&P / GC Fee (8%) | $855,868 | $859,697 | $671,847 |
| Design Contingency (10%) | $1,055,421 | $1,060,591 | $826,694 |
| Soft Costs (12%) | $1,448,578 | $1,455,011 | $1,134,194 |
| Owner Contingency (5%) | $672,911 | $676,076 | $527,292 |
| SCENARIO C — TOTAL ROM | $14,731,123 | $14,797,583 | $11,553,115 |
| Cost Per Unit | $409,198 | $369,939 | $481,380 |
| Gap vs $215K Target | ~$194K/unit | ~$155K/unit | ~$266K/unit |

## 3.4  Scenario D — Garage-Base / Garden Roof Townhouse (36 Units)

*Scenario D applies to Scenario I site layout (36 units, 18 ft × 35 ft footprint). Level 1: CMU/light steel garage on slab-on-grade. Levels 2–3: Off-site modular living stack (factory-complete). Roof: Usable garden/green roof deck. Living program expands to 1,890 SF per unit (3BR/2.5BA). Shared parking court eliminated — each unit has private garage. Amenity zone (112.6 ft) reprogrammed as full community green. Height compliance with Chapter 48 Sec. 48-151 (35 ft max) to be confirmed at City pre-application meeting.

| Line Item | Scenario I — 36 Units |
| --- | --- |
| Living GFA (L2 + L3, 2-story modular stack) | 68,040 SF (36 × 1,890 SF) |
| Garage GFA (L1, CMU/steel slab-on-grade) | 22,680 SF (36 × 630 SF) |
| Sitework / Civil | $432,000 |
| Foundations — Slab-on-Grade (simplified vs modular pier precision) | $756,000 |
| Garage Level Shell — CMU/light steel, 36 units @ $22,000 | $792,000 |
| Modular Factory Units — L2+L3 living stack, factory-complete, MEP rough-in incl. | $3,009,600 |
| Freight + Set — crane lift over garage podium | $580,000 |
| Site MEP Tie-Ins + Utility Connections | $306,000 |
| Exterior Finish Completion — 3-level facade | $780,000 |
| Interior Finish Completion + Module-to-Garage Interface | $280,000 |
| Garden Roof Deck — usable, structural, waterproofed, 36 units @ $24,000 | $864,000 |
| Amenity Zone / Community Green (visitor parking only, no shared lot) | $120,000 |
| Landscaping / Fencing / Unit Walks | $200,000 |
| SUBTOTAL — BASE CONSTRUCTION | $8,119,600 |
| General Conditions (8%) | $649,568 |
| OH&P / GC Fee (6%) | $487,176 |
| Design Contingency (6%) | $487,176 |
| Soft Costs — Arch, Eng, Permits (12%) | $974,352 |
| Owner Contingency (5%) | $405,980 |
| SCENARIO D — TOTAL ROM | $11,123,852 |
| Cost Per Unit | $308,995 |
| Gap vs $215K Target | ~$94K/unit · ~$3,383,820 total |

## 3.5  Master Comparison Matrix

| Scenario | Units | Total ROM | $/Unit | Gap/Unit | Rating |
| --- | --- | --- | --- | --- | --- |
| A — CLT/SIP-Hybrid (Scn I) | 36 | $14,875,352 | $413,204 | ~$198K | C |
| B — Off-Site Modular (Scn I) | 36 | $9,200,026 | $255,556 | ~$41K | A+ |
| C — Stick-Build (Scn I) | 36 | $14,731,123 | $409,198 | ~$194K | C |
| D — Garage-Base / Garden Roof (Scn I) | 36 | $11,123,852 | $308,995 | ~$94K | B |
| A — CLT/SIP-Hybrid (Scn II, 40 units) | 40 | $15,005,993 | $375,150 | ~$160K | C |
| B — Off-Site Modular (Scn II, 40 units) | 40 | $9,918,373 | $247,959 | ~$33K | A++ |
| C — Stick-Build (Scn II, 40 units) | 40 | $14,797,583 | $369,939 | ~$155K | C |
| A — CLT/SIP-Hybrid (Scn III, 24 units) | 24 | $11,635,084 | $484,795 | ~$270K | D |
| B — Off-Site Modular (Scn III, 24 units) | 24 | $6,509,701 | $271,238 | ~$56K | B |
| C — Stick-Build (Scn III, 24 units) | 24 | $11,553,115 | $481,380 | ~$266K | D |

Rating methodology: A++ = best achievable gap with current financing programs; A+ = gap closeable with single-source subsidy (Delaware Catalyst Fund covers ~70%); B = gap requires layered subsidy (Catalyst Fund + HOME or LIHTC); C = gap requires extraordinary subsidy; D = not financially viable under current affordable housing financing structure without major program subsidy.

# 04.  Scope of Services

M4D proposes services in two tracks. Track A — Predevelopment Intelligence — is authorized and delivered as a standalone fixed-fee engagement. Track B — Architecture & Engineering — is authorized separately upon WHA’s selection of a construction type and yield scenario, and is structured as a lump-sum fee by phase.

## 4.1  Track A — Predevelopment Intelligence (Fixed Fee)

| Item | Deliverable | Format | Schedule |
| --- | --- | --- | --- |
| A1 | Site Assessment — parcel confirmation, governing zoning analysis, applicable code standards | Memo / Data Table | Week 1 |
| A2 | Three Yield Scenarios — unit count, site layout, regulatory envelope confirmation for Scenarios I, II, and III | Report + Site Diagrams | Week 1 |
| A3 | Construction Type Matrix — four systems (A through D) analyzed across all yield scenarios with cost ranges, per-unit cost, and gap analysis | Matrix Report | Week 1–2 |
| A4 | Sustainability Add-Alternate Analysis — geothermal HVAC (shared bore field), community solar PV, and rainwater harvesting; PACE financing applicability noted | Analysis Memo | Week 2 |
| A5 | 3D Site Yield Study & Visualization — massing studies for all yield scenarios; solar access study; drive aisle and amenity zone layout; photorealistic perspectives | 3D Visualizations + Site Plan | Week 2–3 |
| A6 | WHA Presentation Package — scenario comparison, cost matrix, sustainability options, and subsidy gap analysis compiled into a WHA-ready deck (PPTX + PDF) | Presentation Deck | Week 3–4 |
| A7 | Subsidy Gap & Grant Program Memo — Delaware Catalyst Fund, HOME, and DSHA program fit analysis | Memo | Week 3 |
| A8 | Gate 0 ROM Lock — cost estimates reconciled and locked; ALDDB entry initiated | Internal / Summary | Week 4 |

## 4.2  Track B — Architecture & Engineering Services (Lump Sum by Phase)

Track B is authorized separately following WHA’s written selection of yield scenario and construction type. Each phase requires individual written authorization. Fees below are based on the Scenario I site layout (36 units); adjustments will be noted for Scenario D which carries additional design complexity.

| Phase | Scope | Basis | Fee |
| --- | --- | --- | --- |
| B1 | Schematic Design (SD) — all confirmed yield scenarios; unit plan types; 3D visualizations; site plan | Lump Sum | $11,700 |
| B2 | Design Development (DD) — selected scenario; system coordination; structural and panel coordination | Lump Sum | $17,550 |
| B3 | Construction Documents (CD) — permit-ready stamped set; all 36 units | Lump Sum | $35,100 |
| B4 | Permitting & AHJ Coordination — City of Wilmington permit submission; plan review response | Hourly NTE | $5,250 |
| B5 | Construction Administration (CA) — site observation; RFI/submittal review; punch list | Hourly NTE | $9,450 |
| B6 | Reimbursable Expenses — printing, travel, plots (billed at cost) | Actual | ~$4,000 |

Subconsultants (Civil Engineer, Structural Engineer, MEP Engineer) are not included in the M4D fee. Budget approximately 12% of construction cost. Subconsultants will be engaged per written authorization from WHA and M4D.

# 05.  Fee Summary

## 5.1  Track A — Predevelopment Intelligence (Fixed Fee)

| Item | Service | Hrs (Est.) | Rate | Fee |
| --- | --- | --- | --- | --- |
| A1 | Site Assessment & Zoning Analysis | 18 | $185/hr | $3,330 |
| A2 | Three Yield Scenarios + Site Layout | 24 | $185/hr | $4,440 |
| A3 | Construction Type Matrix (4 systems × 3 scenarios) | 8 | $185/hr | $1,480 |
| A4 | Sustainability Add-Alternate Analysis | 6 | $185/hr | $1,110 |
| A5 | 3D Site Yield Study & Visualization | 12 | $165/hr | $1,980 |
| A6 | WHA Presentation Package | 10 | $165/hr | $1,650 |
| A7 | Subsidy Gap & Grant Program Memo | 8 | $165/hr | $1,320 |
| A8 | Gate 0 ROM Lock | 5 | $185/hr | $925 |
|  | TRACK A TOTAL — FIXED FEE | 91 hrs | — | $16,235 |

## 5.2  Track B — Architecture & Engineering (Lump Sum by Phase)

| Phase | Scope | Basis | Fee |
| --- | --- | --- | --- |
| B1 | Schematic Design | Lump Sum | $11,700 |
| B2 | Design Development | Lump Sum | $17,550 |
| B3 | Construction Documents | Lump Sum | $35,100 |
| B4 | Permitting & AHJ Coordination | Hourly NTE | $5,250 |
| B5 | Construction Administration | Hourly NTE | $9,450 |
| B6 | Reimbursable Expenses | Actual | ~$4,000 |
|  | TRACK B SUBTOTAL | — | $83,050 |

## 5.3  Combined Fee & Track A Credit

|  | Amount |
| --- | --- |
| Track A — Predevelopment Intelligence (Fixed Fee) | $16,235 |
| Track B — Architecture & Engineering (Lump Sum by Phase) | $83,050 |
| Track B — Reimbursable Expenses (estimated) | ~$4,000 |
| COMBINED TOTAL — TRACKS A + B | ~$103,285 |
| ★ TRACK A FEE CREDIT — Upon WHA’s written authorization of Track B (full design services through Construction Documents), M4D will credit the full Track A fee of $16,235 against the Track B Phase B1 invoice. This credit reflects M4D’s commitment to a long-term WHA relationship and its confidence in this project proceeding to full design authorization. | ($16,235) |
| NET TOTAL AFTER TRACK A CREDIT (upon Track B authorization) | ~$87,050 |

# 06.  Recommended Next Steps

| # | Action | Lead | Timeline |
| --- | --- | --- | --- |
| 1 | Authorize Track A — Predevelopment Intelligence ($16,235 fixed). Execute M4D PSA M2_2026_005. | WHA + M4D | Immediate |
| 2 | Request City of Wilmington Land Use pre-application meeting — confirm R-3 use, block face setback, 10-unit row cap, overlays, and Scenario D height compliance. | M4D | Week 1 |
| 3 | Order Phase I Environmental Site Assessment — prior school facility history; possible asbestos, underground tanks, contaminated soil. | WHA | Week 1 |
| 4 | Authorize geotechnical investigation (minimum 4 test borings). Critical for foundation design across all four construction types. | WHA | Week 1–2 |
| 5 | Confirm WHA homebuyer income targeting (% AMI) and subordinate financing capacity — determines subsidy stack and Catalyst Fund eligibility. | WHA Finance | Week 2 |
| 6 | RFI to modular manufacturers: 18 ft wide × 35 ft deep × 2-story, 36 units, Mid-Atlantic delivery. Also confirm Scenario D podium-set capability. | M4D | Week 2 |
| 7 | Confirm Delaware Catalyst Fund eligibility for Lobdel at $35K/unit × 36 units = $1.26M. Coordinate with DSHA. | M4D + WHA | Week 2–3 |
| 8 | WHA presentation — all 4 construction types, 3 yield scenarios, ROM comparison, sustainability options. | M4D + WHA | Week 4–5 |
| 9 | WHA construction type selection and written authorization of Track B. Track A credit applied at Phase B1 invoice. | WHA | Post-presentation |

# 07.  Authorization — Track A

To authorize Track A services, please execute this proposal and return a signed copy to M4D. A Professional Services Agreement will be issued upon receipt. Services commence within three (3) business days of executed PSA and receipt of retainer.

| Track A Fixed Fee $16,235.00 Retainer (50% due upon authorization): $8,117.50 | Delivery: 4 weeks from written authorization Governing agreement: M4D PSA M2_2026_012-PSA (to be issued) Invoice: Net 15 days |
| --- | --- |

| AUTHORIZED BY — MERGE 4 DESIGN LLC ____________________________________ Trevor Knight, Dir.of Business Development Merge 4 Design LLC Date: _______________________ ____________________________________ David Ainsworth AIA, Principal-in-Charge Date: _______________________ | AUTHORIZED BY — WILMINGTON HOUSING AUTHORITY __________________________________ Name: _______________________ Title: _______________________ Date: _______________________ |
| --- | --- |

FLAG FOR LEGAL/FINANCIAL REVIEW:  Confirm WHA procurement requirements (DBE/MBE thresholds, HUD Section 3, City of Wilmington local hiring provisions) before contract execution. This proposal does not constitute a contract. ROM figures do not constitute a bid, guarantee, or warranty of construction cost. Professional legal review is recommended prior to execution.