1212 LOBDEL AVENUE

MULTI-UNIT AFFORDABLE INFILL HOUSING  |  WILMINGTON, DE  |  1.39 ACRES

ALDi™ Gate 0 — Rough Order of Magnitude Estimate & Fee Proposal — v3

Prepared for: Wilmington Housing Authority (WHA)  |  Lead Firm: Merge 4 Design LLC (M4D)  |  April 9, 2026  |  Doc No. M2_2026_004

# 01  PROJECT DATA & SITE SUMMARY

| Project Name | 1212 Lobdel Ave — Multi-Unit Affordable Infill Housing |
| --- | --- |
| Parcel ID | 2605130241 |
| Address | 1212 Lobdel Avenue, Wilmington, DE (City of Wilmington limits) |
| Client / Owner | Wilmington Housing Authority (WHA) |
| Lead Firm | Merge 4 Design LLC (M4D) |
| Predevelopment Intelligence | M4Di — Merge 4 Development Institute |
| AOR (if required) | David Ainsworth AIA / Aubyn Architecture LLC (subconsultant to M4D) |
| ALDi™ Gate | G0 — ROM (v3) |
| Governing Zoning Code | City of Wilmington Zoning Ordinance, Chapter 48 (Sec. 48-134 R-3) |
| Zoning District | R-3 — One-Family Row Houses |
| Site Area (Confirmed) | 1.39 acres / ±61,705 SF (175 ft × 352.6 ft) |
| Former Use | School facility — site fully cleared |
| Design Intent | New standard for Lobdel Ave corridor. Improve upon existing undersized housing stock. Demonstrate WHA's capacity to deliver quality urban infill at scale. |
| Front Setback Strategy | 20 ft — intentionally exceeds contextual average (<17 ft on block face). Signals quality and community investment. |
| Program Scenarios | I: 36 units (18 ft wide, recommended) ¦ II: 40 units (16 ft wide, max density) ¦ III: 24 units (20 ft wide, quality/size) |
| Construction Types | A: CLT/SIP Hybrid ¦ B: Off-Site Modular (recommended) ¦ C: Stick-Build |
| Target Sales Price | $200,000 – $235,000 per home |
| Date | April 9, 2026 |

# 02  ZONING STANDARDS & SITE YIELD ANALYSIS

## Governing Code — City of Wilmington Chapter 48

This project is governed by the City of Wilmington Zoning Ordinance (Chapter 48) and the City of Wilmington Building and Building Regulations code. The NCC Unified Development Code does not apply to parcels within the incorporated City of Wilmington limits.

| STANDARD | VALUE | AUTHORITY / NOTES |
| --- | --- | --- |
| District | R-3 — One-Family Row Houses | Sec. 48-134. Row houses (3+ attached) permitted as of right. Detached and semi-detached also permitted. |
| Front Setback (code minimum) | Contextual avg (~10-17 ft) | Sec. 48-154. Average setback of existing buildings on block face. Existing Lobdel Ave stock: generally under 17 ft. |
| Front Setback (this project) | 20 ft (adopted) | M4D/WHA design decision. Exceeds contextual minimum. Creates landscaped stoop zone. Signals new quality standard for corridor. |
| Rear Yard | 20 ft | Sec. 48-155. Confirmed. |
| Side Yard — End Units | 5 ft each | Sec. 48-156. R-3: detached buildings 5 ft each side; end row house units 5 ft exposed side. |
| Side Yard — Interior Units | 0 ft (party wall) | Sec. 48-156. Interior row house units share fire-rated party walls. |
| Max Building Height | 35 ft / 3 stories | Sec. 48-151. Three-story row houses permitted without special approval. |
| Max Units Per Row | 10 units | City Building Code Sec. 504.4.2. Wood-frame (Type 5A) row house group: max 10 units per continuous row, max 3 stories. |
| Min Lot Area Per Unit | No explicit minimum for row houses | Wilmington historic row house lots: 900-1,500 SF. No per-unit area minimum equivalent to NCC UDC. |
| Drive Aisles | 20 ft (adopted) | Private internal drives. City standard alley/private drive width. |

## Site Yield — Design Intent vs Existing Conditions

The existing housing stock on the Lobdel Ave block face consists of narrow row houses on undersized lots — the very conditions that define the neighborhood's housing quality problem. This project is positioned to set a new standard: wider units, deeper lots, better setbacks, and more open space than the existing block. Replicating the narrow existing pattern would be a missed opportunity and a poor WHA demonstration project.

| MEASURE | EXISTING LOBDEL AVE STOCK | THIS PROJECT (SCENARIO I) |
| --- | --- | --- |
| Typical unit width | 14-16 ft (narrow row house) | 18 ft — wider, more livable |
| Front setback | Under 17 ft (cramped stoops) | 20 ft — generous stoop, landscaping zone |
| Unit size (2-story) | ~900-1,100 SF (cramped) | 1,260 SF — proper 3BR/2BA |
| Rear open space | Minimal (alley or postage lots) | 113+ ft shared community zone: parking, garden, green space |
| Design quality | Legacy stock — maintenance-deferred | New construction, energy-efficient, accessible, modern systems |
| Units on 1.39 acres | ~24-28 (historic pattern) | 36 (Scenario I) — 50% more homes on same footprint |

## Site Layout — 4-Row Configuration (Scenarios I & II)

| ZONE | DIMENSION | DESCRIPTION |
| --- | --- | --- |
| Front Setback | 20 ft | From Lobdel Ave property line to Row 1 face. Landscaped stoop zone — planters, stoops, unit entries facing street. |
| Row 1 — Street Front | 35ft deep × 9 units | Units facing Lobdel Ave. Primary street address. Individual stoops to street. |
| Drive Aisle 1 | 20 ft | Private internal drive. Access Row 1 rear / Row 2 front. Shared, maintained by HOA/WHA. |
| Row 2 — Interior | 35ft deep × 9 units | Interior homes. Accessed from Drive Aisles 1 and 2. Courtyard / mews character. |
| Drive Aisle 2 | 20 ft | Private internal drive. Access Row 2 rear / Row 3 front. |
| Row 3 — Interior | 35ft deep × 9 units | Interior homes. Accessed from Drive Aisles 2 and 3. |
| Drive Aisle 3 | 20 ft | Private internal drive. Access Row 3 rear / Row 4 front. |
| Row 4 — Rear | 35ft deep × 9 units | Rear homes. Accessed from Drive Aisle 3. Face shared open space / community zone. |
| Rear Yard | 20 ft | Required per Sec. 48-155. |
| DEPTH USED (Scenario I) | 240 ft | 20 + 4×35 + 3×20 + 20 = 240 ft |
| DEPTH USED (Scenario II) | 240 ft | Identical layout; narrower 16 ft units, same depth |
| SURPLUS DEPTH | 112.6 ft | Shared amenity zone: 30+ space parking court, community garden, bio-retention rain garden, open lawn |
| SITE WIDTH | 175 ft total | 5 ft end side yards each side; Scenario I: 9×18 = 162 ft + 8 ft end buffer; Scenario II: 10×16 = 160 ft + 10 ft |

# 03  YIELD SCENARIO COMPARISON

|  | SCENARIO I — RECOMMENDED | SCENARIO II — MAX DENSITY | SCENARIO III — QUALITY / SIZE |
| --- | --- | --- | --- |
| Configuration | 4-row × 9 units/row | 4-row × 10 units/row | 3-row × 8 units/row |
| Unit Width | 18 ft | 16 ft | 20 ft |
| Unit Depth | 35 ft | 35 ft | 38 ft |
| Unit Size (2-story) | 1,260 SF | 1,120 SF | 1,520 SF |
| Unit Size (3-story option) | 1,890 SF | 1,680 SF | 2,280 SF |
| Total Units | 36 | 40 | 24 |
| Units per Acre | 25.9 du/ac | 28.8 du/ac | 17.3 du/ac |
| Site Depth Used | 240 ft | 240 ft | 194 ft |
| Surplus Depth | 112.6 ft | 112.6 ft | 158.6 ft |
| WHA Target (30 units) | Exceeds by +6 | Exceeds by +10 | Below target |
| Cost/Unit (Scen. B Modular, ROM) | $264,866 | $263,462 | $273,664 |
| Total ROM (Scen. B Modular) | $9,535,176 | $10,538,480 | $6,567,936 |
| Subsidy Gap/Unit vs $215K | ~$49,866 | ~$48,462 | ~$58,664 |
| Total Subsidy Gap | ~$1,795,176 | ~$1,938,480 | ~$1,407,936 |
| Catalyst Fund Potential ($35K/unit) | $1,260,000 | $1,400,000 | $840,000 |
| Remaining Gap after Catalyst | ~$535,176 | ~$538,480 | ~$567,936 |
| Drive Aisles | 3 (between rows) | 3 (between rows) | 2 (between rows) |
| Parking (surplus zone) | 30 spaces min | 32 spaces min | 24 spaces min |

M4D RECOMMENDATION: Scenario I (36 units, 18 ft wide, 1,260 SF) is the primary recommendation. It exceeds the WHA target by 20%, delivers proper 3BR/2BA homes at a width and size meaningfully better than the existing Lobdel Ave housing stock, and produces the best balance of unit count, unit quality, and gap financing achievability. Scenario II (40 units) is presented as the maximum density option if WHA wants to push further. Scenario III is the quality/size benchmark for grant applications requiring conventional comparison.

# 04  CONSTRUCTION TYPE A — CLT / SIP HYBRID

Cross-laminated timber (structural) + structurally insulated panels (envelope). Off-site panel fabrication; on-site erection. Mid-Atlantic freight premium applies. Long-term cost position improves when Merge4Ward regional manufacturing is activated. Precedent: Claymont Hybrid Townhouses (Aubyn Architecture, Wilmington DE).

| LINE ITEM | SCN I — 36 UNITS | SCN II — 40 UNITS | SCN III — 24 UNITS |
| --- | --- | --- | --- |
| Gross Floor Area (2-story) | 45,360 SF | 44,800 SF | 36,480 SF |
| Sitework / Civil (internal drives, walks) | $432,000 | $480,000 | $288,000 |
| Foundations (CLT-spec bearing, party wall footings) | $1,179,360 | $1,164,800 | $948,480 |
| CLT Structural Panels (supply + $12/SF freight) | $2,630,880 | $2,598,400 | $2,115,840 |
| SIP Envelope Panels (exterior walls + roof) | $907,200 | $896,000 | $729,600 |
| Erection Crew + Crane (shared sequential) | $360,000 | $400,000 | $240,000 |
| Rough-in MEP (plumbing, elec, HVAC) | $1,360,800 | $1,344,000 | $1,094,400 |
| Interior Finishes (flooring, paint, cabinets, fixtures) | $1,905,120 | $1,881,600 | $1,531,360 |
| Doors, Windows, Hardware (bulk order) | $270,000 | $300,000 | $180,000 |
| Appliances Allowance | $144,000 | $160,000 | $96,000 |
| Site Utilities (connections, shared mains) | $306,000 | $340,000 | $204,000 |
| Shared Open Space / Parking Court (amenity zone) | $200,000 | $200,000 | $175,000 |
| Landscaping / Fencing / Unit Walks | $162,000 | $180,000 | $108,000 |
| SUBTOTAL — BASE CONSTRUCTION | $9,857,360 | $9,944,800 | $7,710,680 |
| General Conditions (10%) | $985,736 | $994,480 | $771,068 |
| OH&P / GC Fee (8%) | $868,648 | $875,942 | $679,341 |
| Design Contingency (8%) | $937,580 | $945,458 | $733,449 |
| Soft Costs — Arch, Eng, Permits, Testing (12%) | $1,517,678 | $1,530,742 | $1,187,447 |
| Owner Contingency (5%) | $708,350 | $714,571 | $554,099 |
| SCENARIO A — TOTAL ROM | $14,875,352 | $15,005,993 | $11,635,084 |
| Cost Per Unit | $413,204 | $375,150 | $484,795 |
| Gap vs $215K Target | ~$198K/unit | ~$160K/unit | ~$270K/unit |

CLT/SIP gap is significant at current Mid-Atlantic freight premiums. This scenario is best positioned as a demonstration/innovation project and M4Di ALDDB data collection asset. Costs improve materially once Merge4Ward regional manufacturing is established.

# 05  CONSTRUCTION TYPE B — OFF-SITE MODULAR (RECOMMENDED)

Factory-built volumetric modules, crane-set on-site. Best-in-class precedent: Kinexx (Chicago urban infill), ProCon (Mid-Atlantic). Fastest schedule, highest quality control, lowest subsidy gap. Modular manufacturers should be briefed on 18 ft wide × 35 ft deep × 2-story footprint for Scenario I.

| LINE ITEM | SCN I — 36 UNITS | SCN II — 40 UNITS | SCN III — 24 UNITS |
| --- | --- | --- | --- |
| Gross Floor Area (2-story) | 45,360 SF | 44,800 SF | 36,480 SF |
| Sitework / Civil | $432,000 | $480,000 | $288,000 |
| Foundations (modular-spec slab/piers) | $816,480 | $806,400 | $656,640 |
| Modular Factory Units (factory-complete, MEP rough-in incl.) | $3,009,600 | $3,344,000 | $2,016,000 |
| Freight + Set (crane, transport, ~200 mi) | $540,000 | $600,000 | $360,000 |
| Site MEP Tie-Ins + Utility Connections | $306,000 | $340,000 | $204,000 |
| Exterior Finish Completion (siding, roofing, trim) | $726,000 | $716,800 | $583,680 |
| Interior Finish Completion (punch-out items) | $234,000 | $260,000 | $156,000 |
| Shared Open Space / Parking Court | $200,000 | $200,000 | $175,000 |
| Landscaping / Fencing / Unit Walks | $162,000 | $180,000 | $108,000 |
| SUBTOTAL — BASE CONSTRUCTION | $6,426,080 | $6,927,200 | $4,547,320 |
| General Conditions (8%) | $514,086 | $554,176 | $363,786 |
| OH&P / GC Fee (6%) | $416,770 | $449,483 | $294,968 |
| Design Contingency (6%) | $441,776 | $476,452 | $312,606 |
| Soft Costs — Arch, Eng, Permits (12%) | $963,217 | $1,038,759 | $681,321 |
| Owner Contingency (5%) | $438,097 | $472,303 | $309,700 |
| SCENARIO B — TOTAL ROM | $9,200,026 | $9,918,373 | $6,509,701 |
| Cost Per Unit | $255,556 | $247,959 | $271,238 |
| Gap vs $215K Target | ~$40,556/unit | ~$32,959/unit | ~$56,238/unit |

Scenario I (36 units, Modular) achieves a ~$40,556/unit gap — the most favorable financing position of any scenario in this analysis. Delaware Catalyst Fund at $35K/unit × 36 = $1.26M covers roughly 70% of the total gap. WHA soft second handles the remaining ~$200K. This is effectively a single-source-closeable gap.

# 06  CONSTRUCTION TYPE C — CONVENTIONAL STICK-BUILD

Traditional wood-frame construction. Highest local GC availability; longest schedule; highest labor content. Retain as base-case benchmark for grant applications.

| LINE ITEM | SCN I — 36 UNITS | SCN II — 40 UNITS | SCN III — 24 UNITS |
| --- | --- | --- | --- |
| Gross Floor Area (2-story) | 45,360 SF | 44,800 SF | 36,480 SF |
| Sitework / Civil | $432,000 | $480,000 | $288,000 |
| Foundations (slab-on-grade, party wall footings) | $816,480 | $806,400 | $656,640 |
| Framing Lumber + Labor | $1,587,600 | $1,568,000 | $1,276,800 |
| Sheathing + Insulation + Weather Barrier | $589,680 | $582,400 | $474,240 |
| Roofing (asphalt shingle, standard gable) | $363,480 | $358,400 | $291,840 |
| Exterior Finish (fiber cement + brick base) | $907,200 | $896,000 | $729,600 |
| Rough MEP (full site labor) | $1,587,600 | $1,568,000 | $1,276,800 |
| Insulation + Drywall | $635,040 | $627,200 | $510,720 |
| Interior Finishes | $1,724,688 | $1,702,880 | $1,386,240 |
| Doors, Hardware, Appliances (bulk order) | $414,000 | $460,000 | $252,000 |
| Site Utilities + Connections | $306,000 | $340,000 | $204,000 |
| Shared Open Space / Parking Court | $200,000 | $200,000 | $175,000 |
| Landscaping / Fencing / Unit Walks | $162,000 | $180,000 | $108,000 |
| SUBTOTAL — BASE CONSTRUCTION | $9,725,768 | $9,769,280 | $7,630,080 |
| General Conditions (10%) | $972,577 | $976,928 | $763,008 |
| OH&P / GC Fee (8%) | $855,868 | $859,697 | $671,847 |
| Design Contingency (10%) | $1,055,421 | $1,060,591 | $826,694 |
| Soft Costs (12%) | $1,448,578 | $1,455,011 | $1,134,194 |
| Owner Contingency (5%) | $672,911 | $676,076 | $527,292 |
| SCENARIO C — TOTAL ROM | $14,731,123 | $14,797,583 | $11,553,115 |
| Cost Per Unit | $409,198 | $369,939 | $481,380 |
| Gap vs $215K Target | ~$194K/unit | ~$155K/unit | ~$266K/unit |

# 07  MASTER COMPARISON MATRIX

| SCENARIO | UNITS | CONST TYPE | TOTAL ROM | $/UNIT | GAP/UNIT | TOTAL GAP | RATING |
| --- | --- | --- | --- | --- | --- | --- | --- |
| I — 36 units, 18ft | 36 | A CLT/SIP | $14,875,352 | $413,204 | ~$198K | ~$7.1M | C |
| I — 36 units, 18ft | 36 | B Modular | $9,200,026 | $255,556 | ~$41K | ~$1.5M | A+ |
| I — 36 units, 18ft | 36 | C Stick | $14,731,123 | $409,198 | ~$194K | ~$7.0M | C |
| II — 40 units, 16ft | 40 | A CLT/SIP | $15,005,993 | $375,150 | ~$160K | ~$6.4M | C |
| II — 40 units, 16ft | 40 | B Modular | $9,918,373 | $247,959 | ~$33K | ~$1.3M | A++ |
| II — 40 units, 16ft | 40 | C Stick | $14,797,583 | $369,939 | ~$155K | ~$6.2M | C |
| III — 24 units, 20ft | 24 | A CLT/SIP | $11,635,084 | $484,795 | ~$270K | ~$6.5M | D |
| III — 24 units, 20ft | 24 | B Modular | $6,509,701 | $271,238 | ~$56K | ~$1.4M | B |
| III — 24 units, 20ft | 24 | C Stick | $11,553,115 | $481,380 | ~$266K | ~$6.4M | D |

# 08  SUSTAINABILITY ADD ALTERNATES

All add alternates are optional scope additions to any base scenario and construction type. At 36-40 units, shared geothermal well field and community solar array are now viable at scale.

| ADD ALTERNATE | PER UNIT | SCN I (36) | SCN II (40) | NOTES |
| --- | --- | --- | --- | --- |
| ADD ALT 1 — Geothermal HVAC (shared well field) | $13,500 | +$486,000 | +$540,000 | Shared bore field viable at 36-40 units. Per-unit cost lower than individual systems. PACE-financeable. |
| ADD ALT 2 — Solar PV (community array, 4kW/unit equiv.) | $9,000 | +$324,000 | +$360,000 | Community solar array on parking court canopy or rear rooftops. Net metering for all 36-40 units. |
| ADD ALT 3 — Rainwater Harvesting (shared cistern) | $4,000 | +$144,000 | +$160,000 | Single shared cistern in amenity zone. Landscape irrigation + toilet flushing. |
| COMBINED Sustainability Package | $26,500 | +$954,000 | +$1,060,000 | All three. Energize Delaware PACE eliminates upfront cost. Green building certification (LEED or Enterprise Green Communities) possible. |

# 09  CBAI / BLENDER WORKFLOW — SITE TO WHA PRESENTATION

Steps 1-2 are ready to execute immediately with confirmed site dimensions and setbacks. Travis leads visualization output; David owns Steps 1, 7, and 8.

| STEP | PHASE | METHOD | OUTPUT |
| --- | --- | --- | --- |
| 1 | Site Model — READY | Regrid API: parcel 2605130241, 175×352.6ft. Bonsai MCP: import boundary, set datum, model 20ft front / 20ft rear setbacks, 20ft drive aisles, 5ft end side yards. Confirm block face avg for street context. | 3D site model with 4-row grid, regulatory envelopes, and Lobdel Ave street context |
| 2 | 3 Scenario Massing | Blender IFC massing: Scenario I (4-row 9-unit), Scenario II (4-row 10-unit), Scenario III (3-row 8-unit). Solar access study each. Flag 10-unit row group fire separation. | 3 massing studies with unit count, density, and solar access comparison |
| 3 | Environmental Study | Ladybug/Honeybee: solar insolation for PV sizing; shading between rows; bio-retention drainage flow in 112ft surplus zone; geothermal bore field layout study. | PV sizing map; shading compliance; drainage report |
| 4 | Selected Scheme BIM | Bonsai BIM: Scenario I to schematic level. Modular panel grid (18ft×35ft units). Structural bay logic. Party wall fire separation. Shared drive and parking court layout. | Schematic BIM with system coordination and panel layout |
| 5 | Renderings | Blender Cycles: Wilmington urban palette (brick base course, fiber cement panels, painted wood trim). Photomatch Lobdel Ave street view. 2 perspectives per scenario. | 9 photorealistic renderings total (3 scenarios × 3 views); aerial site plan overlay |
| 6 | ROM Reconciliation | Export confirmed areas from Bonsai BIM → update M4Di OI Tool. Reconcile v3 ROM assumptions with BIM takeoffs. Lock ALDi G0. | Quantity-verified ROM; ALDi G0 locked; ALDDB row initiated |
| 7 | WHA Presentation | Travis: compile renderings, site plan, scenario comparison, ROM matrix, sustainability options, schedule, and fee proposal into WHA deck (PPTX + PDF). | WHA presentation deck ready for delivery |

# 10  OUTSTANDING DATA GAPS — G0 CANNOT FULLY LOCK UNTIL RESOLVED

| # | UNKNOWN | IMPACT | RESOLUTION PATH |
| --- | --- | --- | --- |
| 1 | Front setback — confirmed block face average for Lobdel Ave | HIGH | City of Wilmington Land Use pre-application meeting. Block face average determines contextual setback. Our 20ft design exceeds it — this is intentional, not a compliance question. |
| 2 | City of Wilmington R-3 use confirmation on this specific parcel | HIGH | Pre-application meeting. Confirm row house use as-of-right; confirm 10-unit row group cap applies; confirm no overlay districts. |
| 3 | Phase I ESA — environmental status | HIGH | Order immediately. Site history as school facility. Possible asbestos, underground tanks, contaminated soil. |
| 4 | FEMA flood zone classification | HIGH | FEMA Map Service Center. If Zone AE, elevated slab required across all scenarios. |
| 5 | Soil bearing / geotechnical | MEDIUM-HIGH | GEOTILL borings. Critical for modular foundation design (precise bearing required at module set points). |
| 6 | Utility capacity at Lobdel Ave (water/sewer/gas/elec) | MEDIUM | City of Wilmington public works + utility companies. 36-40 units is a significant demand increase on existing mains. |
| 7 | WHA homebuyer income targeting (% AMI) | MEDIUM | Determines subsidy stack. 80-120% AMI = Catalyst Fund. Below 80% AMI = LIHTC. Critical for financing strategy. |
| 8 | Modular manufacturer lead time and capacity (18ft×35ft unit) | MEDIUM | RFI to ProCon, Impresa, Apex Modular. 18ft width is non-standard for some manufacturers — confirm availability. |
| 9 | WHA equity contribution / subordinate financing capacity | MEDIUM | WHA finance team meeting. Determines how much subsidy WHA can layer vs external programs. |
| 10 | HOA / shared infrastructure governance | LOW | City of Wilmington City Solicitor or WHA legal counsel. Shared drives and open space require declaration of covenants or WHA-retained ownership structure. |

# 11  PROFESSIONAL FEE PROPOSAL — MERGE 4 DESIGN LLC

All services delivered under Merge 4 Design LLC (M4D) as lead firm. Aubyn Architecture LLC available as AOR subconsultant to M4D if WHA or AHJ requires a licensed Delaware AOR on the permit set. Track A (M4Di predevelopment intelligence) can be authorized immediately as a standalone engagement.

| SERVICE | PHASE | HOURS (EST.) | RATE | FEE |
| --- | --- | --- | --- | --- |
| TRACK A — M4Di PREDEVELOPMENT INTELLIGENCE (M4D) |
| A1 — ALDi G0 ROM: v1-v3 site assessment + zoning research | G0 | 18 | $185 | $3,330 |
| A2 — Three yield scenarios + construction type matrix | G0 | 24 | $185 | $4,440 |
| A3 — Sustainability add-alt analysis (36 + 40 unit scale) | G0 | 6 | $185 | $1,110 |
| A4 — CBai/Blender site yield study + massing (Steps 1-2) | G0 | 12 | $165 | $1,980 |
| A5 — WHA presentation package (deck + all ROM exhibits) | G0 | 10 | $165 | $1,650 |
| A6 — Subsidy gap analysis + grant program memo (Catalyst, HOME, DSHA) | G0 | 8 | $165 | $1,320 |
| A7 — ALDi G0 lock + M4Di OI Tool setup (36-unit program) | G0 | 5 | $185 | $925 |
| TRACK A SUBTOTAL — M4Di PREDEVELOPMENT (FIXED FEE) | 83 hrs |  | $14,755 |
| TRACK B — ARCHITECTURE & ENGINEERING (M4D LEAD FIRM) |
| B1 — Schematic Design (SD) — all 3 yield scenarios; CBai renderings | SD | 60 | $195 | $11,700 |
| B2 — Design Development (DD) — selected scenario | DD | 90 | $195 | $17,550 |
| B3 — Construction Documents (CD) — 36-unit standardized row house set | CD | 180 | $195 | $35,100 |
| B4 — Permitting + City of Wilmington AHJ coordination | CD/CA | 30 | $175 | $5,250 |
| B5 — Construction Administration (CA) | CA | 54 | $175 | $9,450 |
| B6 — Reimbursable Expenses (travel, printing, plots) | All | — | Actual | $4,000 est. |
| TRACK B SUBTOTAL — A&E SERVICES (HOURLY NTE PER PHASE) | 414 hrs |  | $83,050 |
| TOTAL — TRACKS A + B COMBINED | 497 hrs |  | $97,805 |
| AS % OF SCENARIO I / SCENARIO B TOTAL ROM ($9.2M) |  |  | ~1.06% |

- Track A ($14,755 fixed) can be authorized immediately, independent of design authorization.

- Track B is hourly not-to-exceed. Phases B2-B5 each require separate written authorization at the relevant ALDi gate.

- Subconsultants (civil, structural, MEP) not included. Recommend Merestone (civil), Carson Structural, Paragon (MEP, contact Ben). Budget 12% of construction cost: ~$1.1M at Scenario I/B basis.

- If WHA requires a licensed Delaware AOR on the permit set and M4D's license is not sufficient, Aubyn Architecture LLC can serve as AOR subconsultant to M4D. AOR subconsultant fee to be separately proposed.

- FLAG FOR LEGAL/FINANCIAL REVIEW: Confirm WHA procurement requirements (DBE/MBE thresholds, HUD Section 3, City of Wilmington local hiring provisions) before contract execution.

# 12  RECOMMENDED NEXT STEPS

| # | ACTION | LEAD | TIMELINE |
| --- | --- | --- | --- |
| 1 | Authorize Track A — M4Di Predevelopment ($14,755 fixed). Issue M4D PSA. | WHA + David | Immediate |
| 2 | Request City of Wilmington Land Use pre-application meeting. Confirm R-3 use, block face setback, 10-unit row cap, overlays. | David | Week 1 |
| 3 | Order Phase I ESA — GEOTILL or approved environmental firm. | WHA / David | Week 1 |
| 4 | Site visit — David + Travis (photo documentation, street context, existing conditions, block face measurement). | David + Travis | Week 1 |
| 5 | Confirm parcel is within City of Wilmington incorporated limits (not NCC unincorporated). Pull City of Wilmington GIS parcel layer. | David | This week |
| 6 | Initiate CBai/Blender site model — Steps 1-2 of workflow. Update to 4-row layout, 20ft front / 20ft rear setbacks. | Travis + David | Week 1-2 |
| 7 | RFI to modular manufacturers: 18ft wide × 35ft deep × 2-story, quantity 36 units, Mid-Atlantic delivery. Confirm lead time. | David | Week 2 |
| 8 | Confirm WHA income targeting (% AMI) and subordinate financing capacity. | Leo + WHA Finance | Week 2 |
| 9 | Order geotechnical borings — GEOTILL. Especially critical for modular foundation bearing design. | WHA / David | Week 2-3 |
| 10 | Complete CBai renderings + WHA presentation deck (Steps 3-7 of workflow). | Travis | Week 3-4 |
| 11 | WHA presentation — 3 yield scenarios, 3 construction types, ROM comparison, sustainability options. | David + Travis + Trevor | Week 4-5 |
| 12 | WHA scenario selection and authorization of Track B (SD). | WHA | Post-presentation |

This is ALDi™ Gate 0 ROM Document v3. Supersedes all prior versions and addenda. Governing zoning authority: City of Wilmington Zoning Ordinance, Chapter 48. Cost estimates are rough orders of magnitude based on limited site information and do not constitute a bid, guarantee, or contract. Professional legal and financial review is recommended prior to authorization of design services or financing applications. All values subject to revision upon receipt of Phase I ESA, geotechnical data, and confirmed zoning compliance.

David Ainsworth AIA  |  Merge 4 Design LLC  |  M4Di Predevelopment Intelligence

215 N Market St, Suite 317, Wilmington DE 19801  |  david4d@merge4design.com