PROFESSIONAL FEE PROPOSAL 1212 Lobdel Avenue — Attainable Homeownership Development Wilmington, DE · Predevelopment Intelligence Services · April 23, 2026

| Submitted To | Wilmington Housing Authority (WHA) · Wilmington, DE |
| --- | --- |
| Submitted By | Merge 4 Design LLC (M4D) · 500 Delaware Ave., Suite 1 #1551, Wilmington, DE 19899 · 302 367 5726 · merge4design.com |
| Date Submitted | April 23, 2026 |
| Project Reference | M2_2026_005 · 1212 Lobdel Avenue |
| Proposal Valid | 90 days from submission date |

01.  Project Identification

| Project Name | 1212 Lobdel Avenue — Attainable Homeownership Development |
| --- | --- |
| Parcel ID | 2605130241 |
| Address | 1212 Lobdel Avenue, Wilmington, DE (City of Wilmington limits) |
| Client / Owner | Wilmington Housing Authority (WHA) |
| Project Lead | Merge 4 Design LLC (M4D) |
| Zoning Jurisdiction | City of Wilmington Zoning Ordinance, Chapter 48 — R-3 District |
| M4D Project Number | M2_2026_005 · April 23, 2026 |

02.  Project Context

1212 Lobdel Avenue is a 1.39-acre cleared infill site within the City of Wilmington, zoned R-3 (One-Family Row Houses, Chapter 48). The site is targeted for 30 or more units of for-sale attainable homeownership under WHA’s homeownership program, with a target sale price of $200,000–$235,000 per home at 80% AMI.

WHA has confirmed a preference for fee-simple individual lot ownership with standard deeds — the appropriate structure for first-time homebuyer FHA and conventional financing. M4D’s predevelopment scope delivers the full analysis needed to bring WHA to an informed yield configuration and construction type decision within a four-week engagement.

Track B — Architecture and Engineering — is scoped and priced in Section 03 for WHA’s planning purposes and will be authorized separately upon written selection of yield scenario and construction type.

03.  Scope of Services & Fee

M4D proposes services in two tracks. Track A — Predevelopment Intelligence — is authorized as a standalone fixed-fee engagement and delivered within four weeks. Track B — Architecture & Engineering — is authorized separately upon WHA’s written selection of yield option and construction type.

WHA Program Additions — Incorporated into Track A Scope Unit width targets: WHA has requested that yield analysis prioritize 18 ft and 20 ft wide lot configurations across all yield options (Options B, A+FW12, and D). Both widths will be carried through the construction cost matrix and site plan yield study. Rear attached garage with occupiable roof deck: WHA has requested inclusion of a rear attached garage typology with the garage roof deck programmed as occupiable outdoor space accessed directly from the second-level living area. This adds a meaningful square footage premium and private outdoor amenity to each unit without increasing lot footprint, and will be carried as a distinct line item in the construction type matrix. Roofline variety study: WHA’s baseline preference is a standard A-shaped gable roof. The 3D site yield study will present a full range of roofline profiles within the 35 ft R-3 height limit — gable, shed, hip, and flat/garden roof — with the flat garden roof option specifically targeted at or near the same ROM price point as the traditional gable. All roofline options will be carried across both 18 ft and 20 ft wide unit widths on a 2-story footprint.

3.1  Track A — Predevelopment Intelligence  (Fixed Fee: $16,235)

The table below is the single combined scope, schedule, and fee reference for Track A.

| Item | Deliverable — Description | Format | Schedule | Hrs | Rate | Fee |
| --- | --- | --- | --- | --- | --- | --- |
| A1 | Site Assessment — parcel confirmation, Chapter 48 R-3 zoning analysis, applicable code standards and overlays | Memo | Wk 1 | 18 | $185 | $3,330 |
| A2 | Yield Scenario Analysis — fee-simple lot configurations for 18 ft and 20 ft wide units across Options B, A+FW12, and D; regulatory envelope confirmation | Report + Plans | Wk 1 | 24 | $185 | $4,440 |
| A3 | Construction Type Matrix — four systems (CLT/SIP-Hybrid, Off-Site Modular, Stick-Build, Garage-Base/Garden Roof) across all yield options and both unit widths; per-unit cost and gap analysis; rear garage typology as discrete add-alternate | Matrix Report | Wk 1–2 | 8 | $185 | $1,480 |
| A4 | Sustainability Add-Alternate — geothermal HVAC (shared bore field), community solar PV aisle canopy, rainwater harvesting; PACE financing and virtual net metering applicability | Analysis Memo | Wk 2 | 6 | $185 | $1,110 |
| A5 | 3D Site Yield Study & Visualization — massing studies for all yield options across 18 ft and 20 ft widths; full roofline profile study (gable, shed, hip, flat/garden roof) within 35 ft height limit; flat garden roof cost-parity analysis; solar access analysis; photorealistic perspectives | 3D + Site Plan | Wk 2–3 | 12 | $165 | $1,980 |
| A6 | WHA Presentation Package — all yield options, unit widths, roofline profiles, construction cost matrix, sustainability options, subsidy gap analysis (PPTX + PDF) | Presentation | Wk 3–4 | 10 | $165 | $1,650 |
| A7 | Subsidy Gap & Grant Program Memo — Delaware Catalyst Fund, HOME, DSHA program fit; per-unit gap analysis by option | Memo | Wk 3 | 8 | $165 | $1,320 |
| A8 | Gate 0 ROM Lock — cost estimates reconciled and locked; ALDDB entry initiated | Summary | Wk 4 | 5 | $185 | $925 |
|  | TRACK A TOTAL — FIXED FEE |  | 4 weeks | 91 hrs | — | $16,235 |

3.2  Track B — Architecture & Engineering  (Authorized Separately)

Fees below are based on the 36-unit baseline. Yield Option D (54 units) or a rear garage typology addition will be subject to a fee addendum. Subconsultants (Civil, Structural, MEP) are not included; budget approximately 12% of construction cost.

| Phase | Scope | Basis | Fee |
| --- | --- | --- | --- |
| B1 | Schematic Design — selected yield option and unit width; roofline profiles; unit plan types; 3D visualizations; site plan | Lump Sum | $11,700 |
| B2 | Design Development — system coordination; structural and panel coordination | Lump Sum | $17,550 |
| B3 | Construction Documents — permit-ready stamped set | Lump Sum | $35,100 |
| B4 | Permitting & AHJ Coordination — City of Wilmington permit submission; plan review response | Hourly NTE | $5,250 |
| B5 | Construction Administration — site observation; RFI/submittal review; punch list | Hourly NTE | $9,450 |
| B6 | Reimbursable Expenses (at cost) | Actual | ~$4,000 |
|  | TRACK B SUBTOTAL | — | $83,050 |

3.3  Combined Fee & Track A Credit

|  | Amount |
| --- | --- |
| Track A — Predevelopment Intelligence (Fixed Fee) | $16,235 |
| Track B — Architecture & Engineering | $83,050 |
| Track B — Reimbursable Expenses (estimated) | ~$4,000 |
| COMBINED TOTAL — TRACKS A + B | ~$103,285 |
| ★ TRACK A FEE CREDIT — Upon WHA’s written authorization of Track B (full design services through Construction Documents), M4D will credit the full Track A fee of $16,235 against the Track B Phase B1 invoice. | ($16,235) |
| NET TOTAL AFTER TRACK A CREDIT | ~$87,050 |

04.  Authorization — Track A

To authorize Track A services, execute this proposal and return a signed copy to M4D. A Professional Services Agreement (PSA M2_2026_005) will be issued upon receipt. Services commence within three (3) business days of executed PSA and receipt of retainer.

| Track A Fixed Fee $16,235.00 Retainer (50% due upon authorization): $8,117.50 Balance due upon delivery of final Track A deliverables. | Delivery: 4 weeks from written authorization Governing agreement: M4D PSA M2_2026_005 Invoice: Net 15 days Payment by check (payable to Merge 4 Design LLC) or ACH — banking instructions provided separately upon execution. |
| --- | --- |

Upon authorization, M4D will initiate the following in Week 1 alongside Track A delivery:

| # | Immediate action item | Lead |
| --- | --- | --- |
| 1 | Execute PSA M2_2026_005 and submit Track A retainer invoice. | M4D |
| 2 | Request City of Wilmington Land Use pre-application meeting: R-3 use confirmation; block face setback; 10-unit row fire code; Scenario D height (Sec. 48-151); rear yard easement interpretation for yield Options B and D; cross street rear boundary and 15 ft rear yard variance feasibility for Option A+FW12. | M4D |
| 3 | Order Phase I ESA (prior school facility; asbestos, tanks, soil risk). | WHA |
| 4 | Authorize geotechnical investigation — minimum 4 borings; required for foundation design and geothermal bore field feasibility. | WHA |
| 6 | Confirm Delaware Catalyst Fund eligibility pathway; Energize Delaware PACE on fee-simple lots; Delmarva Power virtual net metering for HOA subscriber structure. | M4D |

| AUTHORIZED BY — MERGE 4 DESIGN LLC _______________________________________ Trevor Knight, Director of Business Development Merge 4 Design LLC Date: ________________________ _______________________________________ David C. Ainsworth AIA, Principal-in-Charge Aubyn Architecture LLC (AOR) Date: ________________________ | AUTHORIZED BY — WILMINGTON HOUSING AUTHORITY _______________________________________ Name: _______________________ Title: _______________________ Date: ________________________ |
| --- | --- |

FLAG FOR LEGAL/FINANCIAL REVIEW:  Confirm WHA procurement requirements (DBE/MBE thresholds, HUD Section 3, City of Wilmington local hiring provisions) before contract execution. This proposal does not constitute a contract. Professional legal review recommended prior to execution.