## COVER
M4Di ¦ ALDi Design & Construction Budget Tracker
Forward Home Program · City of Wilmington Vacant Lot Initiative
Project Name / Code: |  |  | Enter official M4Di project code (e.g., FH-WIL-001)
Project Address: |  |  | Full site address including lot numbers
Owner / Client: | L.E.E.P., Inc. / City of Wilmington Program |  | Legal entity name
Architect of Record: | Aubyn Architecture LLC (AOR) ¦ M4D lead
M4Di Project Lead:
Gross Area (SF — all units): | 13500 |  | Total project SF: units × SF/unit
ALDi Start Date: |  |  | Date M4Di ALDi engagement begins
ROM Estimate Date: | May 2026 |  | Date of M4Di G0 ROM
ALDi Gate Status: | Gate 0 — ROM Baseline In Progress
COLUMN GUIDE — Four Estimate Stages (ALDi Gate Architecture)
Column D M4Di ROM | Rough Order of Magnitude | At ALDi Gate 0 (G0) | The locked baseline. Never changes after ALDi Gate 0. All variances measured against this.
Column E 75% DD Estimate | Design Development (75%) | At ALDi Gate 2 | First major design-informed reality check. Variance >15% triggers formal review and log entry.
Column F 100% CD / SOV | Construction Documents / GMP | At ALDi Gate 3 | The contracted number. All future change orders are logged against this column.
Column G Actual Cost | Construction Closeout | Updated monthly G4 | Running total of all committed costs: executed SOV line items + approved change orders.

## ASSUMPTIONS
PROJECT ASSUMPTIONS & CONTROLS
Forward Home Program · M4Di OI Tool v2 · G0 ROM ±25%
Input | Value | Notes
A — PROJECT BASIS
Project Name | Forward Home — Type D 10-Unit Cluster | Enter the official M4Di project code (e.g., FH-WIL-001)
Estimate Date | May 2026 | Enter as MM/DD/YYYY. Update with each revision.
Estimate Type | ROM / Conceptual | ROM / Conceptual ¦ Schematic ¦ Design Development ¦ GMP
Project Type | New Construction — Residential | New Construction ¦ Adaptive Reuse ¦ Interior Improvement
Client / Owner | L.E.E.P., Inc. / City of Wilmington Program | Legal entity name of the owner organization.
Site Address | City of Wilmington Vacant Lot Cluster, Wilmington DE 19801 | Full property address for zoning lookup reference.
Total Gross Area (SF) — per unit | 1350 | Gross floor area per unit. Total = this × number of units.
Number of units (Type D cluster) | 10 | Pilot: 10-unit lot cluster. Adjust for Type A (4 units).
Total Project SF (all units) | 13500 | Computed: unit SF × number of units.
Base Region | Delaware | Delaware = M4Di baseline. All unit prices sourced from DE bid data.
Selected Pricing Region | New Castle / Wilmington | Must match REGIONAL FACTORS regional factor table.
B — COST ESCALATION
ENR Construction Cost Index (CCI) escalation % | 2.7% | Source: ENR CCI Q1 2026. Update quarterly. Applied to labor-intensive items.
ENR Building Cost Index (BCI) escalation % | 4.3% | Source: ENR BCI Q1 2026. Update quarterly. Applied to material-intensive items.
Blended escalation rate | 2.7% | Average of CCI and BCI. Applied uniformly in unit price library.
Material / market factor | 1 | Adjust for procurement pressure, bid climate, supply chain risk. 1.00 = neutral.
C — MARKUPS & CONTINGENCIES
General Conditions (GC) % | 8% | Typical range: 6%–10%. On-site supervision, temp facilities, insurance.
Overhead & Profit (OH&P) % | 10% | Typical range: 8%–12%. Applied to subtotal after GC.
Design Contingency % | 12% | Reduce to 8% at SD; 5% at DD; 0% at GMP. ROM = 12%.
Existing Conditions Contingency % | 0% | New construction = 0%. Renovation/adaptive reuse: 8%–15%.
Owner Selection / Equipment Contingency % | 5% | Reduce as owner selections confirmed. Tier upgrades reduce this.
Bid / Permit / Bonds % | 2% | Permitting fees, bid bonds, performance bonds. Delaware residential.
Total Contingency % | 17% | Sum of all contingency lines. ROM = ~17%.
D — HARD COST UNIT RATES (blended installed per floor SF — all tiers)
4Ward-SIB Forward Panel — base (all tiers) | 31.11 | Blended installed per floor SF · $42K/unit at 1,350 SF · Barricade INDEVCO ROM May 2026
Foundation — T1 CMU/poured slab | 20.74 | $28K/unit at 1,350 SF · Includes CMU party wall bearing element
Foundation — T2–T4 Superior Walls Xi Plus | 22.22 | $30K/unit · TER 2211-02 (DrJ/ANAB) · premium over T1 CMU
MEP base — T1 std mini-split HVAC + plumbing + electrical | 14.07 | $19K/unit · cold-climate mini-split SEER2 ≥18 · residential MEP bundle
MEP base — T2 Quilt 3-zone + plumbing + electrical | 15.56 | $21K/unit · SEER2 25.3 / HSPF2 12 · ERV separate line item
MEP base — T3–T4 Mitsubishi FX H2i sumo + plumbing + electrical | 16.3 | $22K/unit · SEER2 29.9 · 10-yr warranty
Finishes / millwork / appliances — all tiers | 17.04 | $23K/unit · mid-range Forward Home spec
E — SOFT COST RATES (CBai MEP SOP v1 disaggregated)
Typology toggle (1=First use · 2=Repeat/Claymont template) | 1 | 1 = first Forward Home engagement · 2 = Claymont template repeat (Q4 2026+)
A&E architectural fee (per unit, fixed) | 5500 | AOR + schematic + permit drawings · fixed regardless of typology
MEP PE fee — first typology (per unit) | 3200 | CBai-assisted target · full G0–G3 scope · M4Di CBai MEP Workflow SOP v1 Table 2
MEP PE fee — repeat/Claymont template (per unit) | 1800 | 40–50% of full-service · G3 stamp only · available Q4 2026 after Claymont G4 archive
Permits / filing / AHJ fees (per unit) | 1800 | City of Wilmington residential permit · fixed
M4Di OI Tool / ALDi Tracker (per unit) | 1200 | G0 ROM + ALDi gate tracking G1–G4 · OED cost-verification standard
SOFT COSTS / UNIT (base, active typology) | 11700 | Active total · First: ~$11,700 · Repeat/Claymont: ~$10,300
F — REVENUE (feeds BID SUMMARY / TOTAL PROJECT BUDGET)
Sale price / unit — T1 Code+ | 235000 | City target $220K–$250K · Type D cluster achieves higher end
Sale price / unit — T2 Zero | 250000 | Net premium ~$12K–$18K over T1 · DOE ZERH certified
Sale price / unit — T3 Positive | 265000 | Net premium ~$28K–$42K · PHIUS+ certified
Sale price / unit — T4 Harvest | 290000 | Net premium ~$52K–$72K · off-grid agrivoltaic
Monthly rent / unit (rental hold) | 1550 | Wilmington forward housing market rate · affordable range
Stabilized expense ratio | 45% | NOI = 55% of gross annual income
Capitalization rate (valuation) | 6.2% | Delaware multifamily Q1 2026 estimate
G — QUICK REFERENCE (auto-calculated from BID SUMMARY)
Base hard cost subtotal (pre-markup) | 200
GC + OH&P + contingency | 3500
Total Project ROM (hard cost) | #VALUE!
Total Soft Costs | 0
TOTAL PROJECT INVESTMENT | #VALUE!
COLOR CODE: Dark navy text + pale yellow bg = input · Dark green text + pale green bg = formula · Gray italic = note / source · Soft cost typology toggle: C=1 (first) or C=2 (Claymont repeat)

## BID SUMMARY
ROM COST ESTIMATE — FORWARD HOME PROGRAM · FOUR-TIER SUMMARY
Forward Home — Type D 10-Unit Cluster ¦ May 2026
Summary Item | T1 Code+ | T2 Zero | T3 Positive | T4 Harvest | Notes / Basis
SECTION 1 — HARD COSTS (Pre-Markup Subtotal by CSI Division)
DIV 01 — General Requirements / GC Conditions | #VALUE! | #VALUE! | #VALUE! | #VALUE! | On-site supervision, temp facilities, site logistics per ALDi standard rates
DIV 02 — Existing Conditions / Demolition | #VALUE! | #VALUE! | #VALUE! | #VALUE! | New construction = $0 demo. Allowance for minor site clearing.
DIV 03 — Concrete (foundation, slab, CMU party wall) | 200 | 200 | 200 | 200 | T1: CMU+slab. T2–T4: Superior Walls Xi Plus + slab.
DIV 04 — Masonry (CMU party wall complement) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 8″ CMU party wall continuous foundation to underside of roof deck. All tiers.
DIV 05 — Metals (structural, misc) | #VALUE! | #VALUE! | #VALUE! | #VALUE!
DIV 06 — Wood / CLT Structural Spine + Framing | 3500 | 3500 | 3500 | 3500 | T1–T2: 2×6 SPF-S light frame. T3–T4: TerraLam TL500S CLT ESR-5053 where specified.
DIV 07 — 4Ward-SIB Panel + Thermal/Moisture Protection | #VALUE! | #VALUE! | — | — | Barricade Thermo-Brace SIB TER 1507-09. Includes WRB, R-5 CI, air barrier. T3-4 adds Intello+.
DIV 08 — Openings (windows, doors) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | T1-2: Crystal Magnus 4500 tilt-turn U≤0.20. T3-4: Magnus 4700 PH U≤0.14.
DIV 09 — Finishes (GWB, flooring, paint, tile) | 400 | — | — | — | Interior finishes · mid-range Forward Home spec
DIV 10 — Specialties (cladding, accessories) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Allura fiber cement cladding. T1: Lap. T2-3: Panel. T3-4: Panel+Shakes. 50-yr warranty.
DIV 11 — Equipment (appliances, kitchen, specialty) | 1200 | 1200 | 1200 | 1200 | T4: Crop Circle Farms rooftop system. NatureMill composter.
DIV 12 — Furnishings (FF&E allowance) | 4500 | 4500 | 5000 | 5000
DIV 14 — Conveying (elevator — if applicable) | 0 | 0 | 0 | 0 | Type D pilot: 2-story — no elevator. Allow for 3+ story future configurations.
DIV 21 — Fire Suppression (NFPA 13R residential) | 2100 | 2100 | 2800 | 2800 | NFPA 13R townhouse sprinkler system.
DIV 22 — Plumbing (DWV, domestic water, fixtures) | — | — | — | — | T4: includes cistern plumbing, gravity-fed drip irrigation.
DIV 23 — HVAC / Mechanical | 0 | 0 | 0 | 0 | T1: std mini-split. T2: Quilt 3-zone + ERV. T3: Mitsubishi FX H2i sumo. T4: Quilt battery-opt.
DIV 26 — Electrical (service, panels, wiring, lighting) | — | — | — | 4000 | T2-4: SPAN MAIN 40 UL 3141. T4: island-mode configured.
DIV 26E — PV + Battery Storage (energy systems) | 500 | 500 | 500 | 500 | T1: stub only. T2: 5.5kW+Enphase IQ5P. T3: 8.5kW+Powerwall 3. T4: Agrivoltaic+EcoFlow/FranklinWH.
DIV 27/28 — Communications + Security | — | 4000 | 4000 | 4000
DIV 32/33 — Site Work + Landscaping + Rooftop | #VALUE! | #VALUE! | #VALUE! | #VALUE! | T2: LiveRoof Standard. T3: LiveRoof MAXX+edible rows. T4: Crop Circle Farms agrivoltaic trellis.
BASE BUILDING SUBTOTAL (pre-markup, all CSI divisions) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Sum of all CSI division line items. Pre-GC, pre-OH&P, pre-contingency.
SECTION 2 — MARKUPS & CONTINGENCIES
General Conditions (GC overhead) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Rate: ASSUMPTIONS!C24 (8%). On-site supervision, temp facilities.
Overhead & Profit (OH&P) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Rate: ASSUMPTIONS!C25
Total Contingencies (design + existing + owner selection) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | ROM: Design 12% + Existing 0% + Owner 5% = 17%
Bid / Permit / Bonds | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2% covers permitting, bid bonds, performance bonds.
TOTAL PROJECT ROM (hard costs only) | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Hard cost only. Soft costs, owner contingency in TOTAL PROJECT BUDGET.
Project Cost per SF (hard ROM) | 0 | 0 | 0 | 0 | $/SF per unit. Compare to SF BENCHMARK for reasonableness check.
SECTION 3 — SOFT COSTS + TOTAL (from SOFT COSTS sheet)
Architecture Fee (from SOFT COSTS) | 0 | 0 | 0 | 0 | M4Di fee schedule · Type A residential · % of hard cost ROM
Total Engineering Fees | 0 | 0 | 0 | 0 | Structural + MEP PE (CBai-assisted) + FP + civil
Other Consultants & Owner Costs | 0 | 0 | 0 | 0 | Permits, M4Di OI, testing, legal, insurance
TOTAL SOFT COSTS | 0 | 0 | 0 | 0 | See SOFT COSTS sheet for full detail.
Owner Contingency (post-GMP reserve) | 0 | 0 | 0 | 0 | 5% owner contingency on hard costs
TOTAL PROJECT INVESTMENT | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Hard + Soft + Owner contingency. Full project cost.

## HARD COST TAKEOFF
M4Di ¦ Forward Home Program — Hard Cost Takeoff by CSI Division
Forward Home — Type D 10-Unit Cluster
Budget Item / Scope | CSI / Ref | T1 Code+ ROM (LOCKED) | T2 Zero ROM (LOCKED) | T3 Positive ROM (LOCKED) | T4 Harvest ROM (LOCKED) | ROM vs. DD Variance | GC Quote | Notes / Source
SECTION 1 — HARD COSTS (Construction) · Per-Unit ROM Values
1A — DIV 01 General Requirements / GC Conditions | DIV 00/01
General Conditions (GC time, overhead) | DIV 00/01 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | 8% of base building subtotal at each tier. See ASSUMPTIONS GC rate.
Temporary facilities, utilities, hoarding | DIV 01-TF | 2500 | 2500 | 2500 | 2500 | — |  | Allowance per unit — 10-unit cluster
Site safety, security & signage | DIV 01-SS | 800 | 800 | 800 | 800 | — |  | Allowance per unit
GC fee / OH&P | DIV 00-OH | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | 10% of base subtotal. See ASSUMPTIONS OH&P rate.
DIV 01 SUBTOTAL | DIV 01 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1B — DIV 02 Existing Conditions / Demolition | DIV 02
Selective demolition — interior | DIV 02-DI | — | — | — | — | — |  | New construction. $0. Allowance only if renovating an existing unit.
Site clearing / minor demolition | DIV 02-SC | 500 | 500 | 500 | 500 | — |  | Allowance per unit — lot clearing, minor grading
Hazardous materials survey (Phase I allowance) | DIV 02-HT | 250 | 250 | 250 | 250 | — |  | Allowance per lot — Phase I required for City program parcels
DIV 02 SUBTOTAL | DIV 02 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1C — DIV 03 Concrete (foundation, slab, CMU party wall base) | DIV 03
Cast-in-place slab-on-grade (4" with R-10 under) | DIV 03-CF | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $6.50/SF floor area · includes sub-slab EPS R-10 · all tiers
Foundation — T1 CMU / poured (see also DIV 04) | DIV 03-CM | #VALUE! | — | — | — | — |  | T1: 55% of found. rate is concrete/forming. Remainder in DIV 04 CMU.
Foundation — T2–T4 Superior Walls Xi Plus | DIV 03-SW | — | #VALUE! | #VALUE! | #VALUE! | — |  | TER 2211-02 · 5,000 psi precast · built-in EPS+polyiso · Tiers 2–4
Concrete repair / patching (new const. allowance) | DIV 03-CR | 200 | 200 | 200 | 200 | — |  | Punch-list allowance per unit
DIV 03 SUBTOTAL | DIV 03 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1D — DIV 04 Masonry (8″ CMU party wall — ALL TIERS) | DIV 04
8" CMU party wall — continuous foundation to roof underside | DIV 04-NM | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | 8" CMU inherent 2-hr fire / STC≥50. All tiers. ~45% of foundation rate.
Thermafiber SafingFire mineral wool (firestop at CLT/CMU) | DIV 04-FS | 400 | 400 | 400 | 400 | — |  | Firestop joint detail at every CLT floor/CMU bearing intersection. All tiers.
Hilti FS-ONE MAX sealant at penetrations | DIV 04-HL | 150 | 150 | 150 | 150 | — |  | Both faces of CMU at all MEP penetrations.
DIV 04 SUBTOTAL | DIV 04 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1E — DIV 05 Metals (structural, misc, stairs) | DIV 05
Structural steel connections / lintels / angles | DIV 05-MM | 1200 | 1200 | 1800 | 1800 | — |  | Light residential — lintels, hold-downs, CMU bearing plates
Stairs — metal pan or open-riser steel | DIV 05-ST | 3500 | 3500 | 3500 | 3500 | — |  | 2-story unit: one stair per unit. Allowance.
Miscellaneous metals — railings, guards | DIV 05-RL | 1800 | 1800 | 1800 | 1800 | — |  | Guardrails, handrails per IBC. Allowance per unit.
DIV 05 SUBTOTAL | DIV 05 | 6500 | 6500 | 7100 | 7100
1F — DIV 06 Wood / CLT Structural Spine + Light Framing | DIV 06
Light-frame wall — 2×6 SPF-S @ 16″ OC (T1–T2) | DIV 06-LF | #VALUE! | #VALUE! | — | — | — |  | $4.50/SF floor area for 2×6 framing. T1–T2 light frame wall system.
CLT structural spine — TerraLam TL500S 5-ply ESR-5053 (T3–T4) | DIV 06-CLT | — | — | #VALUE! | #VALUE! | — |  | $9.80/SF · T3–T4 Type C/D CLT structural spine. ESR-5053. EOR required.
Floor framing — 2×10 SPF-S joists + ¾" T&G subfloor | DIV 06-FL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $5.20/SF floor area. All types (or CLT floor deck substitute at T3–T4).
Roof framing — stick rafters / pre-eng trusses @ 24" OC | DIV 06-RF | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | R-49 blown-in attic above. T2–T4: LiveRoof / agrivoltaic at roof plane.
Rough carpentry — blocking, nailers, backing | DIV 06-RC | 800 | 800 | 800 | 800 | — |  | Allowance per unit.
Finish carpentry / millwork / casework | DIV 06-FC | 4500 | 4500 | 4500 | 4500 | — |  | Kitchen cabinets, vanities, closets. All tiers.
DIV 06 SUBTOTAL | DIV 06 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1G — DIV 07 4Ward-SIB Panel + Thermal & Moisture Protection | DIV 07
4Ward-SIB Forward Panel — Barricade Thermo-Brace Blue SIB™ | DIV 07-SIB | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | TER 1507-09 · R-5 GPS CI + WRB + AIB integrated · 24″OC · 200mph Vult · all tiers
Cavity insulation — batt (T1 fiberglass / T2–T4 Rockwool Comfortbatt) | DIV 07-WI | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | R-23 cavity · T2–T4 mineral wool for fire/vapor performance
Attic insulation — R-49 blown-in fiberglass | DIV 07-AI | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | R-49 at attic floor plane · all tiers · blower door <2.0 ACH50 auto via SIP
Interior air barrier membrane — Pro Clima Intello+ (T3–T4) | DIV 07-AB | — | — | #VALUE! | #VALUE! | — |  | $1,800/unit at 1,350 SF · PHIUS+ compliant continuous air barrier · T3–T4 only
Roofing membrane — EPDM/TPO (T1 base) | DIV 07-RF | #VALUE! | #VALUE! | — | — | — |  | Standard flat/low-slope EPDM or TPO at T1–T2 (LiveRoof replaces at T2+)
Caulking, sealants, joint fillers | DIV 07-SL | 600 | 600 | 600 | 600 | — |  | Per unit allowance · all tiers
Waterproofing below grade / foundation dampproofing | DIV 07-WP | 400 | — | — | — | — |  | T1: slab edge dampproofing. T2–T4: Superior Walls eliminates.
DIV 07 SUBTOTAL | DIV 07 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1H — DIV 08 Openings (doors, windows, hardware) | DIV 08
Crystal Magnus 4500 tilt-turn windows — double-pane (T1–T2) | DIV 08-WN | 7800 | 9200 | — | — | — |  | U≤0.20 · PG70 · STC 41dB · HVHZ · per unit allowance T1 low / T2 high
Crystal Magnus 4700 PH windows — triple-pane (T3–T4) | DIV 08-WP | — | — | 13200 | 13200 | — |  | U≤0.14 · Passive House certified · REHAU RAU-FIPRO · per unit allowance
Hollow metal doors, frames & hardware — exterior | DIV 08-HM | 3200 | 3200 | 3200 | 3200 | — |  | Entry door + 1 rear door per unit. Allowance.
Interior doors — hollow core / solid core + hardware | DIV 08-ID | 2400 | 2400 | 2400 | 2400 | — |  | ~8 interior doors per unit. Mid-range allowance.
Accessible entry operators / ADA hardware | DIV 08-AE | 600 | 600 | 600 | 600 | — |  | Per unit allowance · all tiers
DIV 08 SUBTOTAL | DIV 08 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1I — DIV 09 Finishes (GWB, flooring, paint, tile) | DIV 09
Drywall — partitions, shafts, soffits | DIV 09-DW | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $5.20/SF floor area · standard residential framed partitions
Tile — ceramic/porcelain (bathrooms, kitchen) | DIV 09-TL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $2.80/SF floor area · blended bath + kitchen coverage
Flooring — LVT / hardwood / specialty | DIV 09-FL | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $3.50/SF T1–T2 LVT · $3.80/SF T3–T4 enhanced spec
Acoustical ceiling tile (ACT) / drywall ceiling | DIV 09-CT | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $1.80/SF · mix of ACT and painted drywall ceiling
Paint & wall coatings — interior | DIV 09-PI | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $1.50/SF T1–T2 · $1.80 T3–T4 higher-end spec
Specialty / acoustic wall finish allowance | DIV 09-WC | — | 500 | 500 | 500 | — |  | T2–T4 acoustic enhancement allowance per unit
DIV 09 SUBTOTAL | DIV 09 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1J — DIV 10 Specialties (Allura cladding, accessories) | DIV 10
Allura Lap siding — T1 base cladding | DIV 10-CL | 8450 | — | — | — | — |  | 7" exposure · factory primed · 50-yr warranty · 1" ventilated rainscreen on SIB
Allura Panel + Shakes + Soffit — T2–T4 upgrade | DIV 10-CP | — | 9650 | 11050 | 11050 | — |  | Allura Panel primary + Shakes accent + Soffit · Spectrum pre-finished · no field paint
Allura Trim (all openings, corners) — all tiers | DIV 10-CT | 1200 | 1200 | 1200 | 1200 | — |  | All window/door trim, corner boards, band boards. All tiers.
Fire extinguishers & cabinets | DIV 10-FE | 300 | 300 | 300 | 300 | — |  | Code-required per unit. Allowance.
Toilet partitions & bath accessories | DIV 10-TP | 800 | 800 | 800 | 800 | — |  | Grab bars, mirrors, TP holders per unit.
Signage — code-required (egress / unit ID) | DIV 10-SG | 250 | 250 | 250 | 250 | — |  | Per unit allowance
DIV 10 SUBTOTAL | DIV 10 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1K — DIV 11 Equipment (appliances, specialty, rooftop systems) | DIV 11
Kitchen appliances — refrigerator, range, DW, microwave | DIV 11-KIT | 4500 | 4500 | 5000 | 5000 | — |  | Mid-range residential appliance package. All tiers.
HPWH — heat pump water heater (all tiers) | DIV 11-WH | 2100 | 2100 | 2100 | 2100 | — |  | UEF ≥3.5 · all tiers · AO Smith / Rheem 50-gal residential
Drainwater heat recovery (T2–T4) | DIV 11-DHR | — | 750 | 750 | 750 | — |  | Shower stack heat recovery. T2–T4.
NatureMill indoor composter (T4 only) | DIV 11-NM | — | — | — | 1000 | — |  | 5W draw · 2-week cycle · feeds rooftop growing medium
Crop Circle Farms® modular rooftop system (T4) | DIV 11-CC | — | — | — | 10000 | — |  | Patented · 40+ country trademark · 200–600 lbs/yr yield per unit
DIV 11 SUBTOTAL | DIV 11 | #VALUE! | #VALUE! | #VALUE! | 18850
1L — DIV 12 Furnishings (FF&E, window treatments) | DIV 12
FF&E — fixed furnishings allowance | DIV 12-FF | 1500 | 1500 | 2000 | 2000 | — |  | Built-in shelving, closet systems, mirror. Allowance per unit.
Window treatments — blinds / shades | DIV 12-WT | 600 | 600 | 800 | 800 | — |  | Per unit allowance — all tiers
DIV 12 SUBTOTAL | DIV 12 | 2100 | 2100 | 2800 | 2800
1N — DIV 14 Conveying Equipment | DIV 14
Elevator — shaft provisions only (2-story: $0) | DIV 14-SP | — | — | — | — | — |  | Type D pilot = 2 stories: no elevator. Allowance for 3+ story future config.
DIV 14 SUBTOTAL | DIV 14 | — | — | — | —
1O — DIV 21 Fire Suppression (NFPA 13R residential) | DIV 21
Sprinkler system — NFPA 13R (residential townhouse) | DIV 21-SR | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $4.20/SF · NFPA 13R residential. AHJ may require NFPA 13 — verify City of Wilmington.
Standpipe / fire pump (if required by AHJ) | DIV 21-FP | — | — | — | — | — |  | 2-story: not typically required. Confirm with Wilmington Fire.
DIV 21 SUBTOTAL | DIV 21 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1P — DIV 22 Plumbing (DWV, domestic water, fixtures, cistern) | DIV 22
Plumbing — sanitary DWV (drain/waste/vent) | DIV 22-DWV | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $3.80/SF · residential townhouse · 2 bathrooms + kitchen per unit
Plumbing — domestic water supply (hot/cold) | DIV 22-DW | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $2.40/SF · copper or PEX supply + distribution
Plumbing fixtures & trim (toilets, sinks, tubs/showers) | DIV 22-FX | 3800 | 3800 | 4500 | 4500 | — |  | 2 baths + kitchen · T3–T4 higher-end fixtures
Gas rough-in & distribution (if gas — else $0) | DIV 22-GS | — | — | — | — | — |  | All-electric spec — no gas. $0 all tiers.
Roof drainage / interior leaders | DIV 22-RD | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $1.20/SF · interior roof leaders + overflow drains
500-gal cistern + gravity-fed drip irrigation (T4) | DIV 22-CI | — | — | — | 4000 | — |  | Closed water loop: roof collection → cistern → Rain Bird XFS-CV drip → crops → compost
DIV 22 SUBTOTAL | DIV 22 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1Q — DIV 23 HVAC / Mechanical | DIV 23
HVAC — T1 standard cold-climate mini-split (≥SEER2 18) | DIV 23-MS | #VALUE! | — | — | — | — |  | Blended installed rate per ASSUMPTIONS MEP T1 rate. Ductless.
HVAC — T2 Quilt 3-zone (SEER2 25.3 / HSPF2 12) | DIV 23-QT | — | #VALUE! | — | #VALUE! | — |  | Quilt 3-zone · OTA firmware · 7⅞" indoor unit · occupancy sensing · T2 and T4 battery-opt.
HVAC — T3 Mitsubishi FX-Series H2i sumo (SEER2 29.9) | DIV 23-MF | — | — | #VALUE! | — | — |  | 10-yr warranty · R454B · 100% capacity @ 5°F · Diamond Contractor required
Viessmann Vitoair ERV — 85% SRE / MERV 13 (T2–T4) | DIV 23-ERV | — | 2700 | 2700 | 2700 | — |  | CO₂-responsive · ASHRAE 62.2+25% · T2–T4
Ductwork / distribution (mini-split: minimal) | DIV 23-DK | 500 | 500 | 500 | 500 | — |  | Minimal for ductless systems — supply/return stubs only per unit
Exhaust — bathrooms, kitchen, laundry | DIV 23-EX | 800 | 800 | 800 | 800 | — |  | Per unit allowance · all tiers · inline bath fans + range hood
Building automation / smart thermostat integration | DIV 23-BAS | 400 | 600 | 600 | 600 | — |  | T1: standard programmable. T2–T4: Quilt/Mitsubishi app + occupancy sensors.
DIV 23 SUBTOTAL | DIV 23 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1R — DIV 26 Electrical (service, wiring, lighting, panels) | DIV 26
Electrical service & switchgear — standard 200A (T1) | DIV 26-SV | 3200 | — | — | — | — |  | 200A residential panel · utility-ready · EV + PV stub-outs included
SPAN MAIN 40 smart panel (T2–T4) — UL 3141 certified | DIV 26-SP | — | 4000 | 4000 | 4000 | — |  | First UL 3141 certified smart panel · 32 individually controllable circuits · Eaton-backed
Branch wiring — power & circuits | DIV 26-BW | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $4.80/SF · residential townhouse · copper NM or MC cable
Lighting fixtures — interior LED | DIV 26-LI | #VALUE! | #VALUE! | #VALUE! | #VALUE! | — |  | $2.20/SF T1–T2 · $2.40 T3–T4 enhanced spec fixtures
Lighting — exterior / entry | DIV 26-LE | 600 | 600 | 600 | 600 | — |  | Allowance per unit · code-required exterior lighting
Emergency / exit lighting | DIV 26-EM | 400 | 400 | 400 | 400 | — |  | Per unit allowance · battery-backup exit signs + emergency egress
EV charging stub (conduit + circuit — not charger) | DIV 26-EV | 350 | 350 | 350 | 350 | — |  | NEMA 14-50 circuit stub at parking or garage. Future EV-ready.
DIV 26 SUBTOTAL | DIV 26 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1R-E — DIV 26E PV Solar + Battery Storage (energy systems) | DIV 26E
PV stub-out only — T1 (conduit, inverter space, utility notice) | DIV 26E-S1 | 1200 | — | — | — | — |  | T1: future-ready stub only. No panels or inverter.
PV 5.5 kW — T2 (Enphase IQ8 microinverters) | DIV 26E-P2 | — | 17250 | — | — | — |  | Mid of $15K–$19.5K range · Mono PERC or TOPCon · utility interconnect + net metering
PV 8.5 kW — T3 (high-efficiency TOPCon/HJT ≥22%) | DIV 26E-P3 | — | — | 25750 | — | — |  | $25.75K · Enphase IQ8 · high efficiency panels · PV export to grid
PV 8.5–12 kW agrivoltaic trellis — T4 bifacial TOPCon | DIV 26E-P4 | — | — | — | 28250 | — |  | Elevated 5–6 ft on galvanized trellis · E/W orientation over Crop Circle beds
Battery — Enphase IQ Battery 5P or Tesla Powerwall 3 (T2–T3) | DIV 26E-B23 | — | 11500 | 11500 | — | — |  | T2: Enphase IQ5P stackable 15-yr OR Powerwall 3 13.5 kWh built-in inverter
Battery — EcoFlow DELTA Pro Ultra + FranklinWH aPower 2 (T4) | DIV 26E-B4 | — | — | — | 18000 | — |  | 19.2–90 kWh · true off-grid island mode · 7.2kW continuous · generator compatible
DIV 26E SUBTOTAL | DIV 26E | #VALUE! | #VALUE! | #VALUE! | #VALUE!
1S — DIV 27/28 Communications, Security & Low Voltage | DIV 27/28
Data / network infrastructure (Cat6 + WiFi stub) | DIV 27-DA | 800 | 800 | 800 | 800 | — |  | Per unit allowance · residential rough-in
Security — access control + camera stub | DIV 28-AC | 400 | 600 | 600 | 600 | — |  | T1: allowance stub. T2–T4: enhanced smart home integration ready.
Fire alarm / smoke detection (interconnected) | DIV 28-FA | 500 | 500 | 500 | 500 | — |  | Hardwired interconnected smoke + CO detectors. Per unit. Code required.
DIV 27/28 SUBTOTAL | DIV 27/28 | 1700 | 1900 | 1900 | 1900
1T — DIV 32/33 Site Work + Landscaping + Rooftop Systems | DIV 32/33
Site work (City-covered: grading, utilities, paving) | DIV 32-SW | — | — | — | — | — |  | City of Wilmington program: site work + utilities = $0 developer cost
Landscaping / planting / entry hardscape allowance | DIV 32-LS | 1500 | 1500 | 1500 | 1500 | — |  | Per unit entry + foundation planting allowance
Rooftop — standard EPDM/TPO membrane (T1 — in DIV 07) | DIV 32-RT | — | — | — | — | — |  | T1: included in DIV 07 roofing membrane line. $0 here.
LiveRoof® Standard (700 SF) — T2 | DIV 32-LR2 | — | 7350 | — | — | — |  | 4.25" soil · FM 4477 · ASTM E108 Class A · 200 PSF wind · sedum mat
LiveRoof® MAXX + edible rows (Up Top Acres) — T3 | DIV 32-LR3 | — | — | 14000 | — | — |  | 8" soil · RoofBlue riser · productive planting rows (lettuce/herbs/tomatoes/kale) · drip irr.
Agrivoltaic trellis + Crop Circle Farms rooftop (T4) | DIV 32-AGR | — | — | — | 14000 | — |  | Galvanized trellis 5–6 ft elevated · bifacial PV above Crop Circle beds · 200–600 lbs/yr yield
Cistern + subsurface drip (T3 stub / T4 full) | DIV 32-CI | — | — | 1600 | — | — |  | T3: drip stub-out + soil moisture sensor. T4: full cistern in DIV 22.
DIV 32/33 SUBTOTAL | DIV 32/33 | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TOTAL HARD COST — ALL CSI DIVISIONS (pre-GC, pre-OH&P, pre-contingency) · Per Unit
TOTAL HARD COST / UNIT (base building — pre-markup) | ALL DIV | #VALUE! | #VALUE! | #VALUE! | #VALUE!
TOTAL HARD COST — ALL UNITS (÷ Tier) |  | #VALUE! | #VALUE! | #VALUE! | #VALUE!

## SOFT COSTS
SOFT COSTS — Professional Fees & Pre-Construction Costs
Forward Home Program · Soft costs per M4Di fee schedule + CBai MEP SOP v1
A — PROJECT BASIS (from ASSUMPTIONS & BID SUMMARY)
Discipline / Fee Item | % of Hard Cost (calc or input) | Calculated Fee ($) | User Override ($ if fixed) | Fee Used | Source / Notes
Total Hard Cost ROM | #VALUE! |  |  |  | Pulled from BID SUMMARY. This is the construction ROM driving all % fees.
Project Type (for fee schedule) | New Construction — Residential |  |  |  | From ASSUMPTIONS. Drives M4Di fee schedule lookup.
Gross Area — per unit (SF) | City of Wilmington Vacant Lot Cluster, Wilmington DE 19801 |  |  |  | Unit SF from ASSUMPTIONS.
B — M4Di FEE SCHEDULE REFERENCE (Type A–E · Residential = Type A)
C — FEE INPUTS & CALCULATIONS
AIA Project Type Code (A=residential · C=fitness/school · etc.) | A |  |  |  | A=warehouse/residential, B=office/retail, C=school/fitness, D=library/restaurant, E=hospital/research
New Construction (vs. Renovation)? | New Construction |  |  |  | New Construction = no renovation premium. Renovation/adaptive reuse adds 0.5%–1.0% to arch fee.
ARCHITECTURE & ENGINEERING FEES
Architecture — Base Fee (M4Di fee schedule Type A) | 7.4% | #VALUE! |  | #VALUE! | Type A residential, ~$1.4M hard cost ROM = 7.4%. Override with actual contract.
+ Renovation Premium (N/A — new construction) | 0% | #VALUE! |  | #VALUE! | New construction = $0 renovation premium.
Architecture — TOTAL FEE |  |  |  | 0
ENGINEERING DISCIPLINES
Structural Engineering | 1.5% | #VALUE! |  | #VALUE! | Typical 1.0%–2.0%. EOR required for CLT/CMU party wall system.
Mechanical Engineering (HVAC — CBai-assisted) | 0.9% | #VALUE! |  | #VALUE! | CBai-assisted target: $3,200/unit first typology = ~0.9% at T1 ROM. SOP v1.
Electrical Engineering | 1.2% | #VALUE! |  | #VALUE! | Typical 1.0%–2.0%. SPAN MAIN 40 + PV + battery adds scope at T2–T4.
Plumbing Engineering | 0.8% | #VALUE! |  | #VALUE! | 0.8%–1.5%. T4: cistern plumbing + drip system adds ~$3,200/unit PE premium.
Fire Protection Engineering | 0.6% | #VALUE! |  | #VALUE! | 0.5%–1.0%. NFPA 13R residential sprinkler system.
Civil Engineering | 0.8% | #VALUE! |  | #VALUE! | 0.8%–2.0%. Minimal — City covers site work/utilities. Grading plan only.
Geotechnical / Soils Report | 0.4% | #VALUE! |  | #VALUE! | 0.3%–0.8% or fixed. Required for Superior Walls Xi Plus seismic confirmation.
Landscape Architecture | 0.3% | #VALUE! |  | #VALUE! | 0.3%–0.8%. Entry + foundation planting plan.
ADA / Accessibility Consultant | 0.3% | #VALUE! |  | #VALUE! | 0.3%–0.5%. Required for City program ADA compliance documentation.
HERS Rater / DOE ZERH (T2) | 0% | #VALUE! |  | #VALUE! | $2,000 fixed at T2. Override with actual.
PHIUS Rater + Commissioning (T3–T4) | 0% | #VALUE! |  | #VALUE! | $4,250–$7,500 fixed at T3–T4. Override with actual.
Engineering Subtotal (all disciplines) |  |  |  | #VALUE!
SPECIALTY CONSULTANTS & OWNER COSTS
M4Di OI Tool / ALDi Tracker (this engagement) | 0% | #VALUE! |  | #VALUE! | $1,200/unit = $12,000 for 10 units. Override with actual contract.
Permitting / Plan Review Fees | 1.5% | #VALUE! |  | #VALUE! | ~1.5% typical City of Wilmington residential. $1,800/unit fixed preferred.
Builder's Risk Insurance | 0.8% | #VALUE! |  | #VALUE! | 0.5%–1.5% of total project cost. Override with actual premium quote.
Testing / Special Inspections | 0.4% | #VALUE! |  | #VALUE! | IBC-required. Concrete, CLT bearing, blower door (T2–T4), PHIUS (T3–T4).
Legal / Title / Closing | 0.3% | #VALUE! |  | #VALUE! | Property matters, contract review. Allowance.
Financing / Loan Origination (CDFI) | 1% | #VALUE! |  | #VALUE! | 0.5%–1.5% of construction loan. Delaware market estimate.
IRA §45L Developer Credit (T2–T4) — OFFSET | 0% | #VALUE! |  | #VALUE! | $5,000/unit credit at T2–T4. Reduces net soft cost. Enter as negative override.
Other Consultants & Owner Costs Subtotal |  |  |  | #VALUE!
TOTAL SOFT COSTS |  |  |  | #VALUE!
Soft costs benchmarks: 18%–25% of hard cost ROM is typical for community facility renovation. New residential = 10%–15% of hard cost. CBai MEP SOP v1 reduces PE fees 30%–40% vs. full-service. Toggle ASSUMPTIONS typology to model Claymont repeat savings.

## TOTAL PROJECT BUDGET
TOTAL PROJECT BUDGET — Hard Costs + Soft Costs + Owner Contingency
Forward Home — Type D 10-Unit Cluster ¦ ROM Date: May 2026
Budget Item | Amount ($) | % of Hard Cost | % of Total | Notes
SECTION 1 — HARD COSTS (Construction)
Base Building Subtotal (all CSI divisions) | 200 | 0% | 0% | Quantity-based takeoff from HARD COST TAKEOFF sheet.
General Conditions | #VALUE! | 0% | 0% | On-site supervision, temp facilities, insurance.
Overhead & Profit (OH&P) | #VALUE! | 0% | 0%
Total Contingencies | 3500 | 0% | 0% | Design 12% + Existing 0% + Owner Selection 5% = 17% ROM
Bid / Permit / Bonds | #VALUE! | 0% | 0%
TOTAL HARD COST (Construction ROM) | #VALUE! | 100% | 0%
SECTION 2 — SOFT COSTS (Professional Fees)
Architecture — Total Fee (base + renovation premium) | 0 | 0% | 0% | Base fee per M4Di fee schedule Type A residential.
Structural Engineering | 0 | 0% | 0%
MEP Engineering (Mech+Elec+Plumbing+FP — CBai-assisted) | 0 | 0% | 0% | CBai MEP SOP v1 — 30%–40% below full-service PE fees
Civil + Geotechnical | 0 | 0% | 0%
Other Consultants & Owner Costs | 0 | 0% | 0% | M4Di OI, permits, insurance, testing, legal, financing.
TOTAL SOFT COSTS | 0 | 0% | 0%
SECTION 3 — OWNER CONTINGENCY & DIRECT COSTS
Owner Project Contingency (post-GMP reserve) | 0 | 5% | 0% | 5% owner contingency on hard costs. Held by owner post-GMP.
City Land + Site/Infrastructure (City-funded) | 0 | 0% | 0% | $0 developer cost. City of Wilmington vacant lot program — land at $1/lot, utilities covered.
Predevelopment Costs (M4Di P1–P3 fees — already incurred) | 0 | 0% |  | M4Di predevelopment fees are separate contracts per engagement. Enter actual when known.
IRA §45L Developer Credit (T2–T4) — enter as negative | 0 | 0% |  | –$5,000/unit at T2–T4 DOE ZERH. Enter as negative value to reduce net owner cost.
TOTAL OWNER CONTINGENCY & OTHER | #VALUE! | 0% | 0%
TOTAL PROJECT INVESTMENT | 0
SUMMARY METRICS
Total Project Investment | #VALUE!
Hard Cost ROM | #VALUE!
Total Soft Costs | 0
Soft Costs as % of Hard Costs | 0%
Total Project Cost / SF (all units) | 0
Hard Cost / SF | #VALUE!

## ALDi BUDGET TRACKER
M4Di ¦ ALDi Design & Construction Budget Tracker
· M4Di ALDi Controls · G0 ROM Baseline
Budget Item | CSI / Ref | M4Di ROM (LOCKED BASELINE) | 75% DD ESTIMATE (Gate 2) | 100% CD / SOV (Gate 3 — Contracted) | ACTUAL COST (Running Total) | ROM vs. DD Variance | GC QUOTE / PROPOSAL (Pre-SOV) | GC ACTUALS (Running Total) | ROM vs. GC Variance | CD vs. Actual Variance | % Var | Notes / Status
► Col D: M4Di ROM (locked Gate 0) ► Col E: Enter at Gate 2 (75% DD) ► Col F: Enter at Gate 3 (GMP/SOV) ► Col G: Update monthly during construction ► Cols I–J: GC direct quote + actuals
SECTION 1 — HARD COSTS (Construction) · ROM = T1 Code+ per unit (update for selected tier)
1A — DIV 01 General Requirements
General Conditions (GC time, overhead) | DIV 00/01 | [8 empty] | 0 | - | 8% of base building subtotal
Temporary Facilities, Utilities & Hoarding | DIV 01-TF | [8 empty] | 0 | - | Per unit allowance
Site Safety, Security & Signage | DIV 01-SS | [8 empty] | 0 | - | Per unit allowance
GC Fee / Overhead & Profit | DIV 00-OH | [8 empty] | 0 | - | 10% of subtotal per ASSUMPTIONS
1A SUBTOTAL — General Requirements | DIV 01 | 0 | 0 | 0 | 0
1B — DIV 02 Existing Conditions
Selective Demolition — Interior | DIV 02-DI | [8 empty] | 0 | - | New const = $0. Renovation allowance.
Site Clearing / Minor Demolition | DIV 02-SC | [8 empty] | 0 | - | Lot clearing allowance per unit
Hazardous Materials Survey (Phase I) | DIV 02-HT | [8 empty] | 0 | - | Required for City program parcels
1B SUBTOTAL | DIV 02 | 0 | 0 | 0 | 0
1C — DIV 03 Concrete
Cast-in-Place Slab-on-Grade (4" + R-10 EPS under) | DIV 03-CF | [8 empty] | 0 | - | $6.50/SF floor area
Foundation — T1 CMU/poured OR T2–T4 Superior Walls | DIV 03-CM/SW | [8 empty] | 0 | - | See ASSUMPTIONS for tier rate
Concrete Repair / Patching (allowance) | DIV 03-CR | [8 empty] | 0 | - | Punch-list allowance
1C SUBTOTAL | DIV 03 | 0 | 0 | 0 | 0
1D — DIV 04 Masonry (8" CMU party wall — ALL TIERS)
8" CMU party wall — foundation to underside of roof deck | DIV 04-NM | [8 empty] | 0 | - | ALL TIERS. 2-hr fire + STC≥50 inherent. Continuous per IRC R302.2.
Thermafiber SafingFire mineral wool (firestop at CLT/CMU intersections) | DIV 04-FS | [8 empty] | 0 | - | All levels · CLT floor/CMU bearing joint
Hilti FS-ONE MAX sealant at MEP penetrations | DIV 04-HL | [8 empty] | 0 | - | Both CMU faces
1D SUBTOTAL | DIV 04 | 0 | 0 | 0 | 0
1E — DIV 05 Metals
Structural Steel Connections / Lintels / Angles | DIV 05-MM | [8 empty] | 0 | - | Allowance per unit
Stairs — Metal Pan or Open-Riser | DIV 05-ST | [8 empty] | 0 | - | One stair per unit allowance
Miscellaneous Metals — Railings, Guards | DIV 05-RL | [8 empty] | 0 | - | IBC code-required allowance
1E SUBTOTAL | DIV 05 | 0 | 0 | 0 | 0
1F — DIV 06 Wood / CLT Structural Spine + Framing
Light Frame — 2×6 SPF-S @ 16" OC (T1–T2) | DIV 06-LF | [8 empty] | 0 | - | $4.50/SF T1–T2
CLT Structural Spine — TerraLam TL500S 5-ply ESR-5053 (T3–T4) | DIV 06-CLT | [8 empty] | 0 | - | $9.80/SF T3–T4. EOR required.
Floor Framing — 2×10 SPF-S + ¾" T&G Subfloor | DIV 06-FL | [8 empty] | 0 | - | $5.20/SF all types
Roof Framing — Stick Rafters / Pre-Eng Trusses @ 24" OC | DIV 06-RF | [8 empty] | 0 | - | $4.80/SF · R-49 blown attic above
Rough Carpentry — Blocking, Nailers, Backing | DIV 06-RC | [8 empty] | 0 | - | Allowance per unit
Finish Carpentry / Millwork / Casework | DIV 06-FC | [8 empty] | 0 | - | Kitchens, vanities, closets. All tiers.
1F SUBTOTAL | DIV 06 | 0 | 0 | 0 | 0
1G — DIV 07 4Ward-SIB Panel + Thermal & Moisture
4Ward-SIB Forward Panel — Barricade Thermo-Brace Blue SIB™ | DIV 07-SIB | [8 empty] | 0 | - | TER 1507-09 · R-5 CI + WRB + AIB integrated · all tiers · $31.11/SF
Cavity Insulation — Fiberglass (T1) / Rockwool Comfortbatt (T2–T4) | DIV 07-WI | [8 empty] | 0 | - | R-23 cavity · mineral wool T2–T4
Attic Insulation — R-49 Blown-In Fiberglass | DIV 07-AI | [8 empty] | 0 | - | $3.20/SF · all tiers
Interior Air Barrier — Pro Clima Intello+ (T3–T4) | DIV 07-AB | [8 empty] | 0 | - | $1,800/unit · PHIUS+ compliant · T3–T4
Roofing Membrane — EPDM/TPO Base (T1) | DIV 07-RF | [8 empty] | 0 | - | T1 standard flat roof. T2+: LiveRoof replaces.
Caulking, Sealants & Joint Fillers | DIV 07-SL | [8 empty] | 0 | - | Per unit allowance
Waterproofing / Foundation Dampproofing (T1 only) | DIV 07-WP | [8 empty] | 0 | - | T1: slab edge. T2–T4: Superior Walls eliminates.
1G SUBTOTAL | DIV 07 | 0 | 0 | 0 | 0
1H — DIV 08 Openings (windows, doors, hardware)
Crystal Magnus 4500 Tilt-Turn Windows — Double-Pane (T1–T2) | DIV 08-WN | [8 empty] | 0 | - | U≤0.20 · PG70 · STC 41dB · HVHZ approved
Crystal Magnus 4700 PH Windows — Triple-Pane (T3–T4) | DIV 08-WP | [8 empty] | 0 | - | U≤0.14 · Passive House certified · T3–T4
Hollow Metal Doors, Frames & Hardware — Exterior | DIV 08-HM | [8 empty] | 0 | - | Entry + rear door per unit
Interior Doors — Hollow/Solid Core + Hardware | DIV 08-ID | [8 empty] | 0 | - | ~8 doors per unit allowance
Accessible Entry Operators / ADA Hardware | DIV 08-AE | [8 empty] | 0 | - | Per unit allowance
1H SUBTOTAL | DIV 08 | 0 | 0 | 0 | 0
1I — DIV 09 Finishes
Drywall — Partitions, Shafts & Soffits | DIV 09-DW | [8 empty] | 0 | - | $5.20/SF
Tile — Ceramic/Porcelain (Bathrooms, Kitchen) | DIV 09-TL | [8 empty] | 0 | - | $2.80/SF
Flooring — LVT / Hardwood / Specialty | DIV 09-FL | [8 empty] | 0 | - | $3.50/SF T1–T2 · $3.80/SF T3–T4
Acoustical Ceiling Tile (ACT) / Drywall Ceiling | DIV 09-CT | [8 empty] | 0 | - | $1.80/SF
Paint & Wall Coatings — Interior | DIV 09-PI | [8 empty] | 0 | - | $1.50/SF T1–T2 · $1.80/SF T3–T4
Specialty / Acoustic Wall Finish Allowance | DIV 09-WC | [8 empty] | 0 | - | $0 T1 · $500/unit T2–T4
1I SUBTOTAL | DIV 09 | 0 | 0 | 0 | 0
1J — DIV 10 Specialties (Allura cladding, accessories)
Allura Lap Siding — T1 base cladding | DIV 10-CL | [8 empty] | 0 | - | 7" exposure · 50-yr warranty · 1" ventilated rainscreen on SIB
Allura Panel + Shakes + Soffit — T2–T4 upgrade | DIV 10-CP | [8 empty] | 0 | - | Spectrum pre-finished · no field paint
Allura Trim — all openings, corners (all tiers) | DIV 10-CT | [8 empty] | 0 | - | Window/door trim, corner boards, band boards
Fire Extinguishers & Cabinets | DIV 10-FE | [8 empty] | 0 | - | Code-required per unit
Toilet Partitions & Bath Accessories | DIV 10-TP | [8 empty] | 0 | - | Grab bars, mirrors, accessories per unit
Signage — Code-Required (Egress / Unit ID) | DIV 10-SG | [8 empty] | 0 | - | Per unit allowance
1J SUBTOTAL | DIV 10 | 0 | 0 | 0 | 0
1K — DIV 11 Equipment (appliances, specialty)
Kitchen Appliances — refrigerator, range, DW, microwave | DIV 11-KIT | [8 empty] | 0 | - | Mid-range residential. All tiers.
Heat Pump Water Heater (HPWH) — UEF ≥3.5 | DIV 11-WH | [8 empty] | 0 | - | All tiers
Drainwater Heat Recovery (T2–T4) | DIV 11-DHR | [8 empty] | 0 | - | $750/unit T2–T4
NatureMill Indoor Composter (T4 only) | DIV 11-NM | [8 empty] | 0 | - | $1,000/unit · 5W draw · T4 only
Crop Circle Farms® Modular Rooftop System (T4) | DIV 11-CC | [8 empty] | 0 | - | $10,000/unit · patented · 200–600 lbs/yr yield
1K SUBTOTAL | DIV 11 | 0 | 0 | 0 | 0
1L — DIV 12 Furnishings
FF&E — Fixed Furnishings Allowance | DIV 12-FF | [8 empty] | 0 | - | Built-in shelving, closet systems
Window Treatments — Blinds/Shades | DIV 12-WT | [8 empty] | 0 | - | Per unit allowance
1L SUBTOTAL | DIV | 0 | 0 | 0 | 0
1N — DIV 14 Conveying Equipment
Elevator — Shaft Provisions Only (2-story = $0) | DIV 14-SP | [8 empty] | 0 | - | 2-story pilot = no elevator. Allowance for 3+ story future.
1N SUBTOTAL | DIV | 0 | 0 | 0 | 0
1O — DIV 21 Fire Suppression
Sprinkler System — NFPA 13R (Residential Townhouse) | DIV 21-SR | [8 empty] | 0 | - | $4.20/SF · verify with Wilmington Fire AHJ
Standpipe / Fire Pump (if AHJ-required) | DIV 21-FP | [8 empty] | 0 | - | 2-story: not typically required. Confirm.
1O SUBTOTAL | DIV | 0 | 0 | 0 | 0
1P — DIV 22 Plumbing
Plumbing — Sanitary DWV (drain/waste/vent) | DIV 22-DWV | [8 empty] | 0 | - | $3.80/SF · 2 baths + kitchen
Plumbing — Domestic Water Supply (hot/cold) | DIV 22-DW | [8 empty] | 0 | - | $2.40/SF
Plumbing Fixtures & Trim (toilets, sinks, tubs) | DIV 22-FX | [8 empty] | 0 | - | T1–T2: $3,800/unit · T3–T4: $4,500/unit
Gas Rough-In (all-electric spec = $0) | DIV 22-GS | [8 empty] | 0 | - | All-electric Forward Home. No gas. $0.
Roof Drainage / Interior Leaders | DIV 22-RD | [8 empty] | 0 | - | $1.20/SF
500-gal Cistern + Gravity-Fed Drip Irrigation (T4) | DIV 22-CI | [8 empty] | 0 | - | $4,000/unit T4 · closed water loop
1P SUBTOTAL | DIV | 0 | 0 | 0 | 0
1Q — DIV 23 HVAC / Mechanical
HVAC — T1 Standard Cold-Climate Mini-Split (≥SEER2 18) | DIV 23-MS | [8 empty] | 0 | - | ASSUMPTIONS MEP T1 rate · ductless
HVAC — T2 Quilt 3-Zone (SEER2 25.3/HSPF2 12) + T4 Battery-Optimized | DIV 23-QT | [8 empty] | 0 | - | OTA firmware · 7⅞" indoor unit · occupancy sensing
HVAC — T3 Mitsubishi FX-Series H2i sumo (SEER2 29.9) | DIV 23-MF | [8 empty] | 0 | - | 10-yr warranty · R454B · Diamond Contractor required
Viessmann Vitoair ERV — 85% SRE / MERV 13 (T2–T4) | DIV 23-ERV | [8 empty] | 0 | - | CO₂-responsive · ASHRAE 62.2+25%
Ductwork / Distribution (ductless: minimal) | DIV 23-DK | [8 empty] | 0 | - | $500/unit stub-only allowance
Exhaust — Bathrooms, Kitchen, Laundry | DIV 23-EX | [8 empty] | 0 | - | $800/unit · inline fans + range hood
Building Automation / Smart Thermostat | DIV 23-BAS | [8 empty] | 0 | - | T1: programmable. T2–T4: Quilt/Mitsubishi app + sensors.
1Q SUBTOTAL | DIV | 0 | 0 | 0 | 0
1R — DIV 26 Electrical (service, wiring, lighting, smart panel)
Electrical Service — Standard 200A (T1) | DIV 26-SV | [8 empty] | 0 | - | EV + PV stub-outs included
SPAN MAIN 40 Smart Panel (T2–T4) — UL 3141 Certified | DIV 26-SP | [8 empty] | 0 | - | First UL 3141 · 32 circuits · Eaton-backed
Branch Wiring — Power & Circuits | DIV 26-BW | [8 empty] | 0 | - | $4.80/SF
Lighting Fixtures — Interior LED | DIV 26-LI | [8 empty] | 0 | - | $2.20/SF T1–T2 · $2.40/SF T3–T4
Lighting — Exterior / Entry | DIV 26-LE | [8 empty] | 0 | - | Allowance per unit
Emergency / Exit Lighting | DIV 26-EM | [8 empty] | 0 | - | Battery-backup allowance
EV Charging Stub (conduit + circuit) | DIV 26-EV | [8 empty] | 0 | - | NEMA 14-50 · future-ready · all tiers
1R SUBTOTAL | DIV | 0 | 0 | 0 | 0
1R-E — DIV 26E PV Solar + Battery Storage
PV Stub-Out Only — T1 | DIV 26E-S1 | [8 empty] | 0 | - | Conduit + inverter space + utility notice. No panels.
PV 5.5 kW + Enphase IQ8 Microinverters — T2 | DIV 26E-P2 | [8 empty] | 0 | - | Mid of $15K–$19.5K range
PV 8.5 kW High-Efficiency TOPCon/HJT — T3 | DIV 26E-P3 | [8 empty] | 0 | - | ≥22% efficiency · Enphase IQ8
PV Agrivoltaic Trellis 8.5–12 kW Bifacial TOPCon — T4 | DIV 26E-P4 | [8 empty] | 0 | - | Elevated 5–6 ft · E/W orientation over Crop Circle beds
Battery — Enphase IQ5P or Tesla Powerwall 3 (T2–T3) | DIV 26E-B23 | [8 empty] | 0 | - | 15-yr warranty · island-capable
Battery — EcoFlow DELTA Pro Ultra + FranklinWH aPower 2 (T4) | DIV 26E-B4 | [8 empty] | 0 | - | 19.2–90 kWh · true off-grid island mode
1R-E SUBTOTAL | DIV | 0 | 0 | 0 | 0
1S — DIV 27/28 Communications + Security
Data / Network Infrastructure (Cat6 + WiFi Stub) | DIV 27-DA | [8 empty] | 0 | - | Per unit residential rough-in
Security — Access Control + Camera Stub | DIV 28-AC | [8 empty] | 0 | - | T1 stub · T2–T4 smart-home integration ready
Fire Alarm / Smoke Detection (Interconnected) | DIV 28-FA | [8 empty] | 0 | - | Hardwired · code-required · all tiers
1S SUBTOTAL | DIV | 0 | 0 | 0 | 0
1T — DIV 32/33 Site Work + Landscaping + Rooftop Systems
Site Work (City-Funded: grading, utilities, paving) | DIV 32-SW | [8 empty] | 0 | - | $0 developer cost — City of Wilmington program
Landscaping / Entry Hardscape Allowance | DIV 32-LS | [8 empty] | 0 | - | Per unit entry + foundation planting
LiveRoof® Standard (700 SF) — T2 | DIV 32-LR2 | [8 empty] | 0 | - | 4.25" soil · FM 4477 · ASTM E108 Class A
LiveRoof® MAXX + Edible Rows (Up Top Acres) — T3 | DIV 32-LR3 | [8 empty] | 0 | - | 8" soil · productive planting rows
Agrivoltaic Trellis + Crop Circle Farms Rooftop — T4 | DIV 32-AGR | [8 empty] | 0 | - | Bifacial PV above growing beds · 200–600 lbs/yr yield
Cistern + Drip Stub (T3) / Full System (T4 in DIV 22) | DIV 32-CI | [8 empty] | 0 | - | T3: drip stub. T4: full cistern in DIV 22.
1T SUBTOTAL | DIV | 0 | 0 | 0 | 0
SECTION 1 TOTAL — HARD COSTS (Construction) · ROM = M4Di ALDi Locked Baseline
TOTAL HARD COST (Construction ROM → SOV → Actual) |  | 0 | 0 | 0 | 0
SECTION 2 — SOFT COSTS (Professional Fees & Consultants)
Architecture — Base Fee (M4D / Aubyn Architecture) | AE-ARCH | [8 empty] | 0 | -
Architecture — ALDi / PM / Owner's Rep (M4D) | AE-PM | [8 empty] | 0 | -
Structural Engineering | ENG-STR | [8 empty] | 0 | -
Mechanical Engineering (HVAC — CBai-assisted) | ENG-MECH | [8 empty] | 0 | -
Electrical Engineering | ENG-ELEC | [8 empty] | 0 | -
Plumbing Engineering | ENG-PLMB | [8 empty] | 0 | -
Fire Protection / Sprinkler Engineering | ENG-FP | [8 empty] | 0 | -
Civil Engineering | ENG-CIV | [8 empty] | 0 | -
Geotechnical / Soils Report | ENG-GEO | [8 empty] | 0 | -
ADA / Accessibility Consultant | CONS-ADA | [8 empty] | 0 | -
HERS Rater + DOE ZERH Enrollment (T2) | CERT-T2 | [8 empty] | 0 | -
PHIUS Rater + Commissioning (T3–T4) | CERT-T3T4 | [8 empty] | 0 | -
M4Di ALDi Controls (this workbook + gate fees) | M4DI-ALDI | [8 empty] | 0 | -
Permitting / Plan Review Fees | SC-PERM | [8 empty] | 0 | -
Builder's Risk Insurance (owner-procured) | SC-INSR | [8 empty] | 0 | -
Testing / Special Inspections | SC-TEST | [8 empty] | 0 | -
Legal / Title / Closing Costs | SC-LEGAL | [8 empty] | 0 | -
Financing / Loan Origination / CDFI Fees | SC-FIN | [8 empty] | 0 | -
IRA §45L Developer Credit (enter as negative, T2–T4) | IRA-45L | [8 empty] | 0 | -
TOTAL SOFT COSTS | SOFT | 0 | 0 | 0 | 0
SECTION 3 — OWNER CONTINGENCY & DIRECT COSTS
Owner Project Contingency (post-GMP reserve) | OWN-CONT | [8 empty] | 0 | -
FF&E — Owner-Procured Furnishings | OWN-FFE | [8 empty] | 0 | -
Technology / AV / IT (owner-procured) | OWN-TECH | [8 empty] | 0 | -
Moving / Relocation / Transition Costs | OWN-MOV | [8 empty] | 0 | -
Predevelopment Costs (M4Di P1–P3 Fees) | M4DI-PRE | [8 empty] | 0 | -
Grant Strategy / Application Support (M4Di) | M4DI-GRT | [8 empty] | 0 | -
Program Reserve / Funding Gap Buffer | OWN-RESV | [8 empty] | 0 | -
City Land + Site/Infrastructure (City-funded = $0) | CITY-LAND | [8 empty] | 0 | -
TOTAL OWNER CONTINGENCY & DIRECT COSTS | OWN | 0 | 0 | 0 | 0
TOTAL PROJECT INVESTMENT |  | 0 | 0 | 0 | 0
SUMMARY METRICS
Total Project Investment |  | 0 | 0
Hard Cost Only |  | 0 | 0
Total Soft Costs |  | 0 | 0
Soft Cost as % of Hard Cost |  | - | -