## PROJECT REGISTRY
MERGE 4 DESIGN LLC ¦ AUBYN ARCHITECTURE LLC — MASTER PROJECT REGISTRY
As of: May 19, 2026 ¦ Use filters to isolate by Firm, Phase, PM, or Status
Project # | Project Name | Firm | Client | PM | Phase | Overall Status | Contract Value | Fee Earned | % Complete | Start Date | Target End | Permit Status | Next Action | Notes
AE24-002 | 1316-26 N Claymont — 4-Unit CLT/SIP Townhouse | M4D / Aubyn | L.E.E.P. Inc. | DCA | CD / Permit | In-Process | $185,000 |  | 65% | 2024-09-01 | 2026-09-30 | Foundation Permit Approved | Resolve CR-01–CR-04 AHJ comments | CLT panels in production; SIP started ~5/9/26
AE24-011 | Elsmere Town Hall — Window Replacement | M4D / Aubyn | Town of Elsmere | DCA | Proposal | Behind | TBD |  | 5% | 2024-10-01 | 2025-02-28 | N/A | Resubmit proposal
AE24-012 | 2304 N Market St — Renovation & Addition | M4D | Private Client | DCA | SD | In-Process | TBD |  | 10% | 2024-10-15 | 2026-06-30 | Pre-Application | Complete SD layouts
AE24-003 | 38 E 23rd St — Mixed-Use Apartments | M4D | Private Client | LEO | DD | Behind | TBD |  | 20% | 2024-09-01 | 2026-08-31 | ZBR Pending | Get MEP fee proposal | ZBR approval pending
AE24-004 | 801 S Harrison — L.E.E.P. HQ & Training Center | M4D / Aubyn | L.E.E.P. Inc. | DCA | DD | In-Process | TBD |  | 25% | 2024-09-01 | 2026-12-31 | Pre-Application | Advance DD package
WHA-001 | 1212 Lobdel Ave — Forward Housing Townhouses | M4D | WHA | DCA | Pre-Design / G0 | In-Process | TBD |  | 15% | 2025-12-01 | 2027-06-30 | N/A | Finalize yield scenario selection | 19-unit Scenario A preferred; ROM $4.56M–$5.13M
M4Di-001 | M4Di OI Tool — Path B Hybrid Build | M4Di | Internal | DCA | Development | In-Process | N/A |  | 30% | 2025-10-01 | 2026-12-31 | N/A | Enterprise/WF grant decision July 2026 | Year 1 tech budget $20K–$25K

## GANTT — ACTIVE PROJECTS
MERGE 4 DESIGN LLC ¦ ACTIVE PROJECT GANTT — ROLLING 52-WEEK SCHEDULE
Project # | Task / Deliverable | Phase | Lead | Status | Start Date | End Date | Dur (wks) | May 2026 |  | Jun 2026 |  |  |  |  | Jul 2026 |  |  |  | Aug 2026 |  |  |  |  | Sep 2026 |  |  |  | Oct 2026 |  |  |  | Nov 2026 |  |  |  |  | Dec 2026 |  |  |  | Jan 2027 |  |  |  | Feb 2027 |  |  |  | Mar 2027 |  |  |  |  | Apr 2027 |  |  |  | May 2027
Project # | Task / Deliverable | Phase | Lead | Status | Start Date | End Date | Dur (wks) | 05/18 | 05/25 | 06/01 | 06/08 | 06/15 | 06/22 | 06/29 | 07/06 | 07/13 | 07/20 | 07/27 | 08/03 | 08/10 | 08/17 | 08/24 | 08/31 | 09/07 | 09/14 | 09/21 | 09/28 | 10/05 | 10/12 | 10/19 | 10/26 | 11/02 | 11/09 | 11/16 | 11/23 | 11/30 | 12/07 | 12/14 | 12/21 | 12/28 | 01/04 | 01/11 | 01/18 | 01/25 | 02/01 | 02/08 | 02/15 | 02/22 | 03/01 | 03/08 | 03/15 | 03/22 | 03/29 | 04/05 | 04/12 | 04/19 | 04/26 | 05/03 | 05/10
AE24-002 ¦ 1316-26 N CLAYMONT ST — CLT/SIP HYBRID TOWNHOUSE ¦ Client: L.E.E.P. Inc.
AE24-002 | AHJ Comment Response CR-01–CR-04 | CD | DCA | In-Process | 05/12/26 | 06/06/26 | 4 | bar: May 2026 05/18 to Jun 2026 06/01
AE24-002 | A-502 QA Markup & EOR Submission | CD | DCA | In-Process | 05/19/26 | 06/06/26 | 3
AE24-002 | CLT / SIP Panel Delivery On-Site | Construction | DCA | Not Started | 06/22/26 | 06/22/26 | 1 | bar: May 2026 05/18; Jun 2026 06/22
AE24-002 | Foundation / Slab Complete | Construction | DCA | Complete | 03/01/26 | 05/06/26 | 9
AE24-002 | Structural Framing / Panel Install | Construction | DCA | Not Started | 06/22/26 | 08/15/26 | 8 | bar: May 2026 05/18; Jun 2026 06/22 to Aug 2026 08/10
AE24-002 | MEP Rough-In | Construction | DCA | Not Started | 08/01/26 | 09/15/26 | 6
AE24-002 | Certificate of Occupancy Target | Closeout | DCA | Not Started | 09/30/26 | 09/30/26 | 1 | bar: May 2026 05/18; Sep 2026 09/28
WHA-001 ¦ 1212 LOBDEL AVE — FORWARD HOUSING TOWNHOUSES ¦ Client: WHA
WHA-001 | Yield Scenario Finalization | G0 ROM | DCA | In-Process | 05/01/26 | 05/31/26 | 4 | bar: May 2026 05/18 to May 2026 05/25
WHA-001 | Schematic Design — Selected Scheme | SD | DCA | Not Started | 06/01/26 | 07/31/26 | 9
WHA-001 | DD Package + MEP Narrative | DD | DCA | Not Started | 08/01/26 | 10/31/26 | 13 | bar: May 2026 05/18; Jul 2026 07/27 to Oct 2026 10/26
M4Di-001 ¦ OI TOOL — PATH B HYBRID BUILD ¦ Internal / M4Di
M4Di-001 | Path B Hybrid OI Tool Build | Dev | DCA | In-Process | 04/01/26 | 12/31/26 | 39 | bar: May 2026 05/18 to Dec 2026 12/28
M4Di-001 | E/WF Grant Decision (Round 2) | Grant | LEO | In-Process | 07/01/26 | 07/31/26 | 4
M4Di-001 | OED Pilot Deployment | Pilot | DCA | Not Started | 10/01/26 | 03/31/27 | 26 | bar: May 2026 05/18; Sep 2026 09/28 to Mar 2027 03/29

## PROJECT STATUS REPORT
PROJECT STATUS REPORT
Merge 4 Design LLC ¦ Aubyn Architecture LLC |  |  |  | Report Date: May 19, 2026
PROJECT INFORMATION
Project No.: | AE24-002 |  |  | Firm: | M4D / Aubyn Architecture
Project Name: | 1316-26 N Claymont St — CLT/SIP Hybrid Townhouse |  |  | Client: | L.E.E.P. Inc. / Gwenevere Motley
Project Manager: | David Ainsworth, AIA (DCA) |  |  | Contract Value: | $185,000
Current Phase: | Construction Documents / Permit |  |  | % Complete: | 65%
Start Date: | September 1, 2024 |  |  | Target End: | September 30, 2026
Overall Status: | IN-PROCESS |  |  | Permit Status: | Foundation Permit Approved 05/06/2026
SCHEDULE SUMMARY
Milestone | Responsible | Planned Date | Actual / Target | Status | Notes
Foundation Permit | DCA / AHJ | 05/01/2026 | 05/06/2026 | Complete | Approved
Structural Issue Resolution | DCA / Larry Carson PE | 05/05/2026 | 05/05/2026 | Complete | Zoom with panel engineers
SIP Production Start | Acme / Panelwrights | 05/09/2026 | ~05/09/2026 | Complete | Confirmed
AHJ Comment Response CR-01–CR-04 | DCA | 06/06/2026 | 06/06/2026 | In-Process | Critical/blocking items
CLT / SIP Panel Delivery | Acme | 06/22/2026 | 06/22/2026 | Not Started | On schedule per fabricator
Structural Framing Complete | GC | 08/15/2026 | 08/15/2026 | Not Started
MEP Rough-In Complete | GC + MEP | 09/15/2026 | 09/15/2026 | Not Started
Certificate of Occupancy | AHJ | 09/30/2026 | 09/30/2026 | Not Started | L.E.E.P. occupancy target
OPEN ISSUES & ACTION ITEMS
Issue / Action Item | # | Priority | Assigned To | Due Date | Status
EOR of Record designation required by AHJ | CR-01 | CRITICAL | DCA | 06/06/2026 | In-Process
Structural calcs for CLT-to-CMU connection | CR-02 | CRITICAL | DCA + Larry Carson | 06/06/2026 | In-Process
Fire-resistance assembly documentation (2HR) | CR-03 | CRITICAL | DCA | 06/06/2026 | In-Process
Energy compliance (IECC) path confirmation | CR-04 | CRITICAL | DCA | 06/06/2026 | In-Process
A-502 Detail 3: SIP-to-CMU bearing ESR-4689 deviation | QA-01 | HIGH | DCA | 05/30/2026 | In-Process
CMU wall dimension conflict D-1 (8") vs D-3 (10") | QA-02 | HIGH | DCA | 05/30/2026 | In-Process
2HR rating basis not cited for CLT party wall | QA-03 | HIGH | DCA | 05/30/2026 | In-Process
FEE / BUDGET SUMMARY
Contract Value | $185,000 |  |  | Invoiced to Date | $60,250
Received to Date | $55,000 |  |  | % Fee Earned | 32.6%
Reimbursables Billed | $2,400 |  |  | Reimbursables Received | $2,400
NOTES & NEXT STEPS
1. Complete A-502 Track 1 markup — resolve Detail 3 SIP-to-CMU bearing, reconcile CMU wall dimension conflict, cite 2HR assembly references. 2. Issue formal AHJ response package addressing CR-01 through CR-04 by June 6, 2026. 3. Engage Larry Carson PE for EOR formal acceptance or coordinate alternate EOR per CR-01. 4. Confirm CLT panel delivery window with Acme/Panelwrights (target June 22 on-site). 5. Coordinate GC mobilization and site logistics with Gwen Motley / L.E.E.P.
Merge 4 Design LLC ¦ 215 N. Market St., Suite 317, Wilmington, DE 19801 ¦ david4d@merge4design.com ¦ Confidential — For Project Team Use

## TASK LIST — ALDi GATES
MERGE 4 DESIGN ¦ PROJECT TASK LIST — ALDi GATE SYSTEM
Project # | Phase / Gate | Sub-Category | Task / Deliverable | Accountable | Assist | Status | Start | Due | % Done | Notes / Comments
▶ AE24-002 ¦ 1316-26 N CLAYMONT ST — CLT/SIP HYBRID TOWNHOUSE
AE24-002 | G1 SD | Design | Schematic Design — site + unit layouts | LEO | TRAVIS | Complete | 10/15/24 | 12/15/24 | 100% | Client approved
AE24-002 | G1 SD | Civil | Lot subdivision / site survey | TRAVIS | Civil Eng | Complete | 10/15/24 | 01/15/25 | 100%
AE24-002 | G2 DD | Design | DD Package + MEP narrative | DCA | ENG | Complete | 01/15/25 | 04/01/25 | 100%
AE24-002 | G2 DD | Structural | EOR engagement — structural calcs | DCA | Larry Carson PE | In-Process | 04/01/25 | 06/06/26 | 85% | EOR seat open per CR-01
AE24-002 | G3 CD | Permitting | AHJ Comment Response CR-01–CR-04 | DCA | EOR | In-Process | 05/12/26 | 06/06/26 | 40% | Critical / blocking
AE24-002 | G3 CD | Design | A-502 Track 1 markup — QA issues | DCA | ENG | In-Process | 05/19/26 | 05/30/26 | 20% | Detail 3, CMU dim, 2HR rating
AE24-002 | G3 CD | Construction | CLT / SIP panel delivery on-site | DCA | Acme | Not Started | 06/22/26 | 06/22/26 | 0% | On schedule
AE24-002 | G3 CD | Construction | Structural framing / panel install | GC | DCA | Not Started | 06/22/26 | 08/15/26 | 0%
AE24-002 | G3 CD | MEP | MEP rough-in complete | GC | MEP | Not Started | 08/01/26 | 09/15/26 | 0%
AE24-002 | G4 Closeout | Closeout | Certificate of Occupancy | AHJ | DCA | Not Started | 09/15/26 | 09/30/26 | 0% | L.E.E.P. target July 2026
▶ WHA-001 ¦ 1212 LOBDEL AVE — FORWARD HOUSING TOWNHOUSES
WHA-001 | G0 ROM | Predevelopment | ROM — 20-ft lot (17 units, Scenario B) | DCA | M4Di | Complete | 01/01/26 | 04/30/26 | 100% | $4.08M–$4.59M range
WHA-001 | G1 SD | Design | Yield scenario selection — client approval | TK | DCA | In-Process | 05/01/26 | 05/31/26 | 50% | WHA preference TBD
WHA-001 | G1 SD | Design | Schematic Design — selected scheme | LEO | TRAVIS | Not Started | 06/01/26 | 07/31/26 | 0%

## TEAM & CONTACTS
MERGE 4 DESIGN ¦ AUBYN ARCHITECTURE ¦ TEAM & CONTACTS
# | Name | Initials | Title / Role | Firm | Email | Cell
1 | David Ainsworth, AIA | DCA | Principal / Predevelopment Lead | M4D / Aubyn Architecture | david4d@merge4design.com | (203) 506-2413
2 | Trevor Knight | TK | Dir. Business Development / Strategy | M4D | trevor4d@merge4design.com | (302) 367-5726
3 | Leo Lynch | LLL | Operations / Grants | M4D | leo4d@merge4design.com | (302) 345-1072
4 | Travis Davis | TD | Dir. Architecture Technology | M4D | travis4d@merge4design.com | (302) 317-6608
5 | Gwen Motley | GM | Executive Director | L.E.E.P. Inc. | — | —
STATUS COLOR LEGEND
Not Started |  | Task not yet begun
In-Process |  | Task underway — on schedule
Behind |  | Task underway — at risk of missing deadline
Blocked |  | Task stopped — external dependency or decision required
Complete |  | Task finished
N/A |  | Not applicable to this project

## HOW TO USE
M4D / AUBYN ARCHITECTURE — PROJECT TRACKER ¦ HOW TO USE
SHEET | PROJECT REGISTRY | Master list of all active M4D and Aubyn projects. Use the auto-filter (row 3) to isolate by firm, phase, PM, or status. Print via File → Print (landscape, Fit to 1 page wide).
SHEET | GANTT — ACTIVE PROJECTS | Rolling 52-week Gantt chart. Project banners group tasks. The TODAY column is highlighted in yellow with a red border. Freeze pane at column I keeps task info visible while scrolling weeks. Print via File → Print (landscape, Fit to 1 page wide). Use print title columns A:H to repeat task info on multi-page prints.
SHEET | PROJECT STATUS REPORT | Printable one-page status report. Update the project info block, schedule, issues, and budget sections for each client report. Print via File → Print (portrait, Fit to 1 page). Duplicate this sheet for each project.
SHEET | TASK LIST — ALDi GATES | Per-project task management organized by ALDi gate (G0 ROM → G1 → G2 → G3 GMP → G4 Closeout). Use auto-filter to isolate by project or phase. Status dropdowns in column G.
SHEET | TEAM & CONTACTS | Team directory and color legend reference.
ACTION | Add a new project | 1. Add to PROJECT REGISTRY (row 4+). 2. Add task rows to TASK LIST — ALDi GATES. 3. Add Gantt rows to GANTT sheet with correct start/end dates. 4. Duplicate PROJECT STATUS REPORT sheet and rename.
ACTION | Print a client report | Go to PROJECT STATUS REPORT. Update data. File → Print (portrait). One page per project.
ACTION | Filter by project | PROJECT REGISTRY: use auto-filter column A. TASK LIST: use auto-filter column A (Project #). GANTT: rows are grouped by project banner.
COLOR CODE | Status Key | Not Started = Gray ¦ In-Process = Yellow ¦ Behind = Orange ¦ Blocked = Red ¦ Complete = Green ¦ N/A = Mid-Gray
NAMING | Project number format | AE24-002 = Architecture project #002 started FY24. M4Di-001 = M4Di internal project. WHA-001 = WHA client project.
STANDARD | Firm attribution | M4D / Aubyn = both firms involved (M4D lead, Aubyn as AOR). M4D = M4D only. Aubyn Architecture = Aubyn solo engagement. M4Di = M4Di predevelopment/tool work.