## COVER
M4Di ¦ ALDi Design & Construction Budget Tracker
Project Cost Control from ROM Estimate Through Construction Closeout
Project Name: |  |  |  | Enter the official M4Di project code
Project Address: |  |  |  | Full site address
Owner / Client: |  |  |  | Legal entity name
Architect of Record: |  |  |  | e.g., M4D / Aubyn Architecture
M4Di Project Lead:
Gross Area (SF): |  |  |  | Total building SF in scope
ALDi Start Date: |  |  |  | Date M4Di ALDi engagement begins
ROM Estimate Date: |  |  |  | Date of M4Di P3 ROM (v1)
COLUMN GUIDE — Four Estimate Stages
Column | Stage | When Populated | Purpose / Notes
Column D M4Di ROM | Rough Order of Magnitude | At ALDi engagement start (P3 deliverable) | The locked baseline. Never changes after ALDi Gate 0. All variances measured against this column.
Column E 75% DD Estimate | Design Development (75%) | At ALDi Gate 2 (DD milestone) | First major design-informed reality check. Should be within ±15% of ROM. Flag and explain if not.
Column F 100% CD / Contractor SOV | Construction Documents / GMP | At ALDi Gate 3 (GMP execution) | The contracted number. All future change orders are additions to this column. Defines the budget baseline.
Column G Actual Cost | Construction Closeout | Updated monthly during construction | Running total of all committed costs: executed SOV + approved COs + owner direct costs.
CORE RULES FOR THIS WORKBOOK
1. | Column D (M4Di ROM) is LOCKED after ALDi Gate 0. It never changes. It is the reference baseline for every downstream comparison.
2. | Column E (75% DD) is entered at Gate 2. If the DD estimate exceeds Column D by more than 15%, a written explanation is required in the VARIANCE LOG before the gate is cleared.
3. | Column F (100% CD / SOV) is entered at Gate 3 from the executed Contractor Schedule of Values. This is the contracted hard cost. Soft costs in this column come from executed consultant agreements.
4. | Column G (Actual Cost) is updated monthly. It equals Column F plus all approved change orders plus all owner direct costs incurred to date. It is never projected — only committed costs.
5. | Every line item in this tracker maps to a line item in the M4Di OI Tool (BID SUMMARY, SOFT COSTS, or TOTAL PROJECT BUDGET). The M4Di project lead maintains both files in sync.
6. | This workbook is an M4Di ALDi deliverable. It is issued to the Owner and AE at Gate 0 setup. The Owner and AE receive read-only PDF exports monthly. The live Excel file is M4Di-controlled.

## BUDGET TRACKER
M4Di ¦ ALDi Design & Construction Budget Tracker
[Project Name — complete COVER tab]
Budget Item | CSI / Ref | M4Di ROM (LOCKED BASELINE) | 75% DD ESTIMATE (Gate 2) | 100% CD / SOV (Gate 3 — Contracted) | ACTUAL COST (Running Total) | ROM vs. DD Variance | GC QUOTE / PROPOSAL (Pre-SOV) | GC ACTUALS (Running Total) | ROM vs. GC Quote Variance | CD vs. Actual Variance |  | Notes / Status
Budget Item | CSI / Ref | $ Amount | $ Amount | $ Amount | $ Amount | $ Variance | $ Amount | $ Amount | $ Variance | $ Variance | % Var | Notes / Flag
► Col D: M4Di ROM (locked Gate 0) ► Col E: Enter at Gate 2 (75% DD) ► Col F: Enter at Gate 3 from GMP/SOV ► Col G: Update monthly ► Col I: GC Quote/Proposal (pre-SOV) ► Col J: GC Actuals (monthly)
SECTION 1 — HARD COSTS (Construction)
1A — Procurement & General Requirements
General Conditions (GC Time & Overhead) | DIV 00/01
Temporary Facilities, Utilities & Hoarding | DIV 01-TF | [8 empty] | 0 | - | Per takeoff; hazmat TBD pending survey
Site Safety, Security & Signage | DIV 01-SS | [8 empty] | 0 | - | Housekeeping pads; structural repairs
Dumpsters / Debris Removal | DIV 01-DR | [8 empty] | 0 | - | Misc. metals; stair rails; lintels
Payment & Performance Bond | DIV 00-BD | [8 empty] | 0 | - | Interior partition framing
Builder's Risk Insurance | DIV 00-BR | [8 empty] | 0 | - | Roof repairs; waterproofing; sealants
GC Fee / Overhead & Profit | DIV 00-OH | [8 empty] | 0 | - | Anti-ligature hardware; ADA entries
1B — Existing Conditions | [9 empty] | 0 | - | Rubber athletic; resilient; carpet tile
Selective Demolition — Interior | DIV 02-DI | [8 empty] | 0 | - | High-perf coatings + standard paint
Selective Demolition — Exterior / Site | DIV 02-DE | [8 empty] | 0 | - | ACT; GWB ceilings; soffits
Hazardous Materials Survey / Testing | DIV 02-HT | [8 empty] | 0 | - | Bathroom accessories; millwork
Hazardous Materials Abatement (ACM/Lead/Mold) | DIV 02-HA
Dewatering / Site Preparation | DIV 02-SP | [8 empty] | 0 | - | Full building in Phase 1A per Program Guide
1C — Concrete | [9 empty] | 0 | - | Full building; NFPA 72 compliant
Cast-in-Place Concrete — Foundations / Slabs | DIV 03-CF | [8 empty] | 0 | - | Sized for full building future build-out
Concrete Repair / Patching | DIV 03-CR | [8 empty] | 0 | - | Partial area; backbone for Phase 1B tie-in
Precast Concrete Elements | DIV 03-PC | [8 empty] | 0 | - | Scalable panels; risers; branch circuits
1D — Masonry | [9 empty] | 0 | - | Staff monitoring; access control; data
Masonry — New CMU / Brick | DIV 04-NM | [8 empty] | 0 | - | Structural + enclosure allowance; no cab
Masonry Repair / Repointing | DIV 04-MR
1E — Metals | [9 empty] | 0 | - | Backstops, bleachers, scoreboard — PENDING
Structural Steel — Framing & Connections | DIV 05-SS | [8 empty] | 0 | - | Wall padding, boxing ring, bag systems
Stairs — Structural Steel / Metal Pan | DIV 05-ST | [8 empty] | 0 | - | OT/PT; sensory room; de-escalation rooms
Miscellaneous Metals — Rails, Lintels, Angles | DIV 05-MM | [8 empty] | 0 | - | Commercial kitchen package — PENDING
Metal Decking | DIV 05-MD | [8 empty] | 0 | - | PA, cameras, access control hardware
1F — Wood, Plastics & Composites | [9 empty] | 0 | -
Rough Carpentry — Blocking, Nailers, Backing | DIV 06-RC
Finish Carpentry — Millwork & Casework | DIV 06-FC | [8 empty] | 0 | - | 8.0% of base
Architectural Woodwork / Custom Millwork | DIV 06-AW | [8 empty] | 0 | - | 10.0% of base + GC
1G — Thermal & Moisture Protection | [9 empty] | 0 | - | 12.0% — reduce at SD, DD, GMP
Roofing — Membrane System (TPO/EPDM/BUR) | DIV 07-RF | [8 empty] | 0 | - | 12.0% — pre-1980 building; reduce after hazmat survey
Roof Insulation & Cover Board | DIV 07-RI | [8 empty] | 0 | - | 5.0% — reduce as equipment selections confirmed
Wall Insulation (Batt / Rigid / Spray) | DIV 07-WI | [8 empty] | 0 | - | 2.0% of total
Acoustic Insulation (STC / NRC Assemblies) | DIV 07-AI | [8 empty] | 0 | -
Air Barrier / Vapor Retarder | DIV 07-AB
Waterproofing — Below Grade / Foundation | DIV 07-WP
Caulking, Sealants & Joint Fillers | DIV 07-JS
1H — Openings | [9 empty] | 0 | - | Per AIA fee schedule, Type C renovation + premium
Hollow Metal Doors, Frames & Hardware | DIV 08-HM | [8 empty] | 0 | - | Project Management per fee agreement
Wood Doors & Frames | DIV 08-WD | [8 empty] | 0 | - | 1.5% of hard cost
Storefront / Curtain Wall / Aluminum Glazing | DIV 08-CW | [8 empty] | 0 | - | 1.8% of hard cost
Windows — New / Replacement | DIV 08-WN | [8 empty] | 0 | - | 1.5% of hard cost
Overhead / Coiling Doors | DIV 08-OD | [8 empty] | 0 | - | 1.0% of hard cost
Accessible Entry — Operators, Ramp, Hardware | DIV 08-AE | [8 empty] | 0 | - | 0.8% of hard cost
1I — Finishes | [9 empty] | 0 | - | Limited site coordination only
Drywall — Partitions, Shafts & Soffits | DIV 09-DW | [8 empty] | 0 | - | Fixed fee — required before Phase 1A foundation work
Drywall — Acoustic / STC Assemblies | DIV 09-AC | [8 empty] | 0 | - | 0.5% — required for HUD/CDFI-funded projects
Plaster / Stucco / EIFS | DIV 09-PL | [8 empty] | 0 | - | Gates 0–4 + monthly reporting through closeout
Tile — Ceramic / Porcelain (Floors & Walls) | DIV 09-TL
Flooring — LVT / VCT / Vinyl Sheet | DIV 09-FV | [8 empty] | 0 | - | 2.0% of hard cost — NCC + state agencies
Flooring — Carpet / Carpet Tile | DIV 09-FC | [8 empty] | 0 | - | 0.8% — confirm with owner’s insurance agent
Flooring — Wood / Bamboo / Specialty | DIV 09-FW | [8 empty] | 0 | - | IBC-required inspections; materials testing
Flooring — Polished / Sealed Concrete | DIV 09-FP | [8 empty] | 0 | - | Required for CDFI/HUD financing
Acoustical Ceiling Tile (ACT) & Grid | DIV 09-CT | [8 empty] | 0 | - | Pre-1980 building — asbestos/lead survey required
Gypsum Ceiling / Drywall Ceiling | DIV 09-CC | [8 empty] | 0 | - | Contract review; property matters
Paint & Wall Coatings — Interior | DIV 09-PI | [8 empty] | 0 | - | 1.0% of CDFI loan amount
Paint & Coatings — Exterior | DIV 09-PE | [8 empty] | 0 | - | Grant consultant; application support
Wall Covering / Specialty Wall Finish | DIV 09-WC | [8 empty] | 0 | - | Fixed fee; required for adaptive reuse
1J — Specialties | [9 empty] | 0 | -
Toilet Partitions & Accessories | DIV 10-TP
ADA Restroom Accessories & Grab Bars | DIV 10-ADA
Fire Extinguishers & Cabinets | DIV 10-FE | [8 empty] | 0 | - | 5% of hard cost — reduce as design advances
Signage — Code-Required (Egress / Room ID) | DIV 10-SC | [8 empty] | 0 | - | Enter actual owner FF&E budget
Signage — Branding / Wayfinding (Program) | DIV 10-SB | [8 empty] | 0 | - | Owner-procured systems outside contract
Lockers / Storage Units | DIV 10-LK | [8 empty] | 0 | - | If applicable
Folding Partitions / Operable Walls | DIV 10-FP | [8 empty] | 0 | - | P1 $8K + P2 $14K + P3 $22K — already incurred
Loading Dock Equipment | DIV 10-LD | [8 empty] | 0 | - | Funder exhibits; CDFI package; 3 grants
1K — Equipment (Program-Specific) | [9 empty] | 0 | - | 3–8% of total — enter when funding stack confirmed
Equipment Allowance 1 — [Define per project] | EQP-01 | [8 empty] | 0 | -
Equipment Allowance 2 — [Define per project] | EQP-02
Equipment Allowance 3 — [Define per project] | EQP-03
Equipment Allowance 4 — [Define per project] | EQP-04 | [8 empty] | 0 | -
Kitchen / Food Service Equipment | EQP-KIT
Stage / Platform / Performance Equipment | EQP-STG
1L — Furnishings
FF&E — Fixed Furnishings Allowance | DIV 12-FF
Window Treatments — Blinds / Shades / Acoustic | DIV 12-WT
Casework — Lab / Medical / Specialty | DIV 12-CW
1M — Special Construction
Special Construction — [Define per project] | DIV 13
1N — Conveying Equipment
Elevator — Traction / Hydraulic | DIV 14-EL
Elevator — Shaft Provisions Only | DIV 14-SP
Wheelchair Lift / Vertical Platform Lift | DIV 14-WL
1O — Fire Suppression
Sprinkler System — NFPA 13 (Full Building) | DIV 21-SP
Sprinkler System — NFPA 13R / 13D (Residential) | DIV 21-SR
Standpipe / Fire Pump | DIV 21-FP
1P — Plumbing
Plumbing — Sanitary DWV (Drain/Waste/Vent) | DIV 22-DWV
Plumbing — Domestic Water Supply (Hot/Cold) | DIV 22-DW
Plumbing Fixtures & Trim | DIV 22-FX
Natural Gas Rough-in & Distribution | DIV 22-GS
Roof Drainage / Interior Leaders | DIV 22-RD
1Q — HVAC / Mechanical
HVAC — Ducted Split / RTU / Packaged Systems | DIV 23-RT
HVAC — VRF / Mini-Split Systems | DIV 23-VF
Ductwork & Distribution | DIV 23-DK
Exhaust — Restrooms, Kitchen, Specialty | DIV 23-EX
Controls / Building Automation System (BAS) | DIV 23-BAS
Mechanical Insulation — Piping & Duct | DIV 23-IN
1R — Electrical
Electrical Service & Switchgear / Panels | DIV 26-SV
Branch Wiring — Power & Circuits | DIV 26-BW
Lighting Fixtures — Interior (LED) | DIV 26-LI
Lighting Fixtures — Exterior / Site | DIV 26-LE
Emergency / Exit Lighting | DIV 26-EM
Fire Alarm / Voice Evacuation System | DIV 26-FA
Generator / Emergency Power | DIV 26-GN
1S — Communications & Low Voltage
Data / Network Infrastructure (Cat6/Fiber) | DIV 27-DA
AV / Audio-Visual Systems | DIV 27-AV
Nurse Call / Staff Call / Patient Systems | DIV 27-NC
Security — Access Control | DIV 28-AC
Security — Camera / CCTV System | DIV 28-CC
Intrusion Detection / Alarm | DIV 28-ID
1T — Earthwork & Site Work
Earthwork — Grading / Excavation / Backfill | DIV 31-EW
Paving — Asphalt / Concrete | DIV 32-PA
Landscaping / Planting | DIV 32-LS
Site Utilities — Underground | DIV 33-SU
Site Fencing & Perimeter | DIV 32-SF
1U — Markups & Contingencies
Design Contingency (pre-permit) | MKP-DC
Existing Conditions Contingency | MKP-EC
Owner Selection Contingency | MKP-OS
Bid / Permit / Bond Allowance | MKP-BPB
TOTAL HARD COST (Construction ROM → SOV → Actual) |  | 0 | 0 | 0 | 0 |  | 0 | 0
SECTION 2 — SOFT COSTS (Professional Fees & Consultants)
2A — Architecture & Engineering
Architecture — Base Fee (M4D) | AE-ARCH
Architecture — ALDB / PM / Owner's Rep (M4D) | AE-PM
Structural Engineering | ENG-STR
Mechanical Engineering (HVAC) | ENG-MECH
Electrical Engineering | ENG-ELEC
Plumbing Engineering | ENG-PLMB
Fire Protection / Sprinkler Engineering | ENG-FP
Civil Engineering | ENG-CIV
Geotechnical / Soils Report | ENG-GEO
ADA / Accessibility Consultant | CONS-ADA
Acoustic / AV Design Consultant | CONS-AC
M4Di ALDi Controls (this workbook + gate fees) | M4DI-ALDI
2B — Owner Soft Costs & Agency Fees
Permitting / Plan Review Fees | SC-PERM
Builder's Risk Insurance (owner-procured) | SC-INSR
Testing / Special Inspections / Commissioning | SC-TEST
Phase I / II Environmental Assessment | SC-ENV
Hazardous Materials Survey & Abatement Design | SC-HAZ
Survey / As-Builts / Laser Scan | SC-SURV
Legal / Title / Closing Costs | SC-LEGAL
Financing / Loan Origination / CDFI Fees | SC-FIN
Fundraising / Grant Development Support | SC-DEV
TOTAL SOFT COSTS |  | 0 | 0 | 0 | 0 |  | 0 | 0
SECTION 3 — OWNER CONTINGENCY & DIRECT COSTS
Owner Project Contingency (post-GMP) | OWN-CONT
FF&E — Owner-Procured Furnishings | OWN-FFE
Technology / AV / IT (owner-procured) | OWN-TECH
Moving / Relocation / Transition Costs | OWN-MOV
Predevelopment Costs (M4Di P1–P3 Fees) | M4DI-PRE
Grant Strategy / Application Support (M4Di) | M4DI-GRT
Program Reserve / Funding Gap Buffer | OWN-RESV
TOTAL OWNER CONTINGENCY & DIRECT COSTS |  | 0 | 0 | 0 | 0 |  | 0 | 0
TOTAL PROJECT INVESTMENT |  | 0 | 0 | 0 | 0 |  | 0 | 0
SUMMARY METRICS
Total Project Investment |  | 0 | 0 | 0 | 0
Hard Cost Only |  | 0 | 0 | 0 | 0
Total Soft Costs |  | 0 | 0 | 0 | 0
Soft Cost as % of Hard Cost |  | - | - | - | -
GC Quote Total |  | "-" | "-" | "-" | 0
GC Actuals Total |  | "-" | "-" | "-" | 0
ROM vs. GC Quote Variance |  | - | "-" | "-" | "-"
LEGEND: Blue text = hardcoded input ¦ Green text = cross-sheet link ¦ Gray row = division rarely applicable (leave blank if not in scope) ¦ Blue background columns (I–K) = Contractor side

## VARIANCE LOG
VARIANCE LOG — Cost Changes Requiring Documentation
Any variance >5% between estimate columns must be documented here before the next ALDi gate is cleared.
Line Item / Budget Category | Gate | ROM Amt ($) | New Est. Amt ($) | Var ($) | Var (%) | Status | Root Cause & Resolution | Approved By
Existing Conditions Contingency — higher than ROM | Gate 2 | 347000 | 420000 | 73,000 | 21.0% | Approved | Hazmat survey confirmed asbestos in 3 locations. Abatement scope added. Owner approved $73K increase. | T. Maxwell / M4Di
HVAC — Phase 1A scope expanded per DDDS requirements | Gate 2 | 310000 | 365000 | 55,000 | 17.7% | Watch | DDDS licensing pre-app required supplemental ventilation for clinical areas. Engineering confirmed scope. | Pending owner
[Next Variance Item — enter as identified] | [5 empty] | On Track

## CHANGE ORDER LOG
CHANGE ORDER LOG — ALDi Gate 3–4
All changes to the contracted GMP/SOV (Column F) must be logged here. Actual Cost (Column G) = Column F + approved COs below.
CO # | Description | Date | GC Amount ($) | Owner Cost ($) | Cumulative COs ($) | CO Running % of GMP | Status | Category | Notes / Justification
CO-001 | Hazardous Materials Abatement — Phase 1 (asbestos, 3 locations) | 04/15/2026 | 73000 | 0 | 73000 | 2.1% | Approved | Existing Conditions | Required; covered by existing conditions contingency draw
CO-002 | Additional HVAC ductwork — DDDS ventilation compliance | 05/01/2026 | 55000 | 0 | 128000 | 3.7% | Pending | Regulatory | DDDS licensing requirement; pending owner authorization
[Future CO — enter as issued] | [6 empty] | Pending
TOTAL APPROVED COs |  |  | 0

## DRAW SCHEDULE
FUNDING DRAW SCHEDULE — Budget vs. Actual Spend
Track each funding source draw against actual project expenditures. Updated monthly with each pay application.
Funding Source | Total Committed ($) | Draw 1 ($) | Draw 2 ($) | Draw 3 ($) | Draw 4 ($) | Draw 5 ($) | Total Drawn ($) | Remaining ($) | % Drawn
Owner / Developer Equity (Dr. Maxwell) | 2500000 | [5 empty] | 0 | 2500000 | 0%
CDFI Construction Loan (NCALL) | 3500000 | [5 empty] | 0 | 3500000 | 0%
HUD CDBG Grant | 750000 | [5 empty] | 0 | 750000 | 0%
Delaware DDDS Capital Support | 500000 | [5 empty] | 0 | 500000 | 0%
Philanthropic Grants (Longwood / Welfare Fdn) | 750000 | [5 empty] | 0 | 750000 | 0%
Owner Contingency Reserve (escrowed) | 300000 | [5 empty] | 0 | 300000 | 0%
TOTAL FUNDING | 8300000 | 0 | 0 | 0 | 0 | 0 | 0 | 8300000 | 0%

## GATE DASHBOARD
ALDi GATE DASHBOARD — Project Status Summary
One-page project status for owner, AE, and lender reporting. Update at each gate.
Project | 0
Owner | 0
AE | 0
M4Di Lead | 0
Building SF | 0
ALDi Start | 0
M4Di ROM (Locked Baseline) | 0
75% DD Estimate | 0
100% CD / GMP (Contracted) | 0
Actual Cost to Date | 0
GC Quote Total (pre-SOV) | 0
GC Actuals to Date | 0
ROM vs. GC Quote Variance
ALDi GATE STATUS
Gate | Name | Target Date | Actual Date | Status | Budget Check | Key Conditions / Notes
Gate 0 | Controls Setup + Budget Baseline Lock |  |  | In Progress | ROM Locked | Project charter issued. Budget baseline = Column D. Procurement calendar set.
Gate 1 | Schematic Design Review |  |  | Pending | Target ±15% | SD documents reviewed. Constructability input provided. DDDS pre-app status confirmed.
Gate 2 | Design Development + 75% DD Estimate |  |  | Pending | Column E entered | DD estimate entered in Column E. Variance log updated. Owner contingency reviewed.
Gate 3 | GMP Execution + SOV Entry |  |  | Pending | Column F = GMP | Contractor SOV entered in Column F. GMP executed. Financing closed.
Gate 4 | Construction Controls + Closeout |  |  | Pending | Column G current | Monthly actual cost updates. CO log maintained. HISTORICAL DB row completed.

## STRATEGY MEMO
M4Di STRATEGY MEMO — The ALDi Budget Tracker as a Revenue Growth Engine
WHAT THIS TOOL IS
The ALDi Design & Construction Budget Tracker is M4Di’s most direct revenue-generating product after the P1–P3 feasibility packages. Where the OI Tool establishes credibility at the predevelopment stage, the Tracker sustains M4Di’s role — and M4Di’s fees — through the full design and construction lifecycle of every project. This memo outlines the strategic case for how M4Di positions, prices, and grows this product.
THE CORE VALUE PROPOSITION
Every AE firm has a fee agreement. Every contractor has a schedule of values. Every owner has a checkbook. What none of them has is a single document that ties all three to the original feasibility estimate and tracks variance across the full project life. That gap is exactly what this Tracker fills — and it is a gap that costs project owners real money every time a design decision quietly moves the budget without anyone’s explicit awareness.
M4Di owns this Tracker. M4Di controls it. The AE and contractor provide inputs at defined gate milestones; M4Di synthesizes, interprets, and reports. This is not an administrative function — it is the delivery backbone that the M4Di strategy describes as ALDi. The Tracker is the physical artifact of that backbone.
THE FOUR-COLUMN ARCHITECTURE IS THE PRODUCT
The four columns — ROM, 75% DD, 100% CD/SOV, Actual — are not an accident of format. They are the intellectual property. Each column transition is a gate event where M4Di adds specific, billable value:
▶ Gate 0 → Column D locked M4Di establishes the baseline. No one can move the ROM without going through M4Di. This is leverage — the ROM is the anchor against which every subsequent decision is measured.
▶ Gate 2 → Column E entered M4Di reviews the 75% DD estimate from the AE. If it exceeds Column D by more than 15%, M4Di flags it, investigates the cause, and either documents a scope-driven explanation or pushes back on the design team. This review function is not available to any other party because only M4Di holds the original takeoff assumptions.
▶ Gate 3 → Column F = GMP M4Di reviews the contractor SOV against Column D. M4Di identifies any scope that was added during design but not authorized through the ALDi gate process. This review catches overruns before they become change orders.
▶ Gate 4 → Column G updated monthly M4Di maintains the running actual cost total from contractor pay applications and owner direct costs. M4Di is the single source of truth for how much has been spent, how much remains, and how the project tracks against the original feasibility commitment.
WHO PAYS FOR IT AND HOW MUCH
The Tracker is included as a component of the ALDi retainer fee. It is not a standalone product — it is the output of the ALDi gates. Current M4Di ALDi pricing for a project of this size ($3.8M–$9.3M total investment) targets $85,000 for full Gate 0–4 controls, of which approximately $25,000–$35,000 of the value is directly attributable to Tracker maintenance and gate reporting.
At scale — with 4–6 active ALDi engagements simultaneously — the Tracker becomes a productized deliverable that drives recurring monthly revenue: setup at Gate 0 (one-time), monthly reporting fees (recurring), and gate review fees (milestone-based). A pricing model of $2,500–$5,000/month for active construction phase reporting is defensible given what the Tracker replaces: a $300–$500/hour owner’s representative doing the same work manually.
THE AE RELATIONSHIP ANGLE
M4D and Aubyn Architecture are the current AE partners. Their relationship to this Tracker is important to define correctly: they are data providers, not owners. At Gate 2, the AE provides their 75% DD cost estimate (or M4Di independently updates Column E). At Gate 3, the contractor provides the SOV that populates Column F. The AE does not control the Tracker and should not — because the Tracker’s independence is exactly what makes it valuable to the owner and to funders.
This does not create an adversarial relationship. The AE’s interest is in having a credible, independent cost control record that demonstrates design-to-budget discipline — which is increasingly required by CDFIs, HUD, and institutional funders. M4Di’s Tracker serves the AE’s professional interest while being owned by the party (M4Di / owner) that has the most incentive to keep it honest.
GROWTH PATH: FROM PROJECT TOOL TO PLATFORM
Near-term (Year 1–2): The Tracker is a manually maintained Excel workbook issued to the owner at Gate 0 and updated by M4Di monthly. M4Di controls the file; the owner and AE receive read-only PDF exports. Revenue = ALDi retainer fee.
Medium-term (Year 2–3): M4Di develops a branded Tracker template tied to the ALDDB Master. Completed project Tracker data flows into the ALDDB at closeout, enriching the firm’s cost intelligence. M4Di offers the Tracker as a standalone service to projects where M4Di is not the full ALDi backbone — a “cost controls only” engagement at $1,500–2,500/month. This expands the client base beyond ALDi engagements.
Long-term (Year 3–5): M4Di licenses the Tracker methodology to CDFIs and community development intermediaries as a due diligence requirement for funded projects. “Every project we fund must maintain an M4Di-format budget Tracker” becomes a funder requirement that creates recurring engagement revenue regardless of whether M4Di is the architect or owner’s rep. This is the standard-setting play from the OI Tool strategy document: own the format, become the required infrastructure.
THE POSITIONING STATEMENT
M4Di’s ALDi Budget Tracker is the only design-to-construction cost control product built specifically for nonprofit and mission-owner community facility projects — connecting the predevelopment ROM estimate to every gate in the design and construction lifecycle. M4Di owns the baseline. M4Di maintains the record. M4Di is the single source of truth from feasibility through closeout.
That is not a feature. That is a category. Build it carefully, maintain it obsessively, and the market value compounds with every project completed.
TEMPLATE VERSION NOTE — This is the M4Di Generic CSI Template v1.0 (April 2026). Built to MasterFormat division structure with subcategories for high-cost divisions. Gray rows = divisions rarely applicable — leave blank rather than delete. Columns I–K are the GC/Contractor mirror columns (Quote + Actuals). Populate project-specific data in COVER tab. ROM values in Column D are locked at Gate 0.